## Slide 1: Texas Nodal Program Implementation TPTF June 6, 2006 Agenda

## Slide 2: Agenda
Rational Unified Process training: 10 mins
  Information….request for action
Market Participant Accountable Executive: 20 mins
  Request approval to proceed
Key Dates for Planning: 30 mins
  Information
  Discussion
  Agreement on next steps

## Slide 3: Texas Nodal Market Participant RUP Training June 6, 2006

## Slide 4: TPTF RUP Training Overview
Summary
Provide overview of RUP (Rational Unified Process)
Basics to writing Use Cases
Two 16-person classes
One day in length
All classes at IBM Austin – downtown
  July 12th (Wednesday)
  August 9th (Wednesday)

## Slide 5: TPTF RUP Training Overview Contd
Logistics
  One day in length
    July 12th (Wednesday)
    August 9th (Wednesday)
    All classes at IBM Austin – downtown
  Registration
    First come, first choice
    Email: Ryan Aldridge (raldridge@ercot.com)
      In case of an emergency Ryan’s office number… 512-248-6832
      Ryan will confirm registration and will send location specifics, etc. via return email

## Slide 6: Texas Nodal TPTF Discussion Nodal Market Participant Executive June 5, 2006

## Slide 7: Nodal Market Participant Executive: Accountable for Market Participant Nodal Readiness
Authority* to include:
Authorized to bind the entity to meet the Market Participants requirements of the agreed Nodal Program Implementation plan and schedule
Authorized to secure adequate Market Participants funds and resources to fulfill the Market Participants obligations to implement the Nodal Program
Authorized to share Market Participants Nodal implementation timeline and project status with ERCOT staff, the ERCOT Board and the PUCT
Authorized to certify Market Participants progress on market readiness
Duties* to include:
Serves as the authoritative point of contact for Market Participant Nodal implementation efforts
Secures the appropriate Market Participants participation at TPTF meetings
Facilitates ERCOT’s verification of progress for the entities represented by the Market Participant
* “or to liaise with those with the authority to commit if required by structure”

## Slide 8: Texas Nodal Key Dates for Planning June 6, 2006

## Slide 9: Preliminary Key Dates
6/7/06 Preferred vendors selected
6/30/06 Start joint requirements, use cases, test cases
        Scenario Development and Choices
9/13/06 ERCOT Board of Directors meeting (commitment: date and dollars)
10/30/06 Rqmts complete and approved *requires TPTF approval
3/31/07 Market Participant interface specs complete
4/1/07 EMS FAT begins
1/1/08 Market Participant SCED offers begin (EDS3)
7/1/08 Market systems, Market Participant offers (EDS4)

## Slide 10: Integrated timeline to September
Week ending dates (Friday)
Jul 14
Sep 15
Jul 28
Jul 21
Jun 16
Jun 9
Jun 2
Jun 30
Jun 23
Jul 7
May 26
Sep 8
Aug 4
Aug 11
Sep 1
Aug 25
Aug 18
MP Engagement & Readiness
NMMS
NMMS Vendor T&M Contract
Mobilize
CSD TPTF approval
NMMS – Requirements, DSOW, Use Case, Conceptual Design Development
CSD TPTF submission
Conceptual System Design
EMS
Proposal
Refinement
TPTF approval
EMS – Requirements, DSOW, Use Case, Conceptual Design Development
TPTF submission
Contract
Mobilize
IDA
Vendors on board 6/30
RUP Training Delivery
Vendor demos
RUP standards definition
Bus process validation
Configuration Mgt Plan
Vendors selected 6/7
Overall architecture 6/7
CSD & Interface doc templates
ERCOT Readiness & Transition
As-is Org Analysis
Org Vision & Principles
EDS Release Strategy – V0.9
Org Options
Org Design
EDS Release Strategy – Socialization
EDS Release Strategy – V1
EDS 3 Release Plan
People Strategy
Capabilities Planning
Testing Strategy
Project Staffing & startup
Nodal Resourcing Template
Nodal Resourcing Template – V1
ERCOT Readiness Criteria
RC link to MPERP
Organization Readiness Plan V1
Draft Release Strategy
Testing Strategy
Release Strategy TPTF submission
EDS3 Release Plan
People Transition plans
EDW
EDW – Architecture definition
EDW – Roadmap definition
Commercial Systems
CM - Contract
FT - Assessment
Reqts TPTF approval
Reqts TPTF submission
Mobilize
Credit Monitoring - Requirements, Use Case Development
Financial Transfer - Requirements, Use Case Development
Disputes
Registration - Conceptual System Design
Registration - Requirements, Use Case Development
Reqts TPTF approval
Reqts TPTF submission
MMS
Reqts TPTF submission
MMS – Requirements, DSOW, Use Case Development
MMS Vendor T&M Contract
Mobilize
Infrastructure
Test Lab Definition
Integrated Testing
MIS
CRR
Requirements, Use Case, DSOW Development
CRR Vendor T&M Contract
Resourcing
Business Implementation plans
Settlements & Billing - Requirements, Use Case Development (multiple drops)
Resourcing
Test Case Template; Procedures
Early Test Cases (EMS/MMS)
Test Script template
Test Case template
Test lab configuration
SAT Criteria
Detailed Planning
Reqts TPTF submission
TPTF Review/Approve Nodal PRRs
TPTF – Review/Approve Business Requirements & Conceptual Systems Designs
Clarification Questions to TPTF
MIS-Posting/Reports/Extracts - Requirements
MIS –UI Requirements from applications identified
TPTF Review/Approve Nodal PRRs
Discuss Readiness Criteria with TPTF
Use Cases