## TPTF Comments & Responses
Document Name: |  |  |  |  | MP Identity Management Requirement Feedback - inf_mp_identity_management_req_v2_3.doc
S.No. | Issuing Entity (Name) | Page Number (Red Line Doc) | Section | Item | Description | Response Type | Reviewer | Reason / Comment
1 | Luminant |  | 1.1 Purpose |  | Requirements have been updated with corresponding release number. Phase 1.5 requirements are at the top of each requirement section. {Note: define the meaning of Phase 1.0 and 1.5} | Accepted | K Blood | Added the following explanation to the section: There are two MPIM releases: o Phase 1.0 - initial MPIM implementation - Deployed on December 7th o Phase 1.5 - first enhancement release to MPIM – Expected to deploy in early March 2008
2 | Luminant |  | 2.2 Future Enhancements |  | The following two enhancements were requested. They should be delivered prior to the 168 Hour Test {What does this statement mean? A specific date or milestone for delivery must be specified and must be sufficiently ahead of the 168 hour test to allow for FAT, ISAT and EDS testing, as appropriate.} | Accepted | K Blood | Added the following explanation to the section: The following two enhancements were requested during Phase 1.0. They should be delivered prior to the 168 Hour Test. Both requirements will be satisfied during Phase 1.5, targeted to deploy in March 2008.
3 | Luminant |  | 2.3 MPIM Components |  | Define the term “provisioning” and delineate the scope of responsibility for each of the listed applications and the INF application that is required to achieve proper operation of the interface. Include data exchange specifications and timing requirements. | Accepted | K Blood | The following text was added to the section: Provisioning: setting of user permissions on applications based on roles. MPIM will provide a mechanism for the MP to assign and unassign roles. MPIM will pass this information to the appropriate applications which will update the user's permissions. In some cases (NMMS) there will be an additional step in granting permissions done at the application level. Additional details will be provided in the design documents.
4 | Luminant |  | 2.4.1 Application Assumptions |  | ERCOT Administrators of the MPIM tool, will access the application directly, NOT through the MIS Portal. – Luminant believes that the application link to the MPIM tool should be through the MIS Portal. | Clarification Provided | K Blood | All MP Users will access MPIM through the Portal. Administrative/Support accounts will access the tool directly. This allows ERCOT application administrators to manage the application without a digital certificate.
5 | Luminant |  | 2.4.3 Application Integration |  | Any improper roles definitions, which provides improper user access, will require a change in the definition of roles by the MPIM administrator. {Explain the meaning of this requirement} | Clarification Provided | K Blood | MPIM administrator will be responsible for creating and editing role definitions and the mapping to application permissions. Through MPIM provisioning, a USA will be able to assign 'roles' to each individual within their company's universe. Each 'role' will have an accompanying definition that should help in determining the assignment. Any improper roles definitions, which provides improper user access, will require a change in the definition of roles within the MPIM application realm. This is to say, ‘the definitions’ are managed with the delivery of the application not as content within.
6 | Luminant |  | 3.7 Out of Scope Requirements |  | Please explain the need for this section. If these requirements are related to a phase 1 or other implementation please specify such. | Accepted | K Blood | The following text was added to this section: Requirements listed in this section are not targeted for an MPIM release. They are contained within this document for tracking purposes for consideration in later releases of MPIM.
7 | Luminant |  | 3.10.7 Application Provisioning |  | Note: The following requirements convey no information and are not acceptable as is. This section must define the relationship that will exist between INF and each of the applications. Detailed design can follow based on the defined relationship. | Clarification Provided | K Blood | 1. Updated each application requirement (SS21, SS19, SS20, SS22, SS23) with the following text: "MPIM will provide provisioning information (e.g. user data and access attributes) to <application name>" 2. MPIM provides notifications of the success/failure of the provisioning process. (SS23 and SS24)

## Data Entry Lists
Response | Description
Accepted | Comment accepted and requirements document updated as per the comment.
Clarification Provided* | Clarification provided and requirements document updated to clarify
Clarification Provided | Clarification provided and no updates made to the requirements document.
Pending | Issue is not resolved yet. All pending issues will be dispositioned to a punch list and resolved later. These issues need more time and coordination across multiple Nodal projects.
Rejected | Comment rejected as it does not comply with Nodal Protocols.