## Slide 1: Texas Nodal Program Update
Jerry Sullivan

## Slide 2: Overall program status remains amber
Nodal
Delivery
Quality
Schedule
Cost
Cost
Schedule
Scope / Quality
Legend
Summary
Green
Currently the project to date costs are under budget. However, the latest forecasted spending in 2008 indicates we may be over the 10% threshold. The focus on finding efficiencies and savings without compromising quality or deferring / delaying protocol intents. We will work with TPTF on these issues. May ask for increased contingency for 2008.
Amber
Amber
Currently fully aligned with protocols.
We are working with TPTF on any possible deferrals.
Red
Amber
Green
Estimate at Complete = <$263m
Estimate at Complete = < $263m + 10%
Estimate at Complete = >$263m + 10%
Go-live = 12/1/08
Go-live = <30 days+
Go-live = >30 days+
Program is aligned with current protocols
Program is aligned to previous protocol version
Program is not aligned to protocols
Amber
Current product quality is not sufficient for Nodal launch
Most Nodal products currently achieve quality standards
All Nodal products currently achieve quality standards
Issues around the importing and exporting of the Network Model (CIM Importer / Exporter) are greatest threat to project schedule at this time. Much progress has been made in last two weeks (since TPTF meeting)
Test results are being managed in Quality Center and results are being used to track defects for resolution

## Slide 3: TNMIP – Various ways in which we’ve measured status
Nodal
Delivery
Quality
Schedule
Cost
1.
2.
3.
4.
5.
6.
7.
8.
These are examples of various communications graphics to illustrate the status of Nodal.
The web page scorecard (graphic 4, 5, 6) provides the best tool for detailed, objective metrics on quality and schedule..
All other items 1, 2, 3, 7 and 8 provide other ways to gauge status, schedule and costs.

## Slide 4
We are proactively managing primary Nodal Delivery “ABB” Risk Factors
 | I | II | III
What? | ERCOT Resources will perform more of the work | ABB Does Value Engineering (do it smarter) | ERCOT / ABB / MP Revise detail design (change approach of design, not requirements)
Impact on Cost | Reduces ABB hours and lowers cost | Reduces ABB hours and lowers cost | Reduces ABB hours and lowers cost
Impact on Schedule | Enables 4/22/08 delivery to FAT | Enables 4/22/08 delivery to FAT | Enables 4/22/08 delivery to FAT
Impact on Confidence | Increases confidence | Increases confidence | Increases confidence
$
$
$
Schedule
Schedule
Schedule

## Slide 5: MMS Project has plan to deliver quality product that meets requirements

## Slide 6
Projects working hard to deliver to schedule
Project | Achievements and Outlook
EDS | Point-to-point check out 99%, 1% error rate; 1 MP outstanding (Extend) due to MP ICCP server implementation SE tuning progressing in the right direction, but lack of combined cycle and data error handling causing issues. Convergence rate at 50 MW. SCED is executing and publishing LMPs to market participants through MIS and ICCP. Issue analysis on-going. MPs encouraged to bring up LMPs questions on weekly EDS calls Working with TPTF on LMP reasonableness understanding
MMS | MMS Release 2 (DAM & RUC) is in FAT at ERCOT – Planned to deploy to EDS in Jan 2008 on time Working on CIM Importer issues with ERCOT and other vendors All functionality required for 168-hour test scheduled to enter FAT by 4/22/08 and to clear FAT by 6/30/07
CRR | Core product is in FAT at ERCOT – Planned to deploy to EDS in late Jan 2008 or early Feb 2008 based on HW and FAT completion Target start of EDS CRR auction in Feb 2008
EMS | EMS Release 3A, 3B and 5.7 OS upgrade completed FAT with defects Moving to EDS for start of LFC (Release 6) testing in early Jan 2008 (on schedule) Working on CIM exporter and Importer issues with ERCOT and other vendors
COMS | Settlement & Billing (core calculations) in FAT at ERCOT, iteration 2 planned FAT release in Jan 2008, on schedule CMM (core credit calculations) completed FAT at ERCOT with defects (all fixed or deferred). On schedule to deliver to iTEST
MPIM | MPIM 1.0 Released to Sandbox, and MP training delivered Next MPIM release 1.5 progressing on schedule
MIS | MMS User Interface development in progress, but schedule is tight and date may be threatened, workaround available Additional MIS releases scheduled corresponding to application releases
EIP | DAM/RUC data submissions in FAT at ERCOT – on target deployment to EDS in Jan 2008
NMMS | FAT testing running late due to Citrix issues (new security layer). Start of Market Trials may be threatened CIM Importer issues continues to be addressed with ERCOT and other vendors.
Readiness Metrics | 2nd round Market Participant and ERCOT Executive readiness self-reporting completed. Results will be published within the week.
Training | 10 of 15 courses now available for enrollment (Instructor-led ). New December releases: NOIE QSE Operations, Settlements More that 4000 individuals have attended training sessions
Both near-term Jan 15 and long-term Dec 1 goals are threatened, but achievable

## Slide 7: Budget Update - Cost Element Summary

## Slide 8: Budget Update – Project Summary

## Slide 9: Budget Update – Latest Forecast of Spending & Anticipated Requirements