|  |  |  |  | System Planning Division |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report to Reliability and Operations Subcommittee for December 2007 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
| Item |  |  |  |  |  |  |  |  |
| 1. | ERCOT is currently tracking 220 active generation interconnection requests totaling almost 97,000 MW. This includes over 41,000 MW of wind generation. |  |  |  |  |  |  |  |
| 2. | Regional Planning is currently reviewing proposed transmission improvements with a total cost of $133.25 M. |  |  |  |  |  |  |  |
| 3. | The 2007 Constraints and Needs Report is now posted on the ERCOT Operations and Planning website: http://oldercot.ercot.com/tmaps |  |  |  |  |  |  |  |
| 4. | An update to the 2007 Capacity Demand and Reserves Report has been posted on the ERCOT Operations and Planning website: http://oldercot.ercot.com/tmaps |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1.	New Generation Beginning Commercial Operations	1

1.2.	Active Generation Interconnection Requests	1

1.3.	Potential Future Generation Interconnections	1

2.	Regional Planning Group Project Reviews	3

3.	Other Notable Activities	3

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” data folder posted in the “Operations and System Planning” data area on the ERCOT website.

## New Generation Beginning Commercial Operations

- Barton Chapel Wind Farm, 120 MW in Jack County

- Snyder Wind Farm, 63 MW in Scurry County

## Active Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY BEING PROCESSED |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Currently tracking 220 active generation interconnection or change requests As of January 3, 2008 |  |  |  |  |  |
|  |  | North | South | West | Total |
| Security Screening Study |  | 7 | 11 | 20 | 38 |
| SSS Completed |  | 11 | 5 | 11 | 27 |
| Full Interconnect Study |  | 21 | 30 | 63 | 114 |
| FIS Completed |  | 0 | 2 | 2 | 4 |
| Interconnect Agreement Completed |  | 7 | 4 | 26 | 37 |
| Capacity for Grid, MW |  | 28,049 | 30,512 | 38,226 | 96,787 |
| Wind Capacity, MW |  | 1,963 | 4,139 | 35,481 | 41,583 |

| Fuel | Public (MW) | Non-public (MW) | Total (MW) |
| --- | --- | --- | --- |
| Natural gas | 3,708 | 27,936 | 31,644 |
| Nuclear | 9,186 | 6,400 | 15,586 |
| Coal | 4,841 | 2,708 | 7,549 |
| Wind | 9,841 | 31,742 | 41,583 |
| Other | 0 | 425 | 425 |
| Totals | 27,576 | 69,211 | 96,787 |

## Potential Future Generation Interconnections

The table below summarizes the publicly known potential future generation projects for the ERCOT region.  (IA=Interconnect Agreement, PL=Public Letter)

| FUTURE GENERATION INTERCONNECTIONS (PUBLIC PROJECTS) As of September 4, 2007 |
| --- |
| INR # | Site Name | Status | County | Region | Fuel | In Service Date | MW into Grid | Change from Last Report |
| 07INR0034 | Wolf Ridge Windfarm | IA | Cooke | North | Wind | Oct-07 | 201 |  |
| 07INR0049 | J T Deely Upgrade | IA | Bexar | South | Coal | Nov-07 | 80 |  |
| 07INR0045 | Airtricity Champion Wind Farm | IA | Scurry | West | Wind | Dec-07 | 126 |  |
| 07INR0028 | Goat Wind 1 | IA | Sterling | West | Wind | Dec-07 | 150 |  |
| 04INR0017 | Ocotillo Wind Farm 1 | IA | Howard | West | Wind | Dec-07 | 59 |  |
| 07INR0010 | Stanton Wind 1 | IA | Martin | West | Wind | Dec-07 | 101 |  |
| 03INR0034 | Silver Star 1 | IA | Erath | North | Wind | Dec-07 | 60 |  |
| 07INR0045 | Roscoe 1 | IA | Scurry | West | Wind | Mar-08 | 209 |  |
| 07INR0030 | Louis (Buffalo Gap 3) | IA | Nolan | West | Wind | Apr-08 | 138 |  |
| 06INR0036 | Quail Run Energy Center 2 | IA | Ector | West | Gas | May-08 | 275 |  |
| 06INR0035 | Colorado Bend Energy Center 2 | IA | Wharton | South | Gas | Jun-08 | 275 | Changed date |
| 07INR0022 | Airtricity Panther Creek Wind Farm | IA | Howard | West | Wind | Jun-08 | 150 |  |
| 04INR0011 | Cottonwood Wind | IA | Shackelford | West | Wind | Aug-08 | 100 |  |
| 04INR0011 | Mesquite Wind Phase 4 | IA | Shackelford | West | Wind | Aug-08 | 136 |  |
| 03INR0030 | Wild Horse Wind Farm 2 | IA | Cottle | West | Wind | Aug-08 | 39 |  |
| 08INR0038 | M Bar Wind | PL | Andrews | West | Wind | Sep-08 | 194 |  |
| 07INR0025 | Airtricity Lamesa Wind Plant | IA | Dawson | West | Wind | Oct-08 | 183 |  |
| 07INR0037 | Bull Creek Wind Plant | IA | Borden | West | Wind | Oct-08 | 180 |  |
| 07INR0045 | Airtricity Inadale | IA | Scurry | West | Wind | Nov-08 | 212 |  |
| 07INR0045 | Airtricity Pyron Wind Farm | IA | Scurry | West | Wind | Nov-08 | 303 |  |
| 06INR0022 | Penascal Wind Farm 1 | IA | Kenedy | South | Wind | Dec-08 | 202 |  |
| 08INR0037 | Airtricity Panther Creek 2 | IA | Howard | West | Wind | Dec-08 | 220 |  |
| 08INR0053 | Elbow Creek Wind Project | IA | Howard | West | Wind | Dec-08 | 117 |  |
| 04INR0011 | Hackberry Wind Farm | IA | Shackelford | West | Wind | Dec-08 | 165 |  |
| 07INR0005 | Notrees-1 | IA | Ector | West | Wind | Dec-08 | 151 |  |
| 07INR0029 | South Trent Wind Farm | IA | Taylor | West | Wind | Dec-08 | 101 |  |
| 06INR0026 | Wild Horse Mountain | IA | Howard | West | Wind | Dec-08 | 120 |  |
| 05INR0015 | Gulf Wind 1 | IA | Kenedy | South | Wind | Dec-08 | 283 | Changed capacity |
| 08INR0059 | Gray Wind Project | PL | Borden | West | Wind | Dec-08 | 141 |  |
| 08INR0018 | Gunsight Mountain | IA | Howard | West | Wind | Dec-08 | 120 |  |
| 08INR0025 | Pistol Hill Energy Center | PL | Ector | West | Wind | Dec-08 | 300 |  |
| 09INR0026a | Sterling Energy Center | PL | Sterling | West | Wind | Dec-08 | 200 |  |
| 07INR0011 | Turkey Track Energy Center | PL | Nolan | West | Wind | Dec-08 | 300 |  |
| 08INR0046 | Bosque Expansion | IA | Bosque | North | Gas | Mar-09 | 255 |  |
| 08INR0047 | Buffalo Gap 4 | PL | Nolan | West | Wind | Mar-09 | 378 |  |
| 09INR0028 | V H Braunig 6 | PL | Bexar | South | Gas | May-09 | 185 |  |
| 08INR0040 | Lenorah Project | PL | Martin | West | Wind | May-09 | 350 |  |
| 09INR0060 | Wind Tex Stephens Wind Farm | PL | Borden | West | Wind | May-09 | 141 |  |
| 09INR0045 | Sand Hill Peakers | PL | Travis | South | Gas | Jun-09 | 90 |  |
| 09INR0027 | Winchester Peaking Plant | PL | Fayette | South | gas | Jun-09 | 178 | Changed capacity |
| 09INR0036 | McAdoo Energy Center II | PL | Dickens | West | Wind | Jun-09 | 500 |  |
| 09INR0026 | Sterling Energy Center | PL | Sterling | West | Wind | Jun-09 | 300 |  |
| 08INR0003 | Sandow 5 | IA | Milam | North | Coal | Jul-09 | 581 |  |
| 05INR0015 | Gulf Wind 2 | IA | Kenedy | South | Wind | Sep-09 | 400 |  |
| 09INR0015 | Comanche Peak 1&2 Upgrade | PL | Somervell | North | Nuclear | Oct-09 | 86 |  |
| 03INR0030 | Wild Horse Wind Farm 1 | IA | Cottle | West | Wind | Nov-09 | 60 |  |
| 09INR0006 | Oak Grove SES 1 | IA | Robertson | North | Coal | Nov-09 | 855 |  |
| 09INR0034 | Gatesville Wind Farm | PL | Coryell | North | Wind | Dec-09 | 200 |  |
| 09INR0037 | Scurry County Wind III | PL | Scurry | West | Wind | Mar-10 | 350 |  |
| 09INR0006 | Oak Grove SES 2 | IA | Robertson | North | Coal | May-10 | 855 |  |
| 06INR0006 | Cobisa-Greenville | PL | Hunt | North | gas | May-10 | 1750 | Changed date |
| 09INR0002 | J K Spruce 2 | IA | Bexar | South | coal | Jun-10 | 750 |  |
| 09INR0001 | Sandy Creek 1 | IA | McLennan | North | coal | Sep-10 | 925 |  |
| 05INR0015 | Gulf Wind 3 | IA | Kenedy | South | Wind | Sep-10 | 400 |  |
| 12INR0003 | Thockmorton Wind Farm | PL | Throckmorton | West | Wind | Dec-10 | 400 |  |
| 11INR0007 | Mountain Creek | PL | Dallas | North | Gas | Apr-11 | 700 |  |
| 11INR0001 | Twin Oaks 3 | PL | Robertson | North | coal | Jun-11 | 630 |  |
| 07INR0004 | Pampa Energy Center | IA | Gray | West | Coal | May-12 | 165 |  |
| 09INR0024 | B&B Panhandle Wind | PL | Carson | West | Wind | Jun-12 | 1001 | Changed date |
| 12INR0004 | Fort Concho Wind Farm | PL | Tom Green | West | Wind | Jul-12 | 400 |  |
| 15INR0002 | Comanche Peak 3 and 4 | PL | Somervel | North | Nuclear | Jan-15 | 3200 |  |
| 15INR0008 | STP 3 and 4 | PL | Matagorda | South | Nuclear | Jan-15 | 2700 |  |
| 11INR0011 | Victoria City Nuclear | PL | Victoria | South | Nuclear | Jan-15 | 3200 |  |
|  |  |  |  |  |  | Total | 27,576 |  |

# Regional Planning Group Project Reviews

- Luminant has submitted two interrelated, yet independent projects for review.  The first project is the planned upgrade of the Tyler Northeast to Tyler East 138 kV line, which was planned to be complete in May 2012, but will be accelerated to May 2009 with an estimated total project cost of $4 M.  The second related project is the addition of the Tyler Grande (Tyler Southeast) 345/138 kV autotransformer and an increase in the planned capacity of Tyler Grande (Southeast) to Tyler South from 326 MVA to 400 MVA.  The second project is planned to be complete in May 2009 with a cost of approximately $10 M and will require ERCOT Board approval due to the new 345/138 kV Tyler Grande switching station and associated autotransformer. This project is in ERCOT Independent Review.

- Oncor submitted a project to rebuild the Big Spring – Chalk – McDonald Road 69 kV line.  This project will alleviate overloads due to new wind projects on the Morgan Creek to McDonald Road 138 kV circuit by adding a new 138 kV from Big Spring into McDonald Road on double circuit 138/69 kV structures that will replace the existing 69 kV single circuit structures.  The cost of the project is $10.8 M and due for completion in December 2008.  This project is now in ERCOT Independent Review.

- Oncor submitted a two phase project to relieve congestion that will occur when two new Wind units are connected to the transmission system in the Lamesa area.  The first phase of the project will upgrade both ends, but not the middle of the Lamesa to Bluff Creek 138 kV line, rebuild the Bluff Creek to China Grove 138 kV line, rebuild the Lamesa to Ackerly Vealmoor 69 kV line to 138/69 kV double circuit, rebuild the Lamesa 138 kV switching station, and build a new 138 kV Ackerly Vealmoor station.  All transmission rebuilds will utilize double circuit construction with one circuit in place, except the Lamesa to Ackerly Vealmoor 138/69 kv double circuit.  The cost of the first phase of these upgrades is $40.3 M.  The second phase of the project has additional work to be done if a third wind unit signs and interconnect agreement that will add second circuits to all rebuilt lines and include station upgrades at China Grove and Big Spring.  The additional cost of the second phase upgrades is $40.5 M.  The first phase was included as an economic project in the 2007 Five Year Plan.  The second phase will be studied separately.

- Oncor submitted a project to rebuild the Elkton to Athens North Tap 138 kV line due to post contingency overloads, age of equipment, and ERCOT OOM instructions.  This cost this project is $20.4 M and would be complete by peak 2010.  It is currently in the comment phase.

- Oncor submitted a two part project based on the 2007 Five Year Plan that will replace the 517 MVA 345/138 kV autotransformer at Roanoke Switch with a 600 MVA autotransformer in 2009 at a cost of $7.25 M.  In 2010 the old Roanoke auto will be installed at Eagle Mountain which showed high congestion levels in the Five Year Plan at a cost of $2.0 M.  This project is in the comment phase.

# Other Notable Activities

- Draft results for Phase II of the Wind Impact/Ancillary Services study are expected next week (about 1/20).  GE is evaluating 4 scenarios of wind capacity on the system:  5,000 MW, 2 scenarios of 10,000 MW, and 15,000 MW.  Phase I of the study (a statistical analysis of increased variability with increasing amounts of wind) was completed in October.  GE is currently finalizing Phase II of the study, an analysis of the ramping capabilities of units in the existing ERCOT generation fleet and determination of required ancillary services.

- CREZ Study (SB20)

- System Planning is analyzing transmission solutions as part of the CREZ Transmission Optimization Study.  The next RPG-CREZ Task Force meeting will be held on January 25, 2008.

- Individual 2008 Q1 TPIT Worksheets were sent to TO’s.  Data is due back Friday, February 1st.

- The following information is now available at http://oldercot.ercot.com/tmaps

  - The updated 2008 Data Set A cases

  - The SSWG 2008 Data Set B cases

  - The 2007 Constraints and Needs Report

The 2007 Electric System Constraints and Needs report, filed in late December with the Public Utility Commission (PUC), identifies and analyzes existing and potential constraints in the transmission system that could pose reliability concerns or increase costs to the electric power market, and ultimately, to Texas consumers.   The report includes $3 billion in proposed projects for the next five years, expected to add 2,538 miles of transmission lines and additional autotransformer capacity.

The major 345-kV transmission lines planned include:

- 88 circuit miles, Bell County East – Twin Oaks, operational 2012

- 198 circuit miles, Red Creek – Killeen line, operational 2012

- 38 circuit miles, Oklaunion – Bowman line, operational 2012

- 22 circuit miles, Nacogdoches – Lufkin line, operational 2012

- 103 circuit miles, Clear Spring – Salado, operational 2010/2011

- 110 circuit miles, San Miquel – Laredo, operational 2010

- 7 circuit miles, West Levee – Norwood (Dallas/Fort Worth), operational 2009

  - An update to the 2007 CDR Report

- Summary of changes:

|  | - 2008 | - 2009 | - 2010 | - 2011 | - 2012 | - 2013 |
| --- | --- | --- | --- | --- | --- | --- |
| - Reserve Margin (Dec 2007) | - 13.1% | - 12.1% | - 14.0% | - 12.6% | - 10.5% | - 8.2% |
| - Reserve Margin (May 2007) | - 12.6% | - 10.1% | - 8.3% | - 6.7% | - 5.9% | - n/a |

  - Reserve margins will drop in 2008 due to the exclusion of 510 MW of mothball returns anticipated in the May CDR.  However, there are known re-powering projects awaiting interconnection agreements.

  - Increases in Reserve Margins for 2009 can be attributed to 2 units (Sandow and the Bosque Expansion) for 836 MW.