## Slide 1: 2007 RO Projects Financial Overview Retail Market Subcommittee January 9, 2008 Hope Parrish Market Operations Division Projects Organization

## Slide 2: 2007 RO PPL
Unplanned 2006
Carry-over Projects
(Green Shaded Area)
Projects ABOVE the
current Capability Line
(Orange Shaded Area)
Projects BELOW the
current Capability Line
(Yellow Shaded Area)

## Slide 3: Unplanned 2006 Carry-Over Projects
No Status Change on these projects
  PR-60006_01 Rescheduled for 02/09/2008 release date due to required additional time to complete testing. Limited Vendor and ERCOT resource availability over holidays to resolve issues.

## Slide 4: Projects ABOVE the Capability Line
PR-50088_01 Moved to “Planning”
PR-60007_01 As noted in ERCOT comments on PUCT Project 33049, ERCOT will recommend thru the proper stakeholder process to consolidate with PR-60008_01 Terms and Conditions in an effort to expedite delivery
Notes: 50061_01 Moved to ON Hold: Freed up approx. $120k, however not recommended for release by CART

## Slide 5: Projects BELOW the Capability Line
No status change on these projects
Notes: ERCOT will continue to evaluate the projects under the line to determine if we can move anything up. Currently the items just below the line are funded with the 2008 PPL

## Slide 6: Financial Overview as of 12/30/2007
RO PPL Budget Activity | Amount | Notes/comments
Approved RO Capability Line Budget Funding | $4.88M | Current approved RO funding allocation Designates where the capability line falls Updated $5.17 budget to $4.88 to reflect accurate funding
Current Forecast Spend of projects above the Capability Line | ~$3.17M | Based on current expectations and run rates for active and not started projects above the capability line Budget range of $2M – $3M
Budget Variance | ~$1.7M | Budget Variance is difference between RO Capability Line Budget Funding and Current Forecast Spend of projects above the Capability Line $245k resulting from projects running under budget $2.012M due to amounts forecasted into 2008 for current projects -$287k resulting from project budget corrections -$265k resulting from taking PR-60006_01 back to execution

## Slide 7: Budget Variance Allocation
Below is the updated view of under spend categories. These categories will be monitored throughout the year to assess potential reallocations.
MO/RO Budget Variance
2007; $ thousand
$2506
$0
$0
RO Total = $1760
No Concerns
Should be monitored
Should not Release
CART, COPS, and RMS have all reviewed the MO-RO portfolio and acknowledged the release of $2.5M from the overall portfolio budget variance of approx. $2.506M.
RO Release of $1760k

## Slide 8: Questions / Contact
Hope Parrish
Project Manager, MO DPO
Market Operations Divisional Projects Organization
ERCOT
(512) 248-6522
hparrish@ercot.com