PMO

Working Readiness Metric Inventory

v0.04

December 20, 2007

Table of Contents

Revision History	4

ERCOT Internal Metrics	5

E2 - Verify ERCOT Performance Monitoring Test Plan	5

E4 - Transition Priceing Mechanisms	6

E7 - Validate EDW Access & Accuracy of Postings Required by the WEMM and PUCT Rules	7

E10 - Validate EDW Commercial Systems Access & Accuracy	8

E11 - Validate EDW Compliance Data Access	9

E14 - Verify QSE Performance Monitoring Test Plan	9

E15 - Verify TSP Performance Monitoring Test Plan	10

Energy Management Operations Metrics	11

EMO3 - Verify Outage Evaluation System Functionality	12

EMO4 - Run 7 Day Stability Test	12

EMO8 - Conduct EECP Test	14

EMO8 - Conduct EECP Test	14

Network Model Management Metrics	15

Market Operations Metrics	15

MO1 - Operate DA Market for 7 Days	15

MO2 - Operate 7 Day market with RUC	16

MO3 - Verify Supplemental Ancillary Services Market (SASM)	16

MO6 - Verify DAM Ancillary Services [what is the difference between this an MO1; both energy and AS are purchased in the DAM and can not be executed separately because of the co-optimization of energy and AS]	17

Contingency Metrics	18

C1 - Contingency Plan for Weekly, Daily and Hourly RUC Failure	18

C2 - Contingency Plan for DAM Failure	18

C3 - Contingency Plan for ICCP Data Failure	19

C4 - Contingency Plan for SCED Failure	19

C5 - Contingency Plans for Key Settlement and Financial Transfer Processes	20

C6 - Develop Plan for SE Failure	20

C7 - Contingency Plan for a Backup Facility	21

C8 - Contingency Plan for Portal/API Failure	21

C9 - Contingency Plan for Site Unavailability	22

C10 - Verify Single Point of Failure Recovery EMS/MMS/NMMS/CRR/COMS	22

IMM Metrics	23

IMM1 - Market Monitor Systems Capability	23

Overall Readiness Metrics	24

R0 – Market Participants Operations Readiness	24

R1 - Nodal Readiness Declaration	24

R2 - Develop Texas Nodal Market Launch Plan	24

# Revision History

| Date | Author | Version Number | Description of Revision |
| --- | --- | --- | --- |
| 11/30/07 | Chris Wilkinson | 0.01 | Initial version. MP11 and MP19 for TPTF review on 12/4/07 |
| 12/05/07 | Chris Wilkinson | 0.02 | Results of 12/3/07 TPTF meeting. Moved MP11 redlined to Active inventory pending TAC approval |
| 12/05/07 | Chris Wilkinson | .03 | Copied remaining metrics from Future inventory and updated with Reliant and Luminant comments in preparation for 12/19/07 meeting |
| 12/20/07 | Chris Wilkinson | .04 | Moved metrics approved by TPTF to Active inventory for TAC approval: MP19 - Load Serving Entities Engagement and Readiness MP16 - MP EDS-4 Trials Participation MP18 - Mapping of Resources and Loads in Private Area Networks is Complete CO1 - Settle Market for 7 Days and Provide Appropriate Extracts CO2 - Verify Dispute Process of 168 Hour Test CO3 - Verify DAM Settlement Statements CO4 - Zonal/Nodal Coordinated Settlement Operations CO5 - Verify RTM Settlement Statements CO6 - Verify RTM Settlement Invoices CO7 - Verify DAM Invoices CO8 - Verify CRR Auction Invoices CO9 - Verify Financial Transfer and Processing CO10 - Verify Credit Calculations EMO12 - Network Operations Model and SE Performance EMO13 - ERCOT Operating Personnel and Facilities Readiness MO7 - ERCOT Operating Personnel and Facilities Readiness |

# ERCOT Internal Metrics

### E2 - Verify ERCOT Performance Monitoring Test Plan

| Reported By: ERCOT |  |  | EDS: Not Defined |
| --- | --- | --- | --- |
| Target Completion: EDS 4 - 168 Hour Test Major Milestone less 30 days |  |  |  |
| Metric Description: ERCOT shall develop a detailed test plan to ensure adherence to the ERCOT Performance Monitoring Requirements |  |  |  |
| Background: It is the intent of this metric to ensure that the systems, access and capabilities are in place to monitor ERCOT performance in the Nodal Market. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that ERCOT is ready to begin the monitoring activities as specified in Section 8.2: Performance Monitoring and Compliance. Readiness will be achieved when the ERCOT Performance Monitoring plan is approved by TPTF and posted. ERCOT Performance Monitoring Test Plan Exists |  |  |  |
| Reporting Data Sources: Notification of Capability to Monitor ERCOT Compliance / ERCOT Readiness PM |  |  |  |
| References | TP: 5.4.12 | TNP: 8.2 |  |

### E4 - Transition Priceing Mechanisms

| Reported By: ERCOT |  |  | EDS: Not Defined |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 90 days |  |  |  |
| Metric Description: ERCOT and the Market Participants shall develop mechanisms to be implemented for a limited period after Nodal Go-Live. |  |  |  |
| Background: This metric will ensure that a plan for limiting pricing of energy and ancillary services is in place during the early stages of nodal market start-up has been created. |  |  |  |
| Criteria: Readiness will be achieved when the ERCOT Board of Directors approves a NPRR establishing the mechanisms. NPRR is Approved |  |  |  |
| Reporting Data Sources: NPRR / ERCOT Readiness PM |  |  |  |
| References | TP: 6.1 (m) | TNP: N/A |  |

### E7 - Validate EDW Access & Accuracy of Postings Required by the IMM and PUCT Rules

| Reported By: WEMM & ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: EDW 6 FAT Milestone plus 90 days |  |  |  |
| Metric Description: ERCOT shall provide access to accurate data via the EDW and postings to the MIS. |  |  |  |
| Background: The intent of this metric is to ensure access to accurate data via the EDW and the MIS. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that data access is available to the IMM via the data warehouse and the MIS as required by PUCT rules. Readiness will be met when source system data is accurately represented in the EDW and is accessible by the IMM and when data required by PUCT Rules to be posted is accessible by Market Participants. Integration Testing Team attests to the successful completion of those the testing of the WEMM component of the EDW. IMM confirms ability to access EDW Market Particpants are able to view requried postings on the MIS |  |  |  |
| Reporting Data Sources: Notification from Integration Test Team Attesting to EDW accuracy / Notification from WEMM Attesting EDW Access / ERCOT EDS 4 PM |  |  |  |
| References | TP: N/A | TNP: 17.3.2 |  |

### E10 - Validate EDW Commercial Systems Access & Accuracy

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: EDW 6 FAT Milestone plus 90 days |  |  |  |
| Metric Description: ERCOT shall provide access to accurate Commercial data via the EDW. |  |  |  |
| Background: The intent of this metric is to ensure access to accurate data via the EDW. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that commercial data access is available via the data warehouse. Readiness will be met when source system data is accurately represented in the EDW and is accessible by ERCOT Commercial Operations. Integration Team verifies consistency of EDW data compared to respective source systems ERCOT Commercial Operations confirms ability to access data within the EDW |  |  |  |
| Reporting Data Sources: Notification from Integration Test Team verifying accuracy of EDW data / Notification from Commercial Operations Attesting EDW Access / ERCOT EDS 4 PM |  |  |  |
| References | TP: N/A | TNP: 17.3.2 |  |

### E11 - Validate EDW Compliance Data Access

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: EDW 6 FAT Milestone plus 90 days |  |  |  |
| Metric Description: ERCOT shall provide access to accurate Compliance Related data via the EDW. |  |  |  |
| Background: The intent of this metric is to ensure access to accurate data via the EDW. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that Compliance Dept. data access is available via the data warehouse. Readiness will be met when source system data is accurately represented in the EDW and is accessible by ERCOT Compliance. Integration Testing Team verifying the successful completion of those test scripts related to the Compliance component of the EDW. Compliance confirms ability to access EDW |  |  |  |
| Reporting Data Sources: Notification from Integration Test Team Verifying Accuracy of EDW data / Notification from Compliance verifying EDW Access / ERCOT EDS 4 PM |  |  |  |
| References | TP: N/A | TNP: |  |

### E14 - Verify QSE Performance Monitoring Test Plan

| Reported By: ERCOT |  |  | EDS: Not Defined |
| --- | --- | --- | --- |
| Target Completion: EDS 4 - 168 Hour Test Major Milestone less 30 days |  |  |  |
| Metric Description: ERCOT shall develop a TAC-approved QSE/Resource monitoring Program. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT has developed a program to monitor Generating Resource Performance Requirements as required in the protocols. |  |  |  |
| Criteria: The Readiness Team will verify that a QSE/Resource monitoring Program is documented and approved and that a corresponding test plan has been successfully executed. Plan developed, approved by TAC, and implemented |  |  |  |
| Reporting Data Sources: QSE Performance Monitoring Plan / ERCOT Readiness PM |  |  |  |
| References | TP: 5.4.12 | TNP: 8.1 |  |

### E15 - Verify TSP Performance Monitoring Test Plan

| Reported By: ERCOT |  |  | EDS: Not Defined |
| --- | --- | --- | --- |
| Target Completion: EDS 4 - 168 Hour Test Major Milestone less 30 days |  |  |  |
| Metric Description: ERCOT shall develop a TAC approved TSP Performance Monitoring program. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT has developed a plan to monitor performance of TSP as required in the protocols. |  |  |  |
| Criteria: The Readiness Team will verify that a TSP monitoring Program is documented and approved and that a corresponding test plan has been successfully executed. Plan developed, approved by TAC, and implemented |  |  |  |
| Reporting Data Sources: TSP Performance Monitoring Plan / ERCOT Readiness PM |  |  |  |
| References | TP: 5.4.12 | TNP: 8.3 |  |

# Energy Management Operations Metrics

### EMO3 - Verify Outage Evaluation System Functionality

| Reported By: MP & ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: EDS-4 Release 9 Complete |  |  |  |
| Metric Description: This metric will measure the ability of ERCOT to manage the Outage Management Process to include the use by Market Participants and also include a temporary Outage Minimization Plan for use in the first weeks of the Nodal Market. |  |  |  |
| Background: It is the intent of this metric to ensure that Market Participants can schedule, change and receive outage notifications, that the ERCOT Operators can distinguish between forced and scheduled outages and that an Outage Minimization Plan is created for the Nodal Market Go Live. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that ERCOT developed an Outage Management System capable of efficiently managing Outages submitted by Market Participants . Readiness will be met when the Outage Minimization plan is published and when the Outage Management Test has been successfully completed. An approved Outage Minimization Plan is implemented A test of the Outage Management Process is completed |  |  |  |
| Reporting Data Sources: Outage Minimization Plan/ Test results of Outage Management Test / EDS 4 PM |  |  |  |
| References | TP: 5.4.10 (1) | TNP: |  |

### EMO4 - Run 7 Day Stability Test

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: Go Live Less 30 days |  |  |  |
| Metric Description: ERCOT will operate all Texas Nodal Market functions including Day Ahead and energy management activities such as SCADA, SE, Network Security Analysis, Transmission Constraint Management, SCED, RUC LFC , and RT settlements for 168 continuous hours. |  |  |  |
| Background: The intent of this metric is to ensure that the EMS is stable for a prolonged period of time without significant data base errors and software failures. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that ERCOT successfully operated all Texas Nodal Market functions including Day Ahead and energy management activities such as SCADA, SE, Network Security Analysis, Transmission Constraint Management, SCED, RUC, LFC RT Setttlements for 168 continuous hours. Readiness will be met when the EMS successfully supports SCADA, Network Security Analysis, Transmission Constraint Management, SCED, RUC and LFC for 168 continuous hours without significant data base errors and software failures. Runtime >= 168 hours without significant errors or failures Market Participants review/approval of settlment statements = 100% |  |  |  |
| Reporting Data Sources: System Logs / ERCOT EDS 4 PM DAM Results Comprised of: 1. DAM Market Solution Timestamp; 2. Missing Settlement Determinant Inventory Time stamped 3. Resolution of MP comments on test settlement statements |  |  |  |
| References | TP: 5.4.9 (1) | TNP: N/A |  |

### EMO8 - Conduct EECP Test

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: EDS 4 - 168 Hour Test Major Milestone less 30 days |  |  |  |
| Metric Description: ERCOT and Market Participants shall conduct a test of the Emergency Electric Curtailment Plan (EECP). |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT can perform the steps of the EECP as outlined in the Protocols.. There must be an orderly, predetermined procedure for managing emergencies. ERCOT shall perform a test to initiate and coordinate the implementation of EECP using the nodal systems. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that ERCOT conducted a test of the Emergency Electric Curtailment Plan (EECP) with Market Participants. Readiness will be achieved when Control Room procedures have been deployed and the EECP test was conducted. EECP Procedures Published EECP Test Completed Successfully as Defined in the EECP Test Plan |  |  |  |
| Reporting Data Sources: Documentation and Control Room Desk Procedures. All procedures are also posted at www.ercot.com. EDS 4 Notification of EECP Test Complete / ERCOT EDS 4 PM |  |  |  |
| References | TP: 5.4.16 | TNP: 6.5.9.4 |  |

# Network Model Management Metrics

# Market Operations Metrics

### MO2 - Operate 7 Day market with RUC

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: Full Nodal Functionality 24*7 Operations plus 60 days |  |  |  |
| Metric Description: ERCOT shall operate RUC in parallel with DAM per the Transition Plan 5.4.7(1) and have the capability of running multiple RUCs simultaneously and provide the appropriate Settlement Bill Determinants.. |  |  |  |
| Background: The intent of this metric is to prove the ability to process the RUC under multiple scenarios. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies that the RUC Process runs successfully in parallel with the DA Market and multiple RUCs can run in the same time frame. Readiness will be met when it is determined that a RUC Process can be run while the DAM is solving. Both RUC and DAM must solve. Readiness will be met when it is determined that a multiple RUC scenarios can be run simultaneously. All RUC scenarios must solve. All appropriate Settlement Bill Determinants are generated accurately. RUC Start > DAM Start and RUC End < DAM End RUC1 Start=RUC2 Start=RUC3 Start Missing (critical) Settlement Determinants = 0 |  |  |  |
| Reporting Data Sources: DAM and RUC Job Timestamps from Job Scheduler / RUC 1,2,3 Timestamps from Job Scheduler / ERCOT EDS 4 PM |  |  |  |
| References | TP: 6.1(d) | TNP: 5 |  |

### MO3 - Verify Supplemental Ancillary Services Market (SASM)

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: Full Nodal Functionality 24*7 Operations |  |  |  |
| Metric Description: ERCOT shall test Supplemental Ancillary Services Market Functionality and Procedures. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT can procure additional ancillary services to meet regulation and responsive reserve requirements during the operating day. |  |  |  |
| Criteria: The Readiness Team will review MMS data indicating that supplemental ancillary services are defined by the output of the real time market ERCOT will perform multiple SASM and SASM Auctions that are successfully executed during 168 hour test. During this test, it is expected that ERCOT will call a SASM and receive the specified ancillary services. It is also expected that ERCOT will call a SASM and not receive the requested ancillary services. In both cases, the expectation is that the market continues to solve. |  |  |  |
| Reporting Data Sources: Nodal MMS Data Extract of RT / Zonal MMS Data Extract of RT / ERCOT EDS 4 PM |  |  |  |
| References | TP: 5.4.14 | TNP: 6.4.8.2 – 6.4.8.2.3 |  |

### MO6 - Verify DAM Ancillary Services [what is the difference between this an MO1; both energy and AS are purchased in the DAM and can not be executed separately because of the co-optimization of energy and AS]

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: Full Nodal Functionality 24*7 Operations plus 60 days |  |  |  |
| Metric Description: ERCOT will during the 168 hour test use DAM to procure adequate ancillary services utilizing test offers from Market Participants |  |  |  |
| Background: The intent of this metric is to ensure that the Nodal Market System can meet regulation and responsive reserve requirements for the operating day governed by the Day Ahead Market and to ensure that they are within a band of adequacy. Also, all appropriate Settlement Bill Determinants are generated accurately. |  |  |  |
| Criteria: The Readiness Team will review MMS data indicating that ancillary services are defined by the output of the Day Ahead Market. Readiness will be met when the DAM ancillary services requirement is defined and within 10% of the zonal ancillary services requirement. DA Nodal Calculated Regulation Service +/- 10% of the RT Operating Requirements DA Nodal Calculated Responsive Reserve Service +/- 10% of RT Operating Requirements DA Nodal Calculated Non Spinning Reserve Service +/- 10% of RT Operating Requirements Missing (critical) Settlement Determinants = 0 |  |  |  |
| Reporting Data Sources: Nodal MMS Data Extract of DAM / Nodal MMS Data Extract of RT / ERCOT EDS 4 PM |  |  |  |
| References | TP: 6.1 (b) - 5.4.6 (2) | TNP: 3.16, 3.17, 3.18 |  |

# Contingency Metrics

### C1 - Contingency Plan for Weekly, Daily and Hourly RUC Failure

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 60 days |  |  |  |
| Metric Description: ERCOT shall develop and test Contingency Plan procedures for RUC Failure. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT has a procedure when the primary RUC system is not available. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies the existence and test of a contingency plan and procedures document for RUC failure. Readiness will be achieved when the RUC Contingency Plan has been successfully tested. RUC Contingency Plan procedures Exists RUC Contingency Plan Successfully Tested |  |  |  |
| Reporting Data Sources: RUC Contingency Plan / RUC Contingency Plan Test Log / ERCOT EDS 4 PM |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### C2 - Contingency Plan Procuedures for DAM Failure

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 60 days |  |  |  |
| Metric Description: ERCOT shall develop and test Contingency Plan procedures in case the DAM fails to solve. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT has the ability to properly manage DAM failures |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies the existence of a contingency Plan procedures document for DAM failures. Readiness will be achieved when the DAM failure procedure has been successfully tested. DAM Failure Plan procedures Exists Procedures Successfully Executed in a test enviorment |  |  |  |
| Reporting Data Sources: DAM LMP Contingency Plan procedures / DAM / LMP Contingency Plan procedures Test Log / ERCOT EDS 4 PM |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### C3 - Contingency Plan procedures for ICCP Data Failure

| Reported By: ERCOT |  |  | EDS: 2 |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 60 days |  |  |  |
| Metric Description: ERCOT shall develop and test Contingency Plan procedures for ICCP Data Failure. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT has the ability to operate during the loss of ICCP links at a single facility and at both the Taylor and Austin facility. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies the existence of a contingency Plan procedures document for ICCP failure. Readiness will be achieved when the ICCP Contingency has been successfully tested. ICCP Contingency Plan procedures Exists ICCP Contingency Plan procedures Successfully Executed |  |  |  |
| Reporting Data Sources: ICCP Contingency Plan procedures / ICCP Contingency Plan procedures Test Log / / ERCOT EDS 2 PM |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### C4 - Contingency Plan procedures for SCED Failure

| Reported By: ERCOT |  |  | EDS: 3 |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 60 days |  |  |  |
| Metric Description: ERCOT shall develop and test Contingency Plan procedures for SCED Failure. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT has the ability to control generation and settle the market in the real time when the SCED system is not available. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies the existence and test of a contingency Plan procedures document for SCED failure. Readiness will be achieved when the SCED Failure Contingency has been successfully tested. SCED Failure Contingency Plan procedures Exists SCED Failure Contingency Plan procedures Successfully Executed |  |  |  |
| Reporting Data Sources: SCED FailureContingency Plan procedures / SCED Failure Contingency Plan procedures Test Log / / ERCOT EDS 3 PM |  |  |  |
| References | TP: N/A | TNP: 6.5.9.2 |  |

### C5 - Contingency Plan procedures for Key Settlement and Financial Transfer Processes

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 60 days |  |  |  |
| Metric Description: ERCOT shall develop and test Contingency Plan procedures for the various Settlement and Financial processes that must be performed in order to settle the market in a timely manner. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT has tested contingency Plan proceduress in place to overcome (in a timely manner) failures of key components of the Settlement and Billing System and Financial Transfer System. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies the existence and test of a contingency Plan procedures document for Settlement and Financial processes. Readiness will be achieved when the Settlement and Financial processes Contingency has been successfully tested. Settlement and Financial processes Contingency Plan procedures Exists Settlement and Financial processes Contingency Plan procedures Successfully Executed |  |  |  |
| Reporting Data Sources: Settlement and Financial processes Contingency Plan procedures / Settlement and Financial processes Contingency Plan procedures Test Log / / ERCOT EDS 4 PM |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### C6 - Develop Plan procedures for SE Failure

| Reported By: ERCOT |  |  | EDS: 2 |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 60 days |  |  |  |
| Metric Description: ERCOT shall develop and test Contingency Plan procedures for SE Failure. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT has the ability to maintain system reliability when the SE system is not available. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies the existence of a contingency Plan procedures document for SE failure. Readiness will be achieved when the SE Contingency has been successfully tested. SE Contingency Plan procedures Exists SE Contingency Plan procedures Successfully Executed |  |  |  |
| Reporting Data Sources: SE Contingency Plan procedures / SE Contingency Plan procedures Test Log / / ERCOT EDS 2 PM |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### C7 - Contingency Plan procedures for a Backup Facility

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 60 days |  |  |  |
| Metric Description: ERCOT shall develop Contingency Plan procedures for a Loss of the Primary Control Room. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT and QSEs have the ability to maintain control of the system when the Primary Control Room becomes unavailable. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies the existence of a contingency Plan procedures document for the Primary Control Room. Readiness will be achieved when the Primary Control Room Contingency has been successfully tested. Primary Control Room Contingency Plan procedures Exists Primary Control Room Contingency Plan procedures Successfully Executed |  |  |  |
| Reporting Data Sources: Primary Control Room Contingency Plan procedures / Primary Control Room Contingency Plan procedures Test Log / / ERCOT EDS 4 PM |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### C8 - Contingency Plan procedures for Portal/API Failure

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 60 days |  |  |  |
| Metric Description: ERCOT shall develop Contingency Plan procedures for a Portal/API Failure. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT has the ability to receive data from market participants when the API / Portal becomes unavailable. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies the existence of a contingency Plan procedures document for a API / Portal Failure. Readiness will be achieved when the API / Portal Contingency has been successfully tested. API / Portal Contingency Plan procedures Exists API / Portal Contingency Plan procedures Successfully Executed |  |  |  |
| Reporting Data Sources: API/Portal Contingency Plan procedures / API/Portal Contingency Plan procedures Test Log / / ERCOT EDS 4 PM |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### C9 - Contingency Plan procedures for Site Unavailability

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 60 days |  |  |  |
| Metric Description: ERCOT shall develop and test contingency Plan procedures for the event of normal site unavailability. |  |  |  |
| Background: The intent of this metric is to ensure that ERCOT has the ability to facilitate the Nodal Market from the backup site. |  |  |  |
| Criteria: The Readiness Team will review documentation that verifies the existence of a contingency Plan procedures document for normal site unavailability. Readiness will be achieved when the normal site unavailability Contingency has been successfully tested. Normal site unavailability Contingency Plan procedures Exists Normal site unavailability Contingency Plan procedures Successfully Executed |  |  |  |
| Reporting Data Sources: Normal Site Unavailability Contingency Plan procedures / Normal Site Unavailability Contingency Plan procedures Test Log / / ERCOT EDS 4 PM |  |  |  |
| References | TP: N/A | TNP: N/A |  |

### C10 - Verify Single Point of Failure Recovery EMS/MMS/NMMS/CRR/COMS

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 60 days |  |  |  |
| Metric Description: ERCOT shall test that a recovery to full functionality occurs for a single point of failure in EMS, MMS, NMMS and CRR and COMS applications. |  |  |  |
| Background: The intent of this metric is to ensure that systems functionality is not lost due to any single point of failure. |  |  |  |
| Criteria: The Readiness Team shall review documentation that ERCOT tested that a continuation of full functionality occurred during any single point of failure in EMS, MMS, NMMS and CRR and COMS applications. Readiness will be achieved when the Single Point of Failure test has been successfully executed. Single Point of Failure Test Plan procedures Exists Single Point of Failure Test Plan procedures Successfully Executed |  |  |  |
| Reporting Data Sources: Single Point of Failure Test Plan procedures / Single Point of Failure Test Log / / ERCOT EDS 4 PM |  |  |  |
| References | TP: N/A | TNP: N/A |  |

# IMM Metrics

### IMM1 - Market Monitor Systems Capability

| Reported By: WEMM |  |  | EDS: N/A |
| --- | --- | --- | --- |
| Target Completion: EDS 4 – Release 9 Complete |  |  |  |
| Metric Description: Verify Market Monitor Systems Capability. |  |  |  |
| Background: The intent of this metric is to validate that the PUC Staff and the Wholesale Electric Market Monitor (WEMM) can access all data deemed necessary by the PUCT staff and IMM to perform their market oversite activities. |  |  |  |
| Criteria: The Readiness Team will receive notification from the WEMM that Market Monitor has sufficient staff, systems and access to data to successfully monitor the market. Readiness will be achieved when the Readiness Team receives notification that the Market Monitor is capable of fulfilling its intended purpose. Market Monitor and PUC Asserts Readiness |  |  |  |
| Reporting Data Sources: Letter of Assurance from the Market Monitor / ERCOT PMO PM |  |  |  |
| References | TP: N/A | TNP: 17.3 |  |

# Overall Readiness Metrics

### R0 – Market Participants Operations Readiness

| Reported By: ERCOT/Market Particpants |  |  | EDS: N/A |
| --- | --- | --- | --- |
| Target Completion: Go Live less 120 days |  |  |  |
| Metric Description: Market Participants operate the nodal systems on a daily routine basis in parallel with the zonal market systems. |  |  |  |
| Background: The intent of this metric is to assure all systems and operations personnel at ERCOT and at Market Participant facilities are fully trainied and ready to operate in a Nodal environments. |  |  |  |
| Criteria: ERCOT will confirm the state of each Market Particpant’s readiness by observation of each MPs actions in the test environments of the nodal systems. ERCOT Asserts Readiness of Market Participants |  |  |  |
| Reporting Data Sources: PMO Dashboard / Readiness Metric Report |  |  |  |
| References | TP: 6.0 | TNP: N/A |  |

### R1 - Nodal Readiness Declaration

| Reported By: ERCOT |  |  | EDS: N/A |
| --- | --- | --- | --- |
| Target Completion: Go Live less 60 days |  |  |  |
| Metric Description: ERCOT Declares the Texas Nodal Readiness State by assessing Program, ERCOT and Market Participant Readiness. |  |  |  |
| Background: The intent of this metric is to provide ERCOT stakeholders with a comprehensive statement of Market Readiness. |  |  |  |
| Criteria: ERCOT will confirm the state of Program Readiness through the PMO dashboard. ERCOT will confirm the state of ERCOT Readiness through assessment of the ERCOT related metrics. ERCOT will confirm the state of Market Participant Readiness through assessment of the MP related metrics. Readiness will be achieved when PMO state has been reported and ERCOT and MP related metric assessments have been completed. ERCOT Asserts Readiness TPTF, TAC and the ERCOT BOD approves Rediness Declaration |  |  |  |
| Reporting Data Sources: PMO Dashboard / Readiness Metric Report / ERCOT Nodal Program Executive Director |  |  |  |
| References | TP: 6.3 | TNP: N/A |  |

### R2 – Develop Texas Nodal Market Launch Plan

| Reported By: ERCOT |  |  | EDS: N/A |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 90 days |  |  |  |
| Metric Description: Develop Texas Nodal Market Launch Plan. |  |  |  |
| Background: The intent of this metric is to ensure that a comprehensive market launch plan exists. The plan will address the activities ERCOT and Market Participants must perform in order to launch the integrated nodal market. TPTF will develop the plan and TAC will approve. |  |  |  |
| Criteria: The Readiness Team will review documentation indicating that the Texas Nodal Market Launch plan has been created and approved by the TAC. Readiness will be achieved when a approved Texas Nodal Market Launch Plan has been published and ERCOT Market Participant communications verifies through voice communication that all Market Particpants are ready. Texas Nodal Market Launch Plan is Posted and communitated to all MarketParticipants |  |  |  |
| Reporting Data Sources: TN Market Launch Plan / ERCOT Readiness PM |  |  |  |
| References | TP: N/A | TNP: N/A |  |