## Slide 1: Reduction of MMS Vendor Effort for TPTF January 8, 2008 Murray Nixon Sai Moorty

## Slide 2: Agenda
Key driver (reminder)
Review of proposed changes impacting MPs
Review of proposed changes impacting ERCOT Operations
Development & implementation timelines
MMS2 FAT status

## Slide 3: Key Driver for Proposed Changes
Ensure the final MMS FAT completes by 30Jun08, allowing 2 months for integration & EDS4 activities prior to the 168 hour test start on 1Sep08
  This was the direction provided to the ERCOT & ABB MMS teams by the Nodal and ABB executives on 28Nov07
  The proposed deferrals will help MMS meet the Nodal program timeline by reducing ~8300 hours of vendor requested work until after the delivery of the final release to ERCOT for the start of FAT
    NOTE: ~7500 additional hours have been removed from the vendor scope by methods such as reducing the number of releases, moving work to ERCOT, deferring low priority SPR work post go-live

## Slide 4: Proposed Changes
Proposed changes
  Multiple models
    NOTE: Workaround is being defined that will be acceptable to ERCOT & MPs
  Two S&B information only calculations (DAOPTPRINFO & RTOPTPRINFO; sections 7.9.1.2 and 7.9.2.2)
    NOTE: No proposed workaround; info to be made available after go-live
  Automated interface for QSEs with resources to update resource parameters (e.g., ramp rates) in MMS
    NOTE: Workaround being defined to determine feasibility of implementation prior to 168 hour test. Otherwise, proposed original functionality to be implemented after go-live.
  Dynamically scheduled resource incremental and decremental energy offer curves
    NOTE: No proposed workaround; functionality to be implemented after go-live
  Co-optimizing energy and AS for self-committed resources in DAM
    NOTE: Regardless of future outcome of TPTF sub-group, functionality to be implemented after go-live

## Slide 5: Proposed Changes (cont’d)
Proposed changes (cont’d)
  Improve the performance of Phase 2 validation for the credit limit check component. Reason for deferring: At present it is not known whether further performance improvements are needed.
  All major processes (SCED, DAM, RUC) inputs/outputs are archived (referred to as save cases). These save cases can be reloaded into MMS for future analysis. To aid in analysis it was considered beneficial if the binary files in the save case could be stored in a ASCII file format. Reason for deferring: Workaround is available as data in binary file is still accessible after loading into MMS.
  RUC: add display to show the corresponding binding transmission constraint, shift factors and flow contribution from the resource (NOTE: ERCOT is considering moving this work in-house if possible). Reason for deferring: Workaround is that data is available in MMS and ERCOT’s plan is to check feasibility of building display internally.
  Constraint Competitive Test (CCT): For monthly and annual CCT making additional data available in database for further analysis (Congestion management group) (NOTE: ERCOT is considering moving this work in-house if possible) Reason for deferring: Workaround is that raw data will be available in files.
  Deliverability Evaluation Function (DEF): This tool is used by ERCOT operators to determine if there is a situation where Ancillary Service (AS) over a given time horizon is undeliverable. During MMS 2 pre-FAT where this tool was tested, certain enhancements in the scenarios simulated and results presented were proposed. Reason for deferring: ERCOT still needs to evaluate the proposed enhancements.
  Weekly RUC : Enhanced configurability of WRUC study periods. Reason for deferring: Very low priority.

## Slide 6: Timeline for Development & Implementation of Proposed Changes
Proposed development timeline: continue work on these items between the start of the last MMS FAT (currently scheduled for 22Apr08) and go-live (1Dec08)
Proposed implementation timeline: no later than the end of the 2nd quarter after Nodal go-live with prioritization of implementation items to be a joint TPTF / Nodal program / MMS project decision
NOTE: regular joint reviews of outstanding MMS requests will be necessary since items of varying priority will be identified during the remaining MMS pre-FAT & FAT, integration and EDS activities

## Slide 7: MMS2 FAT Status
MMS2 FAT started on 3Dec07 with a targeted completion of 11Jan08
As of 4Jan08, 83% of the all FAT tests are complete with a 90% pass rate
  All of the remaining tests are unstructured
A patch containing SPR fixes was deployed to MMS DEV on 7Jan08; planning to move to MMS FAT 8Jan08
The remaining unstructured tests and SPR fixes will be tested 9-11Jan08
The patch will be available for deployment to other environments as soon as the migration to MMS FAT is complete