## Slide 1: PMO Update to PRS
Troy Anderson
Program Management Office
January 17, 2008

## Slide 2: PMO Update
Agenda
  2009 Project Prioritization
  2007 Results
    Project Counts
    Financial results will be reported in February
  Nodal Change Control

## Slide 3: PMO Update - 2009 Project Prioritization
2009 will be a unique year for project planning due to Nodal
  Quantity and type of SO/MO projects in 2009 is not yet known
ERCOT expects to file a fee case in early 2008
  Several months earlier than the usual schedule
This will limit our ability to produce the typical level of detail for project prioritization (Project Requests, CBAs, Time & Cost Estimates)
ERCOT is proposing a two phase approach to 2009 planning
  Phase 1 – Develop high level initiatives list in early 2008
  Phase 2 – Complete required documents in late 2008 for allocation of 2009 funds
  Important
    No project will be allowed to proceed without all required documents
    Both phases will be completed with market subcommittee involvement

## Slide 4: PMO Update - 2009 Project Prioritization
List of initiatives expected in 2009
  Each CART provides as much information as it can
    Actual projects
    Groupings by project type
  Total budget request determined by summing initiatives list estimates
CART Funding Allocation
  Funding per CART determined in late 2008
    Funding provided for “Previously Approved” projects initiated in 2008
    Funding provided for projects that have been defined (all documentation)
  Funds for efforts not yet defined to be held by SRT
    Funding will be allocated as projects become ready to initiate

## Slide 5: PMO Update - 2009 Project Prioritization
2007 – 4th quarter
  Seek approval of process change
  Develop list of high level initiatives by CART with budget range estimates
2008 – 1st quarter
  Internal ERCOT approval of initiatives list & budget (SRT, EC)
  Market participant approval of initiatives list & budget (subcommittees, TAC)
  F&A and Board of Directors approval of initiatives list & budget
2008 – 4th quarter
  Develop 2009 Divisional PPLs according to current standards
  Allocation of funds to CARTs for Previously Approved and known projects
2009
  Operate with the funding approach outlined on slide 5

## Slide 6: PMO Update - 2009 Project Prioritization
2009 Project Prioritization Schedule - Overview
  January
    CARTs revise 2009 Initiative Lists
  February
    Initial review at Market Subcommittee meetings
      MO - COPS (February 12)
      RO - RMS (February 13)
      SO - ROS, WMS (February 14 / February 20)
  March
    Approval by market subcommittees
      MO - COPS (March 11)
      RO - RMS (March 12)
      SO - ROS, WMS (March 13 / March 19)
      CO, IO, MO, RO, SO – PRS (March 20)
  April
    Approval by TAC (April 3)
    Available for F&A and Board review (April 15)

## Slide 7: PMO Update – 2007 Results
2007 CART Project Counts at Year End
CART | Not Started | Initiation | Planning | Execution | Closing / Closed | Cancelled | On Hold | Deferred | Totals
CO | 1 | 1 | 9 | 11 | 8 | 4 | 0 | 14 | 48
IO | 5 | 0 | 2 | 14 | 4 | 0 | 0 | 0 | 25
MO / RO | 0 | 1 | 5 | 7 | 11 | 7 | 1 | 3 | 35
SO | 0 | 0 | 1 | 4 | 14 | 5 | 0 | 0 | 24
Total | 6 | 2 | 17 | 36 | 37 | 16 | 1 | 17 | 132
Original Project List (approved Sept. 2006) = 75
Unexpected Carryovers = 22
New Projects Added = 35

## Slide 8: PMO Update - Nodal Change Control
Final Major Nodal Software Drop Occurs on 4/22
  Most Nodal systems have now frozen changes to functionality required for Go Live
  Only changes with a systems impact deemed absolutely essential for the correct operation of the Nodal market can be considered (with the knowledge that their introduction may delay Go Live)
  NPRRs with no impact can proceed, but diverting Nodal Subject Matter Experts to analyze new NPRRs is not advised
  Non-essential changes should be tabled or will be boxed in the Protocols