## Systems
ITEST View
Project | [52 empty] | Carryover $$ (Yes/No) | time axis 2007-01-07 to 2007-12-29
[11 empty] | NODAL SIEBEL LOCK (03/16 - 06/14) | [23 empty] | NODAL LOCK (09/01 - 12/31: ALL SYSTEMS???)
Feb. Retail Release (02/09/2008) | 2007-01-14: SBL,PFREE,MT,TIBCO
**Includes AIX ODS and PR60008 ODS Changes | 2007-01-14: AIX ODS
PR60006: ERCOT Outage Evaluation and Resolution (TDTWG/SCR745)--Phase II | 2007-01-14: PFREE
Mar. Retail Release | bar: 2007-02-11 to 2007-03-03
PR60008: Terms and Conditions requirements and Performance Measures (PUCT 33049)
Release 1: Siebel App & DB /TIBCO (SIR11549) | 2007-02-11: 1 SBL / TIBCO
Release 2: PFREE, ETS, TIBCO | 2007-03-17: 2 PFREE, TIBCO, ETS; 2007-05-26: Contingency until 06/30
PR40066_04: Lodestar Upgrade | 2007-02-25: Lodestar, Appworx
Includes Nodal Lodestar Lock | 2007-04-21: Lodestar, Appworx, TIBCO
PR70007: MarkeTrack Enhancements (SCR749) | 2007-03-31: SBL & EIF ODS
Release 1: MT/TIBCO | 2007-05-12: 1 MT,TIBCO
Release 2: MT/TIBCO/SBL **MKT Test | 2007-06-23: 2 SBL,MT,TIBCO
Release 3: MT/ TIBCO/(SBL Contingency) **MKT Test | 2007-07-28: 3 MT,TIBCO(SBL?)
Release 4: MT/TIBCO **MKT Test | 2007-09-01: 4 MT,TIBCO
PR70057: ERCOT System Throughput for IDR (Advanced Metering)
Pending
Small Renewables
Distributed Generation
Demand Response