## Slide 1: Texas Nodal Market Implementation Program Infrastructure Update February 5th, 2008
http://nodal.ercot.com <number>
Notes: <number>

## Slide 2: INF: Project Summary - Initial Charter with Approved Changes
Project area: Infrastructure
Description: Provision of development, testing, EDS and production environments across the Program
Vendor(s): IBM, EMC, Oracle
Project Manager: David Forfia
Key deliverables/short term deliverables: Hardware specifications Hardware procurement Data center capacity resolution IT Services Catalogue Service Level Agreements for all Nodal projects Project development & test (FAT) environments Integration testing (SAT) environments EDS environments Production environments | Market Participant Identity Management (new) Release Management processes (from INT) Oracle 10g upgrade for EDW (new) High availability monitoring environment (new)
Key Assumptions: Infrastructure capacity can be incrementally added as the project progresses using IBM’s capacity upgrade on-demand model Data center capacity issues will be resolved in the next 90 days | 
Challenges/Risks: Existing Data Center capacity (power) | 
Comments: IT Operations will be the first ERCOT function to transition to Nodal operations, starting with setting up development environments | 
http://nodal.ercot.com <number> TPTF Nodal Update 02/05/2008
Notes: <number>

## Slide 3
Recap of October 2007 Presentation
http://nodal.ercot.com <number> TPTF Nodal Update 02/05/2008
Notes: <number>

## Slide 4: Expanding existing data center capacity is an integrated process
There are 3 components which are balanced to ensure a reliable data center
  Standby Generator Capacity
  Uninterruptible Power Supply (UPS) capacity
  Data Center Air Conditioning (DCAC) capacity
The maximum capacity for equipment is determined by the minimum carrying capacity of any one of the components.
We have taken all steps possible to maximize the current capacity of the data centers to running at the available capacity of the UPS systems in each site.
Converting EMS test lab into an iTest capable data center.
Very nearly all possible near term facility upgrades have been completed.
http://nodal.ercot.com <number> TPTF Nodal Update 02/05/2008
Notes: <number>

## Slide 5: System requirements are driven by project detailed design documents
Each project team has an assigned architect who is responsible for the architecture for the project’s deliverables
that are consolidated into a deployment diagram by IDA
that become individual work requests for operations
to deploy the systems
http://nodal.ercot.com <number> TPTF Nodal Update 02/05/2008
Notes: <number>

## Slide 6: Market trials and Integration testing will drive changes to the environments
The assumption in the infrastructure plan is that the initial deployment specifications will have to be changed.
The infrastructure technologies selected as the core for the Nodal system were picked because they adapt well to change.
http://nodal.ercot.com <number> TPTF Nodal Update 02/05/2008
Notes: <number>

## Slide 7: Critical Path Mitigation Strategies Procurement and Architectural Delays
Risk | Mitigation Strategy
Long procurement lead times | Define system requirements as soon as possible and place orders.
 | Utilize existing systems or virtual machines where appropriate
Late Technical Architecture design documents | Preorder unassembled equipment and have ERCOT staff built to specification
 | Authorize overtime to build systems
 | Pre-build standard server configurations based upon service catalogue and assign to projects as requirements become known
Server consolidation decommissions behind schedule | Run data center in the safe “buffer” zone of capacity Add capacity in Taylor for Test environment Continue implementing consolidation efforts in other infrastructure components.
http://nodal.ercot.com <number> TPTF Nodal Update 02/05/2008
Notes: <number>

## Slide 8: Infrastructure Capacity is Identified Major risks to Go Live
Risk | Description | Likelihood | Impact on Go Live | Mitigation
MMS delivery schedule | Tight delivery schedule constrains testing and defect cycles, impacts EDS trials schedule | L | H | Enhanced oversight of, and on-site working with, ABB Reallocation of work from ABB to ERCOT Overlap EDS with FAT testing
Infrastructure constraints (power, space, cooling) | Limits speed and scale of environment build outs, impacts development projects, integration and EDS trials | H | L | Prioritizing build out of environments and applications based on EDS schedule Planning active / standby EDS environment to eliminate short-term ITest need Building test environment in Blue Building server room Removing all non-essential equipment from Austin data center Compressing Nodal deployment footprint as much as possible
Integration (including CIM Model) | Lack of source systems and infrastructure limits ability to validate integration points, impacts re- factoring cycle times and costs | M | M | Building interfaces in advance of applications delivery based on available information expecting re-factoring Testing application and integration in available, sub-optimal environments
 | Uncertainty over ability to integrate CIM models may impact data and system quality and testing | H | L | Working with 3 main vendors on multiple iterations of development and validation of CIM import/export Investigating contingency plan to preserve April 1st start of DAM / RUC EDS trials
http://nodal.ercot.com <number> TPTF Nodal Update 02/05/2008

## Slide 9: Infrastructure Capacity is Identified Major risks to Go Live with mitigation activities in progress
Prioritizing build out of environments and applications based on EDS schedule
Building test environment in Blue Building server room
Removing all non-essential equipment from secondary data center
Compressing Nodal deployment footprint as much as possible
Planning active / standby EDS environment (Active / Passive) to eliminate short-term ITest need
Delivering environments as prioritized by delivery schedule.
Blue Building server room construction completes in February
Only equipment to Disaster Recovery, Zonal market and the new Nodal to be in secondary site equipment.
Nodal deployment footprint was architecturally compressed as much as possible
Deployment of standby EDS environment in progress.
http://nodal.ercot.com <number> TPTF Nodal Update 02/05/2008

## Slide 10: Current environmental deployment status
 | Primary Site | Secondary Site | Test Site
Technical Architecture |  |  | 
Hardware Delivered |  |  | 
Hardware Installed |  |  | 
Applications Installed |  |  | 
While the initial technical architecture documents are complete, the assumption is that the initial deployment specifications will have to be changed.
http://nodal.ercot.com <number> TPTF Nodal Update 02/05/2008

## Slide 11
EDS MP Readiness
EDS iTesting
EDS iTesting
EDS MP Readiness
Passive
Active
Initial testing release and site utilization strategy is to isolate sites by release
Release Installation
Cutover
Readiness Preparation
Release Installation
Readiness Preparation
Goals of the strategy are to:
  Ensure the consistency and stability of market readiness environment
  Minimize the rework for project and production resources
  Verify the production sites in preparation for Nodal go live
  Allow vendors to complete as scheduled with FAT deliveries
http://nodal.ercot.com <number> TPTF Nodal Update 02/05/2008

## Slide 12
EDS MP Readiness
EDS MP Readiness
EDS MP Readiness
EDS MP Readiness
Passive
Active
Final testing release and site utilization strategy is what will be used in production
Release Installation
Data/App Synch
EDS iTesting
Test
Release Bundling
Release #2 Installation
EDS iTesting
Utilizing standard Test and Release methodologies require:
  All environments completed
  Incremental vendor releases
  Automated release management processes in place.
http://nodal.ercot.com <number> TPTF Nodal Update 02/05/2008

## Slide 13: Questions
<number>
January 15, 2008
<number>
Questions ??
ERCOT Nodal Market Transition
http://nodal.ercot.com <number> TPTF Nodal Update 02/05/2008
Notes: <number>
<number>