## Slide 1: TPTF Update for TAC February 7, 2008 Trip Doggett
http://nodal.ercot.com <number>
Notes: <number>

## Slide 2: Agenda
http://nodal.ercot.com <number>
Item | Description | Purpose
1. Meeting Summary | Summary of recent TPTF activities | For review
2. Next Meetings | Upcoming activities | For review
3. Approval of Readiness Metrics | Request TAC Approval for ERCOT to move forward with the metrics E2, E4, E7, E10, E11, E14, E15, EMO3, EMO8, MO3, C1 thru C10, IMM1, revised MP14, N4, R0, R1, R2, and R3 | For Vote
4. Approval of Milestones | Request TAC acknowledge TPTF completion of the following Milestones– INF Market Participant Identity Management Requirements v2.3 Requirements complete Enterprise Data Warehouse Conceptual System Design v0.95 complete INF Market Participant Identity Management Conceptual System Design v1.7 complete | For Vote
Notes: <number>

## Slide 3
http://nodal.ercot.com <number>
Meeting Summary – January 7
Meetings January 7-8 and January 21-23.
On January 7, TPTF discussed the following:
  Nodal Program Update
  Nodal Timeline Update
  Flaw in TPTF voting spreadsheet related to Consumer Segment votes.
    Draft NPRR to address issue with September 28, 2006 motion affected by flaw in vote tally
  Extension of the current Service Level Agreement
    On January 7, TPTF approved an extension of the effective period of Service Level Agreement for Nodal EDS Environments v2.2 through February 1, 2008 as modified by TPTF on January 7, 2008. The motion carried by roll-call vote, with 100% in favor and one abstention (Coral Power). All Market Segments were represented for the vote.
  Zonal-to-Nodal Transition Protocol Transition Plan and possible synchronization issues with the EDS Sequence Timeline
  EDW Update
    EDW response to questions/requests raised during previous TPTF meeting
Notes: <number>

## Slide 4
http://nodal.ercot.com <number>
Meeting Summary – January 7 (continued)
On January 7, TPTF discussed the following:
  Clarification Request - Nodal Protocols Section 3.2.3, System Adequacy Reports
    Clarifications to information requested by the Medium-Term System Adequacy Report and the Short-Term System Adequacy Report
  Quality Center Update
  Congestion Revenue Right (CRR) Update
    EDS - CRR Testing Market Participant Handbook v1.05
    Explanation of Market Submission/Retrieval Items
    Settlement issues for the Draft NPRR - PCRR Release Mechanism
      On January 7, TPTF endorsed forwarding the draft NPRR on PCRR Release mechanism to PRS as modified by TPTF on January 7, 2008. The motion carried by roll-call vote, with 100% in favor and ten abstentions (LCRA, CenterPoint Energy, Luminant, AEP, Calpine, Coral Power, Exelon, Reliant, BP Energy, and CitiGroup). All Market Segments were represented for the vote.
  Review proposed Market Rules changes to draft NPRRs:
    Draft NPRR - Protocol Sections 4 and 6 Formula Clarifications and Related Revisions
    Draft NPRR - Changes to Section 8 to Incorporate Role of TRE, the IMM, and the Concept of Market Compliance
  NPRR093, Clarification to Definition of DUNS Number; Section 2, Definitions and Acronyms
Notes: <number>

## Slide 5
http://nodal.ercot.com <number>
Meeting Summary – January 8
On January 8, TPTF discussed the following:
  MMS Update
    MMS deferral items:
      Changes that impact Market Participants
      Changes that impact ERCOT Operations
      Timeline for development and implementation of proposed changes
      Status of current FAT
  Development of draft NPRR for Disclosure of Resource Offers and Supply Curves in accordance with PUCT Rule 25.505 (f)
  Calpine proposal and Exelon comments regarding settlement issues associated with current limitation for combined-cycle configurations
  INF Project
    Review disposition of comments for the Market Participant Identity Management Requirements
      On January 8, TPTF approved the INF Market Participant Identity Management Requirements v2.3 with the understanding that it will be updated to incorporate changes recommended by TPTF on January 8, 2008. The motion carried by roll-call vote, with 100% in favor and five abstentions (First Choice Power, AEP, City of Allen, City of Eastland, and Coral Power). All Market Segments, except Cooperative, were represented for the vote.
Notes: <number>

## Slide 6
http://nodal.ercot.com <number>
Meeting Summary – January 8 (continued)
On January 8, TPTF discussed the following:
  Announce January 14 Subgroup to discuss DAM Participation issues for Self-Committed Generation Resources
  Review remaining Readiness Metrics and market comments in the PMO Working Readiness Metric Inventory:
    ERCOT Internal Metrics
    E2 - Verify ERCOT Performance Monitoring Test Plan
    E4 - Transition Pricing Mechanisms
    E7 - Validate EDW Access and Accuracy of Postings Required by the IMM and PUCT Rules
    Required by the IMM and PUCT Rules
    E10 - Validate EDW Commercial Systems Access Accuracy
    E11 - Validate EDW Compliance Data Access
    E14 - Verify QSE Performance Monitoring Test Plan
    E15 - Verify TSP Performance Monitoring Test Plan
    Energy Management Operations Metrics
    EMO3 - Verify Outage Evaluation System Functionality
    EMO4 - Run 7 Day Stability Test
    EMO8 - Conduct EECP Test
Notes: <number>

## Slide 7
http://nodal.ercot.com <number>
Meeting Summary – January 8 (continued)
On January 8, TPTF discussed the following:
  Review remaining Readiness Metrics and market comments in the PMO Working Readiness Metric Inventory (continued):
    Market Operations Metrics
    MO1 - Operate DA Market for 7 Days
    MO2 - Operate 7 Day market with RUC
    MO3 - Verify Supplemental Ancillary Services Market (SASM)
    MO6 - Verify DAM Ancillary Services
    Contingency Metrics
    C1 - Contingency Plan Procedures for Weekly, Daily and Hourly RUC Failure
    C2 - Contingency Plan Procedures for DAM Failure
    C3 - Contingency Plan Procedures for ICCP Data Failure
    C4 - Contingency Plan Procedures for SCED Failure
    C5 - Contingency Plan Procedures for Key Settlement and Financial Transfer Processes
    C6 - Develop Plan for SE Failure
    C7 - Contingency Plan Procedures for a Backup Facility
    C8 - Contingency Plan Procedures for Portal/API Failure
    C9 - Contingency Plan Procedures for Site Unavailability
Notes: <number>

## Slide 8
http://nodal.ercot.com <number>
Meeting Summary – January 8 (continued)
On January 8, TPTF discussed the following:
  Review remaining Readiness Metrics and market comments in the PMO Working Readiness Metric Inventory (continued):
    Contingency Metrics (continued)
    C10 - Verify Single Point of Failure Recovery EMS/MMS/NMMS/CRR/COMS
    IMM Metrics
    IMM1 - Market Monitor Systems Capability
    Overall Readiness Metrics
    R0 - Market Participants Operations Readiness
    R1 - Nodal Readiness Declaration
    R2 - Develop Texas Nodal Market Launch Plan
  On January 8, TPTF endorsed ERCOT moving forward with the following metrics as modified by TPTF on January 8, 2008. The motion carried by roll-call vote, with 100% in favor and no abstentions. All Market Segments, except Independent Generator, were represented for the vote.
    ERCOT Internal Metrics
      E2 - Verify ERCOT Performance Monitoring Test Plan
      E4 - Transition Pricing Mechanisms
      E7 - Validate EDW Access and Accuracy of Postings Required by the IMM and PUCT Rules
Notes: <number>

## Slide 9
http://nodal.ercot.com <number>
Meeting Summary – January 8 (continued)
January 8 vote continued:
  Required by the IMM and PUCT Rules
    E10 - Validate EDW Commercial Systems Access Accuracy
    E11 - Validate EDW Compliance Data Access
    E14 - Verify QSE Performance Monitoring Test Plan
    E15 - Verify TSP Performance Monitoring Test Plan
  Energy Management Operations Metrics
    EMO3 - Verify Outage Evaluation System Functionality
    EMO8 - Conduct EECP Test
  Market Operations Metrics
    MO3 - Verify Supplemental Ancillary Services Market (SASM)
  Contingency Metrics
    C1 - Contingency Plan Procedures for Weekly, Daily and Hourly RUC Failure
    C2 - Contingency Plan Procedures for DAM Failure
    C3 - Contingency Plan Procedures for ICCP Data Failure
    C4 - Contingency Plan Procedures for SCED Failure
    C5 - Contingency Plan Procedures for Key Settlement and Financial Transfer Processes
    C6 - Develop Plan for SE Failure
Notes: <number>

## Slide 10
http://nodal.ercot.com <number>
Meeting Summary – January 8 (continued)
January 8 vote continued:
  Contingency Metrics
    C7 - Contingency Plan Procedures for a Backup Facility
    C8 - Contingency Plan Procedures for Portal/API Failure
    C9 - Contingency Plan Procedures for Site Unavailability
    C10 - Verify Single Point of Failure Recovery EMS/MMS/NMMS/CRR/COMS
  IMM Metrics
    IMM1 - Market Monitor Systems Capability
  Overall Readiness Metrics
    R0 - Market Participants Operations Readiness
    R1 - Nodal Readiness Declaration
    R2 - Develop Texas Nodal Market Launch Plan
On January 8, TPTF discussed the following:
  Market Rules Changes to language in Draft NPRR - Protocol Sections 4 and 6 Formula Clarifications and Related Revisions
    On January 8, TPTF endorsed forwarding to PRS the draft NPRR for Protocols Sections 4 and 6 Formula Clarifications and Related Revisions as amended at TPTF on January 8, 2008. The motion carried by roll-call vote, with 100% in favor and three abstentions (Austin Energy, CenterPoint Energy, and AEP). All Market Segments, except Independent Generator, were represented for the vote.
Notes: <number>

## Slide 11
http://nodal.ercot.com <number>
Meeting Summary – January 21
On January 21, TPTF discussed the following:
  Nodal Timeline Update
  Nodal Program Update
  Need for Draft NPRR for Scheduling and Operating Transmission Devices in the Nodal Environment
  EDS Update
    Testing concept for the 168-Hour Test
    Recent activities and status for EDS testing
  Review disposition of comments for the EDS - CRR Testing Market Participant Handbook v1.05
    On January 21, TPTF approved the EDS - CRR Testing Market Participant Handbook v1.06 as submitted. The motion carried by roll-call vote, with 100% in favor and one abstention (Exelon). All Market Segments, except Independent Generator, were represented for the vote.
  Verifiable Cost Subgroup Update
    Recent activities for the Verifiable Cost Subgroup
  DC Tie Subgroup Update
    Recent activities from the Jan. 17th DC Tie Subgroup Meeting
Notes: <number>

## Slide 12
http://nodal.ercot.com <number>
Meeting Summary – January 22
On January 22, TPTF discussed the following:
  Quality Center Update
    Quality Center Reports
    Software Problem Report (SPR) Defects
  Project Artifact Schedule
  Readiness Metric R3, 168-Hour System Stability Test and Trial Real-Time Settlement Metric to incorporate the following metrics:
    EMO4 - Run 7 Day Stability Test
    MO1 - Operate DA Market for 7 Days
    MO2 - Operate 7 Day market with RUC
    MO6 - Verify DAM Ancillary Services
  Readiness Metric N4, Network Modeling Single-Entry
  Revisions to Metric MP14, MP EDS-2 Trials Participation
    On January 22, TPTF waived notice to vote for Metric MP14, MP EDS-2 Trials Participation. The motion carried by roll-call vote, with 100% in favor and three abstentions (City of Dallas, Town of Flower Mound, and Coral Power). All Market Segments were represented for the vote.
Notes: <number>

## Slide 13
http://nodal.ercot.com <number>
Meeting Summary – January 22 (continued)
On January 22, TPTF discussed the following:
  On January 22, TPTF approved a Motion to request TAC approval for revisions to the Readiness Metric MP14, MP EDS-2 Trials Participation, as modified by TPTF on January 22, 2008, and to endorse ERCOT moving forward with the following Readiness Metrics:
    R3, 168-Hour System Stability Test and Trial Real Time Settlement
    N4, Network Modeling Single Entry
  The motion carried by roll-call vote, with 100% in favor and five abstentions (LCRA, City of Dallas, Town of Flower Mound, Coral Power, and Exelon). All Market Segments were represented for the vote.
Notes: <number>

## Slide 14
http://nodal.ercot.com <number>
Meeting Summary – January 22 (continued)
On January 22, TPTF discussed the following:
  IDA Punchlist Update
    Review disposition of comments for the IDA Punchlist
    Discuss the need for draft NPRR to address IDA Punchlist Items for MIS and EIP
  Private Use Networks (PUN) Subgroup Update
    Recent activities from the Jan. 11th PUN Subgroup Meeting
  NPRR092, Remove Voltage Schedules Requirement
    On January 22, TPTF approved a Motion to forward TPTF comments for NPRR092, Remove Voltage Schedules Requirement, to PRS for consideration. The motion carried by roll-call vote, with 100% in favor and no abstentions. All Market Segments, except Independent Generator, were represented for the vote.
  COMS Project
    Discuss clarifications for Emergency Operations Settlements
  EDW Update
    Disposition of comments for the EDW Conceptual System Design
      On January 22, TPTF approved the EDW Conceptual System Design v0.95. The motion carried by roll-call vote, with 100% in favor and one abstention (Reliant). All Market Segments were represented for the vote.
Notes: <number>

## Slide 15
http://nodal.ercot.com <number>
Meeting Summary – January 22 (continued)
On January 22, TPTF discussed the following:
  EDW Update (continued)
    Section 8 Performance Reports Update
  INF Update
    Disposition of comments for the Market Participant Identity Management Conceptual System Design
      On January 22, TPTF approved the INF MPIM CSD v1.7 as submitted. The motion carried by roll-call vote, with 100% in favor and one abstention (Reliant). All Market Segments, except the Independent Generator and Consumer segments, were represented for the vote.
  Real-Time Reports (RTR) Project Update
    Overview of the project
    Announce Conceptual System Design (CSD) document in review
  EIP Update
    Market Participant Data Access
      Update on the April 23, 2007 brochure "Understanding Market Participant Data Access“
Notes: <number>

## Slide 16
http://nodal.ercot.com <number>
Meeting Summary – January 22 (continued)
On January 22, TPTF discussed the following:
  EIP Update (continued)
    Disposition of comments for the External Interface Specification v1.07
      On January 22, TPTF approved the EIP External Interfaces Specification v1.07 with the understanding that additional descriptions would be added to the document as discussed at TPTF on January 22, 2008 to address comments received during the document review ending January 16, 2008, including descriptions for:
      - Key string composition for Outage mRIDs
      - PriceCurve multi-hour block
      - Explanations for OutageIdent, OutageWarning, LastModifiedby, - LastModified, versionID, groupID, OutageNotes
      - Difference between newSchedule and Schedule
      The motion carried by roll-call vote, with 100% in favor and two abstentions (CenterPoint and AEP). All Market Segments, except the Independent Generator, were represented for the vote.
    Disposition of comments for the MIS External Interfaces Specification v0.35
  Review NPRR090, Corrections of FIP-FOP in Energy Offers
    On January 17, PRS voted to reject Sections 4.4.9.2.1 and 4.4.9.4.2 and to forward PRS Recommendation Report and IA to TAC
Notes: <number>

## Slide 17
http://nodal.ercot.com <number>
Meeting Summary – January 23
On January 23, TPTF discussed the following:
  EDS testing issue:
    How will the changes that are necessary for the EDS system be authorized so that EDS testing may proceed while corresponding documentation updates proceed through the governance process?
    Proposed Revision for EMS White Paper:
      High Dispatch Limit (HDL) And Low Dispatch Limit (LDL) During Startup and Ancillary Service (AS) Recall
      On January 23, TPTF approved the updates in the HDL And LDL During Start up and AS Recall white paper v1.1 as submitted. The motion carried by roll-call vote, with 100% in favor and no abstentions. All Market Segments, except the Independent Generator, were represented for the vote.
  Updates and new effective period for the Service Level Agreement for Nodal EDS Environments
    On January 23, TPTF approved the updated SLA for Nodal EDS Environments v3.3 as modified by TPTF on January 23, 2008. The motion carried by roll-call vote, with 100% in favor and one abstention (CPS San Antonio). All Market Segments, except the Independent Generator, were represented for the vote.
  Resource Registration Update
Notes: <number>

## Slide 18
http://nodal.ercot.com <number>
Meeting Summary – January 23 (continued)
On January 23, TPTF discussed the following:
  Review disposition of comments for draft NPRR for PUCT 25.505 Publication of Resource and Load Information
  Revisions for configuration limitation in whitepaper IDA003, Combined-Cycle Unit Modeling in the Nodal Design
  Discuss Market Participant Satisfaction Survey Results
Notes: <number>

## Slide 19
http://nodal.ercot.com <number>
Next Meetings
Next meetings
  Monday February 4 through Wednesday February 6
  Thursday February 21 and Friday February 22
  Monday March 3 through Wednesday March 5
  Thursday March 20 and Friday March 21
Notes: <number>

## Slide 20
http://nodal.ercot.com <number>
Next Meetings (continued)
On February 4 through February 6, likely topics include:
  Nodal Program Update / Nodal Timeline Update
    Discuss “pens-down” dates for systems functionality
    Posting of Severity 1 & 2 defects
  NMMS Update
    Open Severity 1 defects for NMMS
  Market Rules Update
    Plan for “nodalizing” remaining protocols
  EDS Update
    Disposition of comments for the updates for EDS 3 SCED Market Participant Handbook v3.01
    Approach to 168-Hour Test, including settlement issues
    LMP reasonableness Daily report review
    Process for authorizing temporary changes for EDS system while corresponding documentation proceeds through the approval process
    Documentation synchronizations related to the recent formula revision in the EMS White Paper, HDL and LDL During Startup and AS Recall
  Draft NPRR for 3.10.7.5.1, Continuous Telemetry of the Status of Breakers and Switches
Notes: <number>

## Slide 21
http://nodal.ercot.com <number>
Next Meetings (continued)
On February 4 through February 6, likely topics include:
  MER Update
    Review market feedback for the Market Participant Satisfaction Survey Results and Action Plan
  EIP Update
    Review updates for the MIS External Interfaces Specification
  Current Day Report (CDR) Project Update
    Disposition of comments for the Current Day Reports Conceptual System Design
  INF Hardware Update
  Outage Scheduler Update
    Status of detailed design and FAT testing
  Section 8 Update
    Discuss NPRR097, Changes to Section 8 to Incorporate Role of TRE, the IMM, and the Concept of Market Compliance, including:
      Language differences between NPRR097 and current Nodal Protocols
      Activities of the Feb. 4 Task Force
  DC Tie Update
    Reasons for imports of emergency power over DC Ties in 2007
    Draft NPRR for settlements of emergency power over DC Ties
Notes: <number>

## Slide 22
http://nodal.ercot.com <number>
Next Meetings (continued)
On February 4 through February 6, likely topics include:
  EDW Update
  COMS Project
    Approach and possible NPRR language to clarify Emergency Operations Settlements
    Discuss Fuel-Oil Index Price
  Draft NPRR for incorporating PUCT 25.505 Publication of Resource and Load Information
    Recent revisions to the draft NPRR to reflect feedback from the market and from nodal projects
  DAM Subgroup Update
    Recent activities for the TPTF Subgroup for Self-Committed Resources in DAM
  WMS Settlement Point Subgroup Update
    Update on activities for the Jan 28th High-Low Task Force Meeting
  Update on Combined-Cycle white paper discussion with IMM
Notes: <number>

## Slide 23
http://nodal.ercot.com <number>
Approval of Readiness Metrics
On January 8, TPTF voted to endorse ERCOT moving forward with the metrics E2, E4, E7, E10, E11, E14, E15, EMO3, EMO8, MO3, C1 thru C10, IMM1, R0, R1, and R2 as modified by TPTF on January 8, 2008. The motion carried by roll-call vote, with 100% in favor and no abstentions. All Market Segments, except the Independent Generators, were represented for the vote.
On January 22, TPTF approved a Motion to request TAC approval for revisions to the Readiness Metric MP14, MP EDS-2 Trials Participation, as modified by TPTF on January 22, 2008, and to endorse ERCOT moving forward with the following Readiness Metrics:
  R3, 168-Hour System Stability Test and Trial Real Time Settlement
  N4, Network Modeling Single Entry
The motion carried by roll-call vote, with 100% in favor and five abstentions (LCRA, City of Dallas, Town of Flower Mound, Coral Power, and Exelon). All Market Segments were represented for the vote.
Notes: <number>

## Slide 24
http://nodal.ercot.com <number>
Approval of Readiness Metrics (continued)
Request TAC approval for ERCOT to move forward with the metrics:
  E2 - Verify ERCOT Performance Monitoring Test Plan
  E4 - Transition Pricing Mechanisms
  E7 - Validate EDW Access and Accuracy of Postings Required by the IMM and PUCT Rules
  E10 - Validate EDW Commercial Systems Access Accuracy
  E11 - Validate EDW Compliance Data Access
  E14 - Verify QSE Performance Monitoring Test Plan
  E15 - Verify TSP Performance Monitoring Test Plan
  EMO3 - Verify Outage Evaluation System Functionality
  EMO8 - Conduct EECP Test
  MO3 - Verify Supplemental Ancillary Services Market (SASM)
  C1 - Contingency Plan Procedures for Weekly, Daily and Hourly RUC Failure
  C2 - Contingency Plan Procedures for DAM Failure
  C3 - Contingency Plan Procedures for ICCP Data Failure
  C4 - Contingency Plan Procedures for SCED Failure
Notes: <number>

## Slide 25
http://nodal.ercot.com <number>
Approval of Readiness Metrics (continued)
Request TAC approval for ERCOT to move forward with the metrics:
  C5 - Contingency Plan Procedures for Key Settlement and Financial Transfer Processes
  C6 - Develop Plan for SE Failure
  C7 - Contingency Plan Procedures for a Backup Facility
  C8 - Contingency Plan Procedures for Portal/API Failure
  C9 - Contingency Plan Procedures for Site Unavailability
  C10 - Verify Single Point of Failure Recovery EMS/MMS/NMMS/CRR/COMS
  IMM1 - Market Monitor Systems Capability
  Modified MP14, MP EDS-2 Trials Participation
  N4, Network Modeling Single Entry
  R0 - Market Participants Operations Readiness
  R1 - Nodal Readiness Declaration
  R2 - Develop Texas Nodal Market Launch Plan
  R3, 168-Hour System Stability Test and Trial Real Time Settlement
Notes: <number>

## Slide 26
http://nodal.ercot.com <number>
TAC Approval of Milestones
On January 8, TPTF approved the INF Market Participant Identity Management Requirements v2.3 with the understanding that it will be updated to incorporate changes recommended by TPTF on January 8, 2008. The motion carried by roll-call vote, with 100% in favor and five abstentions (First Choice Power, AEP, City of Allen, City of Eastland, and Coral Power). All Market Segments, except Cooperative, were represented for the vote.
On January 22, TPTF approved the EDW Conceptual System Design v0.95. The motion carried by roll-call vote, with 100% in favor and one abstention (Reliant). All Market Segments were represented for the vote.
On January 22, TPTF approved the INF MPIM CSD v1.7 as submitted. The motion carried by roll-call vote, with 100% in favor and one abstention (Reliant). All Market Segments, except the Independent Generator and Consumer segments, were represented for the vote.
The Transition Plan says: “Any declaration of the accomplishment of a major milestone (business requirements, conceptual design, and successful completion of Market Participant testing) or a decision to proceed is contingent on the approval of both ERCOT and TAC.”
Request TAC acknowledge TPTF completion of the following Milestones –
  INF Market Participant Identity Management Requirements v2.3 complete
  Enterprise Data Warehouse Conceptual System Design v0.95 complete
  INF Market Participant Identity Management Conceptual System Design v1.7 complete
Notes: <number>

## Slide 27
http://nodal.ercot.com <number>
Questions
?
Notes: <number>