## Slide 1: Texas Nodal Market Implementation Program Update
Jerry Sullivan

## Slide 2: Overall program status remains amber
Nodal
Delivery
Quality
Schedule
Cost
Cost
Schedule
Scope / Quality
Legend
Summary
Green
Revised budget approved by ERCOT BOD.
Preparing for revised Fee Filing with the PUC.
Amber
Most Nodal projects have now frozen changes to functionality required for the 168 hour test (9/1/2008)
Red
Amber
Green
Go-live = 12/1/08
Go-live = <30 days+
Go-live = >30 days+
Program is aligned with current protocols
Program is aligned to previous protocol version
Program is not aligned to protocols
Amber
Current product quality is not sufficient for Nodal launch
Most Nodal products currently achieve quality standards
All Nodal products currently achieve quality standards
Single Entry Go-Live delayed – no projected impact on Go-Live
Key checkpoints being put in place to ensure ongoing viability of 12/1/2008
Test results are being managed in Quality Center and results are being used to track defects for resolution.
Reports being published weekly to http://nodal.ercot.com
Red
Estimate at Complete = <$263m
Estimate at Complete = < $263m + 10%
Estimate at Complete = >$263m + 10%

## Slide 3: Single Entry Model Go-Live postponed to 5/31 – no predicted impact on Go-Live
Status:
  Current NMMS FAT cycle taking longer than expected due to significant SEV 1s.
  Due to defects ERCOT has not started NMMS Market trials on time (original start was Nov 2007)
  NMMS Market trials directly impact Single Model Entry Go Live (Originally March 31, 2008)
Ramifications:
  NMMS Revised schedule for defect correction is by March 1, 2008
  NMMS MP Trials to start immediately thereafter
  Single Entry Go Live now scheduled for May 31, 2008
  Sandbox being established to enable TSPs to gain familiarity with NMMS
Implications / Issues in front of us:
Original Single Model Entry Go Live was based on need for an annual CRR auction in Summer 2008 for Dec Go Live. Constraint no longer exists.
Single Model Entry Go Live MUST be in place by August 2008 to verify the ERCOT model used for the Go Live sequence.
All of NMMS functionality is built by vendor, and thus ERCOT is continuing to put pressure on the vendor to correct issues.
ERCOT management is working with Siemens management on any issues that ERCOT can control.
Notes: <number>

## Slide 4: Key checkpoints are being put in place to assure ongoing viability of 12/1/2008
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
2008
Single Entry Model Go-Live
Nodal Market Go-Live
168 Hr Test
EDS 4
Go Live Sequence
CIM for EDS Go/No-Go
CIM Health-check
Integration Health-check
Performance Health-check
Defect Health-check
168 Hour Test Go/No-Go
Go-Live Go/No-Go
Each checkpoint will review viability of 12/1/08 in addition to the specific focus indicated in the title above
The results of the assessment will be reviewed with TPTF, TAC and BOD

## Slide 5: Critical path defined by successful EDS trials leading into the 168 hr test... requiring timely delivery of core application & successful MP participation
All sections under the “System Testing and Nodal Market Implementation Track” of the ERCOT Nodal Transition Plan will be completed before starting the 168 hour test, with the exception of:
  5.4.9 168-Hour Test and Trial Real Time Settlement
  5.4.11 Real Time Operation and Settlement
MP Trials & NM Verification
SCED & LMP Posting for 6 months
ICCP / P2P
SE Tuning
E1 R2
E2 R3
E2 R4
E3 R5
E3 R6
LFC Testing
E3 R7
CRR Testing
E4 R9
CMM, DAM & RT Settlements, Verifiable Costs & Disputes
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
DAM, SASM & RUC execution, DAM Stability Test, EECP, DST, Compliance
E4 R8
168 Hour Test
EDS 1
EDS 2
EDS 3
EDS 4
Today
1 Load-only QSE outstanding

## Slide 6: PRR 727 governs the time available for completing the 168 Hour Test
PRR 727:
  No part of the nodal market design may start operation until all the Market Readiness Criteria for that part of the nodal market design have been met
  Certification that all Market Readiness Criteria have been met must be made at least by each of the following: the TPTF, TAC, ERCOT Staff and the ERCOT Board.
  Upon such certification, ERCOT shall issue two Notices…the first Notice no less than thirty days prior to the effective date or retirement date...and the second Notice no less than ten days prior...
TAC | Oct 2, 2008 | This implies that we have only 32 days to succesfully complete 168 hour test
ERCOT BOD | Oct 21, 2008 | 
TPTF | TBD | 
Committee | Last scheduled meeting prior to 10/31 | Comments
Sept
Oct
Nov
Start 168 Hour Test
10/31 First Market Notice
11/21 Second Market Notice
10/2 TAC Meeting
10/21 ERCOT BoD meeting
12/1: RTM Go-Live

## Slide 7: ERCOT and Market Participant involvement in 168 Hour Test
ERCOT involvement:
  Staff from ERCOT operations (business and IT) will execute the test
  Staffing will be sufficient to meet business operations and the IT production service level agreement
  Management of daily activities will occur through the ERCOT chain of command
  All defined daily tasks for Nodal will be executed
  The Nodal Program will setup a daily conference call with all MPs to go through issues
  The Nodal Program will only coordinate issue resolution if significant errors occur
Market Participant involvement:
  Staff from the MPs operations (business and IT) will execute the test
  Staffing will be sufficient to meet business operations and the production service level agreement
  Management of daily activities will occur through the MP’s normal operational chain of command
  All protocol defined interactions between MPs and ERCOT will be performed according to the timeline
  Data submissions will reasonably resemble post Go-live submissions
  ICCP must be continually updated by the MPs
  The 168 hour test is the final Qualification test and all MPs are required to participate during the entire test

## Slide 8: Interpretation of the term “significant error”
Significant error:
  Severity 1 defects (Data loss / Critical error, e.g., it won’t work, system crash, etc.)
  Severity 2 defects (Loss of core functionality without workaround)
  The Nodal Executive Director, with support from business and IT and Transition Sponsors, is responsible for deciding the severity of an error and for resetting the 168 hour clock
Upon detection of a significant error, ERCOT shall:
  Halt the 168 hour test
  Work with the vendors / internally to fix all issues that have been identified
  Provide 2 hour notice to MPs before re-starting the 168 hour clock
The EDS environment will continue to be operational with functions not affected, even when the 168 hour clock has been stopped

## Slide 9: Most Nodal projects have now frozen changes to functionality required for the 168 hour test (9/1/2008) – and subsequently Go-Live
Status:
  The final MMS software drop commences FAT 4/22
  NMMS, EMS, CRR, COMS and MMS are already “pens down” on additional changes
  There is some tolerance for changes relating to reports i.e. EDW (within certain constraints affecting source systems)
  We are working with TPTF on the proposed treatment of items which cannot make the 168 Hour Test – including those developed by Nodal before go–live, ready for subsequent production release
Implications on additional NPRRs
  Only changes with a systems impact deemed absolutely essential for the correct operation of the Nodal market can be considered (in the knowledge that their introduction may delay Go-Live)
  The process of impact analysis of all new NPRRs (including those with no system impacts) diverts Nodal Subject Matter Experts from other critical tasks
  Non-essential changes should be tabled or will be boxed in the Protocols
We have sought TPTF’s assistance in identifying non-essential changes early (to minimize impact analysis demands) and verifying as essential for Go-Live those NPRRs with a system impact

## Slide 10: Progress Report: Training Delivery
Course | Length (days) | Classroom Deliveries To-Date | WBT Available On-line?
ERCOT Nodal 101 | 1 | 49 | 
Economics of LMP | 1 | 24 | N/A
Transition to Nodal Markets | Web-based | N/A | 
Load Serving Entities 201 | 1.5 | 8 | 
Basic Training Program | 4.5 | 5 | Apr 2008
Network Model Management System | 1 | 3 | 
Congestion Revenue Rights | 1 | 5 | 
Settlements 301 | 3 | 1 | N/A
NOIE QSE Operations | 1 | 1 | Apr 2008
Generation 101 | 2 | 1 | Apr 2008

## Slide 11: Progress Report: Training Development
Course (length, days) | Subgroup Review | Beta Review | Classroom Delivery | Web Delivery
Basic Training Program (4.5) |  | X | X | Apr 2008
NOIE QSE Operations (1) |  |  |  | Apr 2008
Market Settlements (3) |  |  |  | N/A
Generation 101 (2) |  |  |  | April 2008
Generation 201 (1) |  | Apr 2008 | May 2008 | Jun 2008
Generation 301 (1) | Feb 2008 | May 2008 | Jun 2008 | Jul 2008
Transmission 101 (2.5) |  | May 2008 | Jun 2008 | Jul 2008
ERCOT 101 for Wind Generation (1) |  | Apr 2008 | May 2008 | Jun 2008
Market Information System (TBD) | TBD | TBD | TBD | TBD

## Slide 12: Progress Report: Training Development – Post Go-Live
Course | Length, Days | Delivery Date
Extended Training - System Dynamics | 1 | Once a month within the first 12 months of full Texas Nodal Market Operations
Scenario-Based Training for QSEs with Generation Resources | 1 | Once a Quarter, 2009 only
Scenario-Based Training for Load Serving Entities | 1 | Once a Quarter, 2009 only
Scenario-Based Training for TSPs and DSPs | 1 | Once a Quarter, 2009 only
Post Go-Live

## Slide 13: Progress Report: Training Delivery
Course (length, days) | Classroom Deliveries To-Date | Passed / Total |  | 
 |  | MP | ERCOT | Total
ERCOT Nodal 101 (1) | 49 | 1547/2164 | 522/724 | 2069/2888
Economics of LMP (1) | 24 | 556 | 183 | 685*
Transition to Nodal Markets (WBT) | N/A | 168/309 | 85/135 | 253/444**
Load Serving Entities 201 (1.5) | 8 | 215/362 | 13/42 | 228/404
Basic Training Program (4.5) | 5 | 140/209 | 4/6 | 144/215
Network Model Management System | 3 | 53/62 | 11/18 | 64/80
Congestion Revenue Rights | 5 | 98/178 | 11/17 | 109/195
Settlements 301 | 1 | 20/50 | 2/4 | 22/54
NOIE QSE Operations | 1 | 26/29 | 3/3 | 29/32
Generation 101 | 1 | 20/23 | 3/3 | 23/26
* ILT only / no exam ** WBT only

## Slide 14: Progress Report: Training Delivery – Scheduled Training
Notes: <number>
<footer>
<header>
<date/time>
<number>

## Slide 15: MPs remain AMBER Overall, Engagement Scores Improve
EDS1 and EDS2 remain open. Associated metrics are past due and therefore RED.
Based on December Market Participant NODAL Engagement Survey Results:
  First pass of self-reported Training GREEN for QSEs and TDSPs
  No QSE with Resource RED due to Engagement.
    Xtend remains RED due to Connectivity Test delays
  No TDSP RED due to Engagement.
    Rayburn remains RED due to Connectivity Test delays
  QSEs without Resources category improved from RED to AMBER.
  7 QSEs without Resources RED due to Engagement.
    Ambit Energy
    APN Starfirst
    BOC Energy Services
    JPMorgan Ventures Energy
    Merrill Lynch Commodities
    Vega Resources
    WCW International
  LSEs scored for first time and are AMBER for both engagement and self-reported Training.
http://scorecard.ercot.com/
Note: Market Participant summary scores are now visible to anyone – even without a password

## Slide 16: ERCOT remains AMBER Overall due primarily Engagement and Training scores
ERCOT Engagement Results Remain amber. Summary of results:
  Finance improves from amber to green and is the only division to achieve green status
  Human Resources was green in last survey and has fallen to amber sighting concerns over staffing
  Core Divisions – Information Technology, Systems Operations, and Market Operations - have not completed their transition plans
  Both Market Operations and Systems Operations highlighted concerned over processes and procedures and test planning
  Market Operations has not completed their training plan nor allocated their training budget
  ERCOT Staffing is Yellow. Summary of Status:
  Staffing and organizational sizing models have been completed.
  Approval of staff funding not complete - targeted for Q1.
  Staffing to plan is progressing more slowly than expected.
  ERCOT Training
  Finance, Information Technology, and Market Operations are behind in execution of their training plans
http://scorecard.ercot.com/
Note: ERCOT (and EDS) summary scores are now visible to anyone – even without a password
This version in ITest