## DEFINITIONS
Spreadsheet Definitions
MO CURRENT TAB: How the current 2008 PPL shows today
MO RECOMMENDATIONS TAB: CART Recommendations for Rerank and Priority
RO CURRENT TAB: How the current 2008 PPL shows today
RO RECOMMENDATIONS TAB: CART Recommendations for Rerank and Priority

## 2008
MORO Merged 2008 Project Prioritization - PUCT, Market and ERCOT Projects
Source | Committee | Prog Area | Source Doc | Project | Project No. | Current Status | 2008 Priority | 2008 Rank | 2008 Budget Range | 2008 Running Range | Comments | Project Description
PUCT/MKT | RMS | RO | PRR672 PRR707 PUCT Project 33049 | Terms and Conditions requirements, not limited to Texas SET changes, Performance Measures | 60008_01 | Planning | 0 - Previously Approved | 0.1 | $250k-$500k | $250k-$500k | Planned Carry over Reasons: Nodal Impacts: Test Environment planning around schedule Go-Live Forecast: Scheduled 05/10/2008
PUCT | RMS | RO | PUCT Project 24462 | Performance Measures Reporting Requirements (changes to Project 24462) | 60007_01 | Cancelled | 0 - Previously Approved | 0.15 | 0 | $500k-$1M | Project Cancelled Project Scope moved to PR60008
Market | RMS | RO | SCR745 | ERCOT Outage Evaluation and Resolution (TDTWG)--Phases I and II | 60006_01 | Execution | 0 - Previously Approved | 0.2 | <$100k | $250k-$500k | Unplanned Carry Over Reasons: Issues discovered in test with SAN Fencing, transaction integration, and low availability from HP Support causing delays in resolution of issues to complete testing in 2007. Go-Live Forecast: Rescheduled 03/08/2008 | Identify market facing servers without redundancy. Implement new code and hardware when possible to eliminate single points of failure. This will include clustering market facing servers and implementing code which will be able to switch from one system
Market | RMS | RO | SCR749 | MarkeTrak Enhancements (Workflow & Reporting) | 70007_01 | Planning | 0 - Previously Approved | 0.3 | $1M-$2M | $1M-$2M | Planned Carry over Reasons: Execution not starting until 2008. Nodal Impacts: Environment (Siebel Nodal Code Freeze) Go-Live Forecast: Scheduled thru 2008 | Enhancements to the functionality of MarkeTrak requested under SCR749
Market | RMS | RO | SCR748 | Website Enhancements for ERCOT Outages | 70006_01 | Closing | 0 - Previously Approved | 0.4 | <$10k | $1M-$2M | Unplanned Carryover Reasons: Closing Phase ONLY Go-Live Completed: 11/22/2007 | To add functionality on the ERCOT website for: • Calendar of dates/times for planned outages affecting retail. • Unplanned Outage Alert with web message capability • Log of outages
ERCOT | MO | MO |  | Maestro Replacement - Phase 2 | 50137_02 | Closing | 0 - Previously Approved | 0.5 | <$10k | $1M-$2M | Unplanned Carryover Reason: Closing Phase ONLY Go-Live Completed: 12/14/2007 | This project will replace ERCOT’s current batch job scheduling software. The current scheduling software, Maestro, experiences issues outlined below: • Maestro is currently not supported – Major upgrade required • Maintenance cost expensive due to CPU Pr
ERCOT | RO | RO |  | MO SAS 70 Procedures Optimization (fka EIS Siebel to Lodestar Comparison | 70005_01 | Execution | 0 - Previously Approved | 0.6 | $250k-$500k | $1M-$2M | Unplanned Carry Over Reasons: Delays in receiving hardware and software in 11/2007 Go-Live Forecast: 02/15/2008 | This project will implement hardware, software and licenses that are needed to implement the SAS 70 procedures optimization tool (System Audit Standards) this will lay the foundation to create an improved processes to perform retail data comparisons (ie. Siebel to Lodestar).
ERCOT | MO | MO |  | ERCOT.com Registered Access | 60077_01 | Execution | 0 - Previously Approved | 0.7 | <$100k | $1M-$2M | Unplanned Carry Over Reasons: Dependency on Nodal for Google search engine adevelopment Go-Live Forecast: Q108 | This project will enhance the Operations and System Planning Data section on the ERCOT website by changing the look and feel of the section to match the ERCOT website, improve navigation and bring the security aspects into compliance.
ERCOT | RMS | MO |  | COGNOS Infrastructure (aka Enhancements to SCR727 - Ph2) | 50024_02 | Execution | 0 - Previously Approved | 0.8 | <$100k | $1M-$2M | Unplanned Carry Over Nodal Impacts: Resources - Carry over due to extended stabilization of COGNOS Reports Go-Live Completed: 11/03/2007 | Subproject to provide market-requested enhancements to SCR727 data extract
ERCOT | MO | MO |  | Collage Infrastructure Redesign | 70038_01 | Execution | 0 - Previously Approved | 0.9 | $100k-$250k | $1M-$2M | Planned Carry Over Go-Live Forecasted: 02/15/2008 | Software that supports ERCOT.com deployments is taking too long to run through its process each night. This puts us at risk of not having current information on the website.
ERCOT | MO | MO |  | MV90xi System Upgrade Project | 70048_01 | Execution | 0 - Previously Approved | 0.91 | <$10k | $1M-$2M | Unplanned Carry Over Reasons: Build out of iTest delayed due to AIX and Nodal efforts. Go-Live Forecasted: 03/28/2008 | Perform replacement of non-standard hardware and upgrade of software for ERCOT’s MV90xi system.
ERCOT | MO | MO |  | Lodestar Upgrade | 40066_04 | Planning | 0 - Previously Approved | 0.92 | $250k-$500k | $1M-$2M | Planned Carry Over Nodal Impacts: Nodal Dendency on upgrade Go-Live Forecasted: Early Q208 | Maintain efficiency, and reliability of the LodeStar application to enable ERCOT to meet Energy Aggregation and Billing & Settlements business needs
ERCOT | RO | RO |  | Registration Data Model Enhancement (formerly ESIID Account Table Split) | 60015_01 | Planning | 0 - Previously Approved | 0.93 | $1M-$2M | $1M-$2M | Unplanned Carry Over Reasons: Delays due to Procurement negotiations of Vendor Contracts with Oracle Go-Live Forecasted: Q108 (Data Model Assessment ONLY) | Normalize type of data associated to business objects. Multiple business objects are using the same tables which are growing large causing performance and scalability issues.
ERCOT | MO | MO |  | ERCOT System Throughput for IDR (Advanced Metering) | 70057_01 | Planning | 0 - Previously Approved | 0.96 | $100k-$250k | $2M-$3M | Planned for 2008 (Initiated early in 2007) Go-Live Forecasted: Q408 | This project involves the analysis and implementation of the current retail and wholesale systems to determine possible enhancements that could result in increases to the volume of IDR. Extracts and ODS analysis will be included in the analysis effort. Short-term effort for any configuration scaling will be delivered in 2008 and Conceptual Design for Long-term solution will be provided with this project as well.
ERCOT | RO | RO |  | Data Research and Reporting (formerly ETS Transition to EDW) | 50088_01 | Planning | 0 - Previously Approved | 0.97 | $500k-$1M | $2M-$3M | Planned Carry Over Reasons: Delays due to resource constraints from AIX and Nodal EDW efforts Go-Live Forecasted: 2009 | Deliver a data research and reporting tool for ERCOT Commercial Operations. The project will provide accurate, complete, and efficient reporting and research capabilities of retail transaction data.
ERCOT | RO | RO |  | EDW EAI Transition (inc. PaperFree & NAESB) | 50061_01 | On Hold | 0 - Previously Approved | 0.98 | <$100k | $2M-$3M | Planned Carry Over Reasons: Currently "ON HOLD" Status due to resource and enviornment constraints with AIX ODS implementation Go-Live Forecast: TBD until comes "Off Hold" | This project will transition of Paperfree and NAESB Data to the Operational Data Store (ODS), configure replication tool for these databases as well, and build COGNOS subject Area views for reporting.
ABOVE THIS LINE --Projects carry over from 2007
Market / Legislature | RMS | RO | HS | Small Renewables - RMWG | 80028_01 | Not Started - 2008 | 1 - Critical | 1 | $3M-$4M | $3M-$4M
Market | RMS | RO |  | Advanced Metering - RMWG/TX SET | 80027_01 | Not Started - 2008 | 1 - Critical | 2 | $4M-$5M | $4M-$5M | Placeholder awaiting TX SET required changes
Market | COPS | MO | PRR478 PR385 | Use of Lagged Dynamic Samples for New Load Profiles & DLC Implementation / Demand Response for Settlement | 40056_01 | Not Started - 2008 | 2 - High | 3 | $4M-$5M | $4M-$5M | This needs to be evaluated for Cancellation. Is this still valid for 2008? | This is a change to the method for creating Load Profiles allowing for the use of lagged dynamic samples for new profiles adopted subsequent to market open.
BELOW THIS LINE - Projects Deferred (Will be placed on the 2009 PPL)
Market | RMS | RO | SCR745 | ERCOT Outage Evaluation and Resolution (TDTWG)--Phase III | 60006_02 | Deferred | 9 - Parking Lot | 2009 |  |  | ERCOT recommends leaving this as Parking Lot for 2009 due to need for analysis from AIX stabilization. This phase was to address Database availablilty specifically that are under infrastructure changes in the AIX Project Effort. | Identify market facing servers without redundancy. Implement new code and hardware when possible to eliminate single points of failure. This will include clustering market facing servers and implementing code which will be able to switch from one system to the other without an outage. This project may be addressed in SCR-745
ERCOT | RO | RO |  | Create Retail XML Transaction Format to MPs - set the national standard | 60065_01 | Pending Cancel | 9 - Parking Lot |  |  |  | ERCOT will cancel this project in next CART Voting Meeting due to limited drive and supporting information | Create a Market Standard XML with coordination with other industry standar groups.
ERCOT | RO | RO |  | NAESB Failover - TDTWG | New | Pending Cancel | 9 - Parking Lot |  |  |  | ERCOT will cancel this project in next CART Voting Meeting due to limited drive and supporting information. Have not seen any global events requiring a need for a 2nd protocol. | Create transport protocol failover for submission from ERCOT to Market Participants. Will require a defintion for transport SLA.
[7 empty] | Current 08 Combined Fund: |  | $7.3M
[7 empty] | Current Combined 08 Forecast Spend: |  | $4.5M
[7 empty] | 2008 Combined 08 Variance: |  | $2.8M

## 2009
MORO Merged 2009 Project Prioritization - PUCT, Market and ERCOT Projects
Source | Committee | Prog Area | Source Doc | Project | Project No. | Current Status | Project Manager | 2009 Priority | 2009 Rank | 2009 Budget Range | 2009 Running Range | Summary Description | Benefit Summary
Market | RMS | RO | SCR749 | MarkeTrak Enhancements (Workflow & Reporting) | 70007_01 | Planning | H. Parrish | 0 - Previously Approved | 0.1 | <$100k | <$1M | Planned Enhancements to the functionality of MarkeTrak | Reduce manual workarounds for efficient use of Retail Customer Choice resources, improve reporting capabilities, enhance workflows and improve validations for ERCOT and Market Participants.
ERCOT | MO | MO |  | ERCOT System Throughput for IDR (Advanced Metering) | 70057_01 | Planning |  | 0 - Previously Approved | 0.2 | <$100k | <$1M | Planned: Provide incremental increases in IDR processing capability for ERCOT systems.
ERCOT | RO | RO |  | Data Research and Reporting (formerly ETS Transition to EDW) | 50088_01 | Planning | H. Day | 0 - Previously Approved | 0.9 | <$100k | <$1M | Planned: Transition of ETS reporting from Data Archive to Enterprise Data Warehouse | Improved reporting and analysis efficiency (7 hours per workday); Improved development efficiencies (16 hours per workday)
ERCOT | RO | RO |  | EDW EAI Transition (inc. PaperFree & NAESB) | 50061_01 | On Hold | H. Day | 0 - Previously Approved | 0.4 | <$100k | <$1M | Transition of EAI reporting from Data Archive to Enterprise Data Warehouse | Fewer ad hoc data requests (4 hours per workday), less production support of data archive (4 hours per workday), improved daily research of Siebel service order changes (8 hours per workday)
ABOVE THIS LINE --Project carry over from 2008
Market Legislature / Market - rename | RMS | RO |  | Small Renewables - RMWG | 80028_01 | Not started |  | 1 - Critical | 1 | $500k-$1M | <$1M | Planned:
Market | RMS | RO |  | Advanced Metering - RMWG/TX SET | 80027_01 | Not started |  | 1 - Critical | 2 | $500k-$1M | $1M-$2M | Planned:
ERCOT | TPTF | MO |  | Additional Post-Nodal Efforts | TBD | Not started |  | 1 - Critical | 5 | TBD |  | Additional post-nodal efforts - not yet defined
ERCOT | RO | RO |  | Website Enhancements for ERCOT Outages | 70006_02 | Not started |  | 2 - High | 6 | $250k-$500k | $1M-$2M | ERCOT requested enhancements to automate the email notification and the helpdesk alert. Dependent on Remedy Helpdesk tool expected to deliver in
ERCOT | MO | MO |  | COMS Extract, Report & Web Services Monitoring & Usage Statistics | 80032_01 | Not started |  | 2 - High | 7 | $250k-$500k | $2M-$3M | Provide research capabilities for Commercial Operations extract, report and web services data for internal business users, which include monitoring functionality and usage analysis capabilities.
ERCOT | RO | RO |  | Exception Reporting / Monitoring Enhancements | 70008_01 | Not started |  | 2 - High | 8 | $250k-$500k | $2M-$3M | Automate current exception reporting to monitor protocol compliance for processing exceptions. Create new exception reports using new data available from RBP and/or EDW projects. | Exception reporting in Retail Customer Choice has been very manual. There are protocol requirements that may not be met due to the lack of logging after the processing occurs.
ERCOT | RO | RO |  | Systematic Exception Reprocessing Functionality | 70009_01 | Not started |  | 2 - High | 9 | $500k-$1M | $2M-$3M | Automate current exception processing to meet protocol. Create reporting features after processing occurs. | Exception processing in Retail Customer Choice has been very manual. There are protocol requirements that may not be met due to the manual efforts.
ERCOT | RO | RO |  | EDW EAI Transition (inc. PaperFree & NAESB) | 50061_02 | Not started |  | 2 - High | 10 | $100k-$250k | $3M-$4M
ERCOT | RO | RO |  | EDI Transaction logging | 60062_01 | Not started |  | 2 - High | 11 | $100k-$250k | $3M-$4M | Change the Paper Free application system to log all ANSI records to TRLOG and to log all TXSET records to a new table which will better support current and future business needs. | Improve performance and accessibility of data. The suggested changes in the logging details will allow users to access the data without needing a cross-reference sheet telling them what the columns are in TRLOG and what data (per transaction type) is be
ERCOT | RO | RO |  | 814 inbound XML rewrite (impacts input from portal only) | 60043_01 | Not started |  | 2 - High | 12 | $100k-$250k | $3M-$4M | Re-Write of Inbound 814 XML maps to Increase Efficiency, Reliability and Stability of ERCOT transaction data processing. | Our experience with splitting the inbound 814 X12 maps has shown that reducing the complexity of the map (by implementing clean flowing logic) can reap significant performance gains. The time to analyze and correct any logic errors has been decreased by
ERCOT | RO | RO |  | Commercial Apps - Calendar Consolidation | 60033_01 | Not started |  | 2 - High | 13 | $250k-$500k | $3M-$4M | Develop single business calendar for use by all retail applications | Reduced rework for both market and ERCOT by eliminating possibility of out of sync conditions between multiple business calendars (50 hours per year of data repair activity for CRs and TDSPs)
ERCOT | RO | RO |  | Name to DUNS conversion | 60059_01 | Not started |  | 2 - High | 14 | $100k-$250k | $4M-$5M | Change the Paper Free application system to utilize DUNS numbers as opposed to Market Participant company names. | Consistent naming standards within Paperfree system.
ERCOT | RO | RO |  | MP configuration Table | 60060_01 | Not started |  | 2 - High | 15 | $100k-$250k | $4M-$5M | Remove all of the MPDB.conf files in the MB/PF systems and consolidate all of the configurations into a single table. The complexity of adding new MP to the system must be reduced in order to remove the number of errors that are encountered when adding / | The complexity of adding new MP to the system must be reduced in order to remove the number of errors that are encountered when adding / modifying MP information.
ERCOT | RO | RO |  | MarkeTrak Phase 3 | 80030_01 | Not started |  | 2 - High | 16 | $100k-$250k | $4M-$5M
ERCOT | RO | RO |  | Retail Application Upgrades | 80031_01 | Not started |  | 2 - High | 17 | $1M-$3M | $5M-$6M
ERCOT | RO | RO |  | Enrollment Postcard Notification Process | 80029_01 | Not started |  | 2 - High | 18 | $100k-$250k | $5M-$6M