## Slide 1: MarkeTrak Phase II Task Force
Update to RMS
February 13, 2008

## Slide 2: January 10th and 11th
Accomplishments:
  Reviewed PowerPoint presentation of Conceptual Design Document.
  Reviewed the MT PHASE II Script Matrix
  discussed at TTPT script sub-team meeting in January.
  Completed training plan matrix.
  Completed review of sections 10, 11, and 12 of the User’s Guide with Market Updates

## Slide 3: January 10th and 11th cont.
Action items from our last meeting:
  Conceptual Design PowerPoint presentation – the team asked if this was the only format the Design document was in. There was a concern of being able to track changes and post a redline version to the project site from our updates at this meeting.
  The team expressed a concern not being able to have the Conceptual Design document so that we would be able to write our internal requirements for MarkeTrak. ERCOT would follow up with this request.
  User Guide - K. Thurman, along with the assistance of D. Michelson, will look at setting up the Users Guide so that it is available as a complete guide and also as individual sections. This set up would be similar to the way the Retail Market Guide is currently setup. Will determine if a section in the complete guide is updated that it will automatically update the individual section

## Slide 4: January 24th
Accomplishments:
  Presented and discussed proposed Release buckets
  ERCOT provided Conceptual Design for Market
  Market PR_70007_01 MarkeTrak_CSD_v1 4_MKT
  Reviewed User Guide updates from ERCOT and Market Participants for Cancel with Approval and DEV LSE

## Slide 5: Execution Phases Example – ERCOT
ERCOT would like to propose the following release buckets in order to mitigate impact with Nodal Code Freeze (03-06 and 09-12 Siebel lock down) and provide early delivery of some requirements while working on delivery of more complex requirements. The actual release dates will be confirmed in early March.
MarkeTrak Phase Breakdown Criteria (see Release_Proposal.xls)
Release I (5 Weeks Development)
-MT GUI and minimal API
Release 2 (19 weeks Development)
-IAG Workflows
-DEVLSE Automation
-New Adapter/Interfaces
Release 3 (4 weeks Development)
-API (Complex changes)
-New Workflow fields
-Integration changes
Release 4 (16 weeks Development)
-New Workflows
-Integration changes
-Bulk Insert templates
-Reporting/TML
Notes: Expenses – tracked separately from services costs; Consider cost of traveling btwn ERCOT offices and trips to vendor sites.
End Date – we have an opportunity to eliminate the need for many amendments if we think through the End Date issue up front. Can accomplish definitive end need with milestone descriptions while maintaining some flexibility with End Date.
Signature – Only Directors/Officers may sign contracts, not Managers or Project Managers.

## Slide 6: “DRAFT” Execution Example Timeline
DRAFT Execution Schedule
**Dates will be confirmed in early March (contingent on Nodal)
4th Qtr
2007
06/2008
Release 1
1st Qtr 2008
2nd Qtr 2008
3rd Qtr 2008
4th Qtr 2008
1st Qtr 2009
Timeline
Planning
Release 1
Release 5
Release 2
Release 3
Release 4
07/2008:
Release 2
08/2008:
Release 3/ Release 2 Contingency
11/2008:
Release 4
02/2009
Release 5 (Contingency Date Due to Nodal and Stabilization)

## Slide 7: February 7th
Accomplishments
  Reviewed the revised Release timeline and buckets
  Based on feedback from 01/24/2008 MT Task Force meeting, ERCOT made the following updates to the Release Buckets proposed to accommodate Market concerns. The driver for these changes are to reduce Market Test and Training, yet still isolate testing at ERCOT to deliver quality.
  Release 1 Production June 14, 2008
  Release 2 Production August 16, 2008
  Release 3 Production December 6, 2008
Reviewed the Script Matrix
  This was reviewed at the script sub-team meeting on February 8th
Reviewed User’s Guide - updates from ERCOT and Market Participants for the IAG and Reject sections
  Goal to have User’s Guide updated to current functionality, approved and posted to MarkeTrak site by March month end.

## Slide 8
Updated ERCOT Timeline for delivery

## Slide 9: Planning Phase Status
Milestone | Schedule Completion Date
Requirements (ALL) | 11/21/2007 - Complete
Conceptual Design (ERCOT) | 01/16/2008 - Complete
Security Requirements (optional) (ERCOT) | 03/17/2008 - NA
Technical Architecture (optional) (ERCOT) | 01/25/2008 - NA
Detail Design (ERCOT) | 03/21/2008 – on Schedule
High-Level Test Plan (ALL) | 03/21/2008 – on Schedule
Define Execution Schedule (ALL) | 03/26/2008 – on Schedule
**Planning Complete | 03/28/2008
Notes: Services – the more details, the easier it is to monitor performance, enforce performance, terminate or sue.
Individuals - Don’t need to finalize contract unless you want to make sure a particular person performs. Addition/Substitution language in SOW provides flexibility, but still must complete BGC process.
Cost – T&M or fixed? How priced when vendor selected (e.g. RPF response)? What is approved on PRF?
Expenses – Consider cost of traveling btwn ERCOT offices and trips to vendor sites.
Signature – Only Directors/Officers may sign contracts, not Managers or Project Managers.

## Slide 10: Next Meeting
February 21st at ERCOT
Review proposed timeline (2008 MarkeTrak schedule of activities and meetings) and release buckets
Review remaining D2D and DEV sections of the Users Guide

## Slide 11: Questions