## Slide 1: PMO Update to RMS
Troy Anderson
ERCOT Program Management Office
February 13, 2008

## Slide 2: PMO Update
Agenda
  2007 Program Area Financials - Preliminary
  2008 Program Area Funding
  2009 Project Prioritization

## Slide 3: PMO Update – 2007 Results
2007 CART Results *** Preliminary – Updated 2/11/08 ***
CART | Initial 2007 Funding | Changes | Final 2007 Funding | 2007 Actuals | Variance
CO | 4,250,000 | +1,775,000 | 6,025,000 | 6,096,686 | + 71,686
IO | 5,294,500 | +4,640,000 | 9,934,500 | 8,596,104 | - 1,338,396
MO | 1,500,000 | - 400,000 | 1,100,000 | 1,008,485 | - 91,515
RO | 7,000,000 | - 4,220,000 | 2,780,000 | 3,101,062 | + 321,062
SO | 4,500,000 | - 1,795,000 | 2,705,000 | 2,720,793 | + 15,793
Nodal | 21,455,500 | 0 | 21,455,500 | 21,745,404 | + 289,904
Total | 44,000,000 | 0 | 44,000,000 | 43,268,534 | - 731,466
Legend CO = Corporate Operations MO = Market Operations SO = System Operations
IO = IT Operations RO = Retail Operations Nodal = Zonal/Nodal Allocation

## Slide 4: PMO Update – Summary of Budget Transfers Between CARTs
Total Funding Transfers = $7.1M
Summary | 
Givebacks | 
CO | $0.7M
MO | $0.4M
RO | $4.2M
SO | $1.8M
Total | $7.1M
Recipients | 
CO | $2.5M
IO | $4.6M
Total | $7.1M
Details |  | 
Givebacks |  | Amount
CO | 1 transfer to IO, 1 deferral to 2008 (Project Server upgrade) | $0.7M
MO | Release of funds from various projects due to resource and AIX server upgrade constraints | $0.4M
RO | TX SET 2.1 release of excess funds | $2.1M
RO | Release of funds from various projects due to resource and AIX server upgrade constraints | $2.1M
SO | TRE project funding returned to SRT | $1.4M
SO | Return of excess funds on 2 projects (REC 2007 and Unit Test Submittal Via Web) | $0.4M
Total |  | $7.1M
Recipients |  | 
CO | TCC2 Facility Build-Out | $1.9M
CO | Control Room Projector Upgrade (2008 acceleration) | $0.6M
IO | Blade Refresh, Storage Upgrade (2008 acceleration) | $2.7M
IO | Various infrastructure items that became necessary over the course of the year | $1.9M
Total |  | $7.1M

## Slide 5: PMO Update - 2007 Budget Transfer Benefits
Several benefits were derived from the funding transfers in 2007
  TCC2 Buildout
    Provided much-needed capacity for growing workforce
      Built out unfinished areas of TCC2 (+130 desks, 6 offices)
      Reconfigured cubicles (+216 seats)
      Specialty areas (Market Trials room, vendor rooms, conf. rooms)
      Expanded parking lot (+130 spaces)
  AIX Server Migration
    Project delivered over the course of 2007 that addressed limited data center power and cooling capacity
  2008 Project Accelerations to 2007
    Enabled ERCOT to maintain a flat fee going into 2008
    Control room projector upgrade replaced prior generation equipment used by System Operations – replacement bulbs were exceedingly expensive and there was only one manufacturer who produced them
    IO blade refresh and storage upgrade were IT infrastructure purchases planned for 2008 that could be made in 2007

## Slide 6: PMO Update – 2008 Funding
2008 CART Funding
CART | Initial 2008 Funding
CO | 8,450,000
IO | 6,400,000
MO | 1,200,000
RO | 6,100,000
SO | 50,000
Nodal | 5,300,000
Total | 27,500,000

## Slide 7: PMO Update - 2009 Project Prioritization
2009 will be a unique year for project planning due to Nodal
  Quantity and type of SO/MO projects in 2009 is not yet known
ERCOT expects to file a fee case in early 2008
  Yearly budget cycle will be earlier than the typical schedule
These factors limit our ability to produce the typical level of detail for project prioritization (Project Requests, CBAs, Time & Cost Estimates)
ERCOT has proposed a two phase approach to 2009 planning
  Phase 1 – Develop high level initiatives list in early 2008
  Phase 2 – Complete required documents in late 2008 for allocation of 2009 funds
  Important Notes:
    No project will be allowed to proceed without all required documents
    Both phases will be completed with market subcommittee involvement

## Slide 8: PMO Update - 2009 Project Prioritization
List of initiatives to include all efforts expected in 2009
  Each CART provides as much information as it can
    Actual projects
    Groupings by project type
  Total budget request determined by summing initiatives list estimates
  The CART must stay within a range of effort that they think they can deliver in 2009
CART Funding Allocation
  Funding per CART determined in late 2008
    Funding provided for “Previously Approved” projects initiated in 2008
    Funding provided for projects that have been defined (all documentation)
  Funds for efforts not yet defined to be held by SRT
    Funding will be allocated as projects become ready to initiate
Schedule of activities on the final slide

## Slide 9: PMO Update - 2009 Project Prioritization
2007 – 4th quarter
  Develop initial list of high level initiatives by CART with budget range estimates (done by ERCOT)
2008 – 1st quarter
  Internal ERCOT approval of initiatives list & budget (SRT, EC)
  Market participant approval of initiatives list & budget (subcommittees, TAC)
  F&A and Board of Directors approval of initiatives list & budget
2008 – 4th quarter
  Develop 2009 Divisional PPLs according to current standards
  Allocation of funds to CARTs for Previously Approved and known projects
2009
  Operate with the funding approach outlined on slide 6

## Slide 10: PMO Update - 2009 Project Prioritization
2009 Project Prioritization Schedule - Overview
  January
    CARTs revise 2009 Initiative Lists
  February
    Initial review at Market Subcommittee meetings
      MO - COPS (February 12)
      RO - RMS (February 13)
      SO - ROS, WMS (February 14 / February 20)
  March
    Approval by Market Subcommittees
      MO - COPS (March 11)
      RO - RMS (March 12)
      SO - ROS, WMS (March 13 / March 19)
      CO, IO, MO, RO, SO – PRS (March 20)
  April
    Approval by TAC (April 3)
    Available for F&A and Board review (April 15)

## Slide 11: PMO Update
Questions?