## Script Matrix
Complete | Script # | Release | Script Name | Requirement | Notes | Assigned to
X | 1 | 1 | Connectivity Testing - API |  |  | Kyle Miller
| 2 | 2 | Inadvertant Gain- Gaining - GUI | 25,27 |  | TXUE, CNE
| 3 | 2 | Inadvertant Gain - Losing - GUI | 25,27 |  | TXUE, CNE
| 4 | 2 | Inadvertant Gain- Gaining - API | 25,27 |  | Oncor, CNP
| 5 | 2 | Inadvertant Gain - Losing - API | 25,27 |  | Oncor, CNP
| 6 | 2 | Billing and Usage - GUI | 16,10,8,4,5 | Question for TTPT separate scripts for API? Create MT Issues through bulk insert and GUI. 4a and 4b | CNE, TXUE
| 7 | 2 | Billing and Usage -API | 16,10,8,4,5 | Question for TTPT separate scripts for API? | CNP, Oncor
| 8 | 2 | 997s/Project/Other | 11 | Test only 997 | CNP, Oncor
| 9 | 2 | Missing Transaction - GUI | 13,35,36,10 | Question for TTPT separate scripts for API? | TXUE, CNE
| 10 | 2 | Missing Transaction - API | 13,35,36,10 | Question for TTPT separate scripts for API? | CNP, Oncor
| 11 | 2 | Cancel w/Approval - GUI | 28 | 34 - @ in comments field - ERCOT Recomends removing 34 from this | TXUE, CNE
| 12 | 2 | Cancel w/Approval - API | 28,34 | 34 - @ in comments field | Oncor, CNP
| 13 | 2 | DEV - IDR - GUI | 30 |  | CNP, Oncor
| 14 | 2 | DEV - IDR - API | 30 |  | CNP, Oncor
| 15 | 2 | DEV - LSE - GUI | 31,32,35, 4,5 |  | CNP, Oncor
| 16 | 2 | DEV - LSE - API | 31,32,35, 4,5 |  | CNP, Oncor
X | 17 | 2 | Premise Type | 37, 26 | Be split amongst MPs
| 18 | 2 | Safety Net | 38 | Be split amongst MPs | Oncor, CNP
X | 19 | 3 | Service Order | 39 | Be split amongst MPs
| 20 | 3 | Move Out with Meter Removal | 40 | Be split amongst MPs | CNP, Oncor
| 21 | 3 | Reporting | 17 | Start after completion of prior scripts, Reporting scripts against production? | Oncor, CNP
| 22 | 3 | Wrong MP Inovlved Transition - API | 33 | Make sure that MP system ovewrites the data in their system - API only | CNP, Oncor
| 7 |  | Reject Reason | 12 | May not need to be tested in market test - Tested in ERCOT UAT and Sandbox

## MT01
|  | Script ID | MT PHASE II SAMPLE Script - API Connectivity |  | Power Point
|  | Script Name | API Connectivity
|  | Script Storyline | CR or TDSP complete API pull for Query List and Query Detail.
|  | Success Criteria | CR or TDSP will verify that data was received by Success Query List and Query Detail.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  | Operating Rule |  |  | TRACK | MarkeTrak API
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 0 | 1 | ERCOT | CR or TDSP | Email WSDL & XSDs: ERCOT | Email | ERCOT Emails WSDL & XSDs to CR and TDSP connectivity contacts
|  |  | 1 | CR or TDSP |  | Load new WSDL & XSDs: CR or TDSP
|  |  | 1 | CR or TDSP | ERCOT | Initiate Connectivity |  | API contact will initiate "Query List" and "Query Detail"
|  |  | 1 | CR or TDSP | ERCOT | Email status: CR or TDSP | Email | CR or TDSP will email ERCOT the status of the data received by Success Query List and Query Detail

## MTP13
|  | Script ID | MT PHASE II SAMPLE Script - Premise Type |  | Power Point
|  | Script Name | Premise Type
|  | Script Storyline | CR creates a premise type issue. CR requesting TDSP investigate premise type. CR believes premise type incorrect
|  | Success Criteria | One issue is downloaded and successfully processed and the results correctly uploaded to the MarkeTrak system. The TDSP continues processing until all issue is closed.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | Operating Rule |  |  | TRACK | MarkeTrak API
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | CR | TDSP | *Create* : CR | Submit via GUI | CR submits 1 issue into MarkeTrak via GUI. Issue Type/Sub Type = PremiseType (CR Selects Premise type from drop down box) | CR selects TDSP territory. MarkeTrak assures proper field information and checks for duplicate issue.
|  |  | 1 | TDSP | TDSP | New : TDSP | Begin Working | Marketrak system updates state to - In Progress (Assignee)
|  |  | 1 | TDSP | CR | In Progress (Assignee) :TDSP | 814_20 Sent/Complete | TDSP investigates Premise Type. MarkeTrak system updates state to Pending Complete
|  |  | 1 | CR | CR | Pending Complete: CR | Complete | MarkeTrak system updates state to Complete

## MTP15
|  | Script ID | MT PHASE II SAMPLE Script - Service Order |  | Power Point
|  | Script Name | Service Order
|  | Script Storyline | CR creates a Service Order issue. CR requesting TDSP investigate Service Order. CR requests TDSP to investigate status of Service Order transaction.
|  | Success Criteria | One issue is downloaded and successfully processed and the results correctly uploaded to the MarkeTrak system. The TDSP continues processing until all issue is closed.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | Operating Rule |  |  | TRACK | MarkeTrak API
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | CR | TDSP | *Create* : CR | Submit via GUI | CR submits 1 issue into MarkeTrak via GUI. Issue Type/Sub Type = Service Order (CR Selects Service Order from drop down box) | CR selects TDSP territory. MarkeTrak assures proper field information and checks for duplicate issue.
|  |  | 1 | TDSP | TDSP | New : TDSP | Begin Working | Marketrak system updates state to - In Progress (Assignee)
|  |  | 1 | TDSP | CR | In Progress (Assignee) :TDSP | Return to Submitter | TDSP investigates Service Order determained that TDSP needs more information. Comments are required. MarkeTrak system updates state to New: CR.
|  |  | 1 | CR | CR | New: CR | Begin Working | MarkeTrak system updates state to In Progress: CR
Day 2
|  |  | 1 | CR | TDSP | In Progress (Assignee) : CR | Return to TDSP | CR provides aditional information. Comments are required. MarkeTrak system updates state to New: TDSP.
|  |  | 1 | TDSP | TDSP | New : TDSP | Begin Working | Marketrak system updates state to - In Progress (Assignee)
|  |  | 1 | TDSP | CR | In Progress (Assignee) :TDSP | Complete | TDSP investigates Service Order. TDSP Completes issue. MarkeTrak system updates state to Pending Complete: CR.
|  |  | 1 | CR | CR | Pending Complete : CR | Complete | MarkeTrak system updates state to Complete