## Slide 1: 2009 Project Prioritization
Troy Anderson
ERCOT Program Management Office
February 20, 2008

## Slide 2: PMO Update
Agenda
  2008 Program Area Funding
  2009 Project Prioritization

## Slide 3: PMO Update – 2008 Funding
2008 CART Funding
CART | Initial 2008 Funding
CO | 8,450,000
IO | 6,400,000
MO | 1,200,000
RO | 6,100,000
SO | 50,000
Nodal | 5,300,000
Total | 27,500,000

## Slide 4: PMO Update - 2009 Project Prioritization
2009 will be a unique year for project planning due to Nodal
  Quantity and type of SO/MO projects in 2009 is not yet known
ERCOT expects to file a fee case in early 2008
  Yearly budget cycle will be earlier than the typical schedule
These factors limit our ability to produce the typical level of detail for project prioritization (Project Requests, CBAs, Time & Cost Estimates)
ERCOT has proposed a two phase approach to 2009 planning
  Phase 1 – Develop high level initiatives list in early 2008
  Phase 2 – Complete required documents in late 2008 for allocation of 2009 funds
  Important Notes:
    No project will be allowed to proceed without all required documents
    Both phases will be completed with market subcommittee involvement

## Slide 5: PMO Update - 2009 Project Prioritization
List of initiatives to include all efforts expected in 2009
  Each CART provides as much information as it can
    Actual projects
    Groupings by project type
  Total budget request determined by summing initiatives list estimates
  The CART must stay within a range of effort that they think they can deliver in 2009
CART Funding Allocation
  Funding per CART determined in late 2008
    Funding provided for “Previously Approved” projects initiated in 2008
    Funding provided for projects that have been defined (all documentation)
  Funds for efforts not yet defined to be held by SRT
    Funding will be allocated as projects become ready to initiate
Proposed schedule of activities on the final slide

## Slide 6: PMO Update - 2009 Project Prioritization
2007 – 4th quarter
  Develop first draft of high level initiatives by CART with budget range estimates (ERCOT)
2008 – 1st quarter
  Internal ERCOT approval of initiatives list & budget (SRT, EC)
  Market participant approval of initiatives list & budget (subcommittees, TAC)
  F&A and Board of Directors approval of initiatives list & budget
2008 – 4th quarter
  Develop 2009 Divisional PPLs according to current standards
  Allocation of funds to CARTs for Previously Approved and known projects
2009
  Operate with the funding approach outlined on slide 6

## Slide 7: PMO Update - 2009 Project Prioritization
2009 Project Prioritization Schedule - Overview
  January
    CARTs revise 2009 Initiative Lists
  February
    Initial review at Market Subcommittee meetings
      MO - COPS (February 12)
      RO - RMS (February 13)
      SO - ROS, WMS (February 14 / February 20)
  March
    Approval by market subcommittees
      MO - COPS (March 11)
      RO - RMS (March 12)
      SO - ROS, WMS (March 13 / March 19)
      CO, IO, MO, RO, SO – PRS (March 20)
  April
    Approval by TAC (April 3)
    Available for F&A and Board review (April 15)

## Slide 8: SO Update - 2009 Project Prioritization

## Slide 9: API for CRR system
Currently the Nodal Congestion Revenue Rights (CRR) system requires that Market Participants who are CRR Account Holders login and manually interface with the system to accomplish the following data transfers.
  Nomination submittals (upload)
  Auction bid/offer submittals (upload)
  CRR Network Model files (download)
  CRR ownership records (download)
  CRR Auction results (download)
In response to TPTF concerns over not having a CRR Application Programming Interface (API) between the CRR system and Market Participants who are CRR Account Holders , the project team drafted a Nodal project change control.
In July 2007, TPTF directed ERCOT to submit a change control request for a CRR API to be included in the Nodal Program scope. The ERCOT Board of Directors rejected the request as not critical for go-live. This functionality is now being proposed as a post-go live project.
The completion of this project will allow for system to system interactions for the uploading and downloading of data between ERCOT and Market Participants without manual intervention.

## Slide 10: API for NMMS system
Currently the Network Model Management System (NMMS) requires that Market Participants who are Network Operations Model Change Request (NOMCR) data submitters login and manually interface with the system to accomplish the following data transfers.
  NOMCR submittals (upload)
    Data submittals
    One-line submittals
    CIM XML submittal
    Various other submittals such as Rating Methodologies, SPS documents, etc
In response to MP concerns over not having a NMMS Application Programming Interface (API) between the NMMS and Market Participants who are NMMS NOMCR data submitters, the project team has proposed this new functionality project for 2009.
The completion of this project will allow for system to system interactions for the uploading and possible future downloading of data between ERCOT and Market Participants with minimal manual intervention.

## Slide 11: PMO Update
Questions?