PMO

Working Readiness Metric Inventory

v0.07

February 28, 2007

Table of Contents

Revision History	3

CO1 - Settle Market for 7 Days and provide appropriate extracts	5

E5 - Nodal SAS 70 Readiness	5

# Revision History

| Date | Author | Version Number | Description of Revision |
| --- | --- | --- | --- |
| 11/30/07 | Chris Wilkinson | 0.01 | Initial version. MP11 and MP19 for TPTF review on 12/4/07 |
| 12/05/07 | Chris Wilkinson | 0.02 | Results of 12/3/07 TPTF meeting. Moved MP11 redlined to Active inventory pending TAC approval |
| 12/05/07 | Chris Wilkinson | .03 | Copied remaining metrics from Future inventory and updated with Reliant and Luminant comments in preparation for 12/19/07 meeting |
| 12/20/07 | Chris Wilkinson | .04 | Moved metrics approved by TPTF to Active inventory for TAC approval: MP19 - Load Serving Entities Engagement and Readiness MP16 - MP EDS-4 Trials Participation MP18 - Mapping of Resources and Loads in Private Area Networks is Complete CO1 - Settle Market for 7 Days and Provide Appropriate Extracts CO2 - Verify Dispute Process of 168 Hour Test CO3 - Verify DAM Settlement Statements CO4 - Zonal/Nodal Coordinated Settlement Operations CO5 - Verify RTM Settlement Statements CO6 - Verify RTM Settlement Invoices CO7 - Verify DAM Invoices CO8 - Verify CRR Auction Invoices CO9 - Verify Financial Transfer and Processing CO10 - Verify Credit Calculations EMO12 - Network Operations Model and SE Performance EMO13 - ERCOT Operating Personnel and Facilities Readiness MO7 - ERCOT Operating Personnel and Facilities Readiness |
| 2/12/08 | Chris Wilkinson | .05 | Moved the following metrics to the Active Metric Inventory: ERCOT Internal Metrics E2 - Verify ERCOT Performance Monitoring Test Plan E4 - Transition Pricing Mechanisms E7 - Validate EDW Access and Accuracy of Postings Required by the IMM and PUCT Rules E10 - Validate EDW Commercial Systems Access Accuracy E11 - Validate EDW Compliance Data Access E14 - Verify QSE Performance Monitoring Test Plan E15 - Verify TSP Performance Monitoring Test Plan Energy Management Operations Metrics EMO3 - Verify Outage Evaluation System Functionality EMO8 - Conduct EECP Test Market Operations Metrics MO3 - Verify Supplemental Ancillary Services Market (SASM) Contingency Metrics C1 - Contingency Plan Procedures for Weekly, Daily and Hourly RUC Failure C2 - Contingency Plan Procedures for DAM Failure C3 - Contingency Plan Procedures for ICCP Data Failure C4 - Contingency Plan Procedures for SCED Failure C5 - Contingency Plan Procedures for Key Settlement and Financial Transfer Processes C6 - Develop Plan for SE Failure C7 - Contingency Plan Procedures for a Backup Facility C8 - Contingency Plan Procedures for Portal/API Failure C9 - Contingency Plan Procedures for Site Unavailability C10 - Verify Single Point of Failure Recovery EMS/MMS/NMMS/CRR/COMS IMM Metrics IMM1 - Market Monitor Systems Capability Overall Readiness Metrics R0 - Market Participants Operations Readiness R1 - Nodal Readiness Declaration R2 - Develop Texas Nodal Market Launch Plan Moved EMO4, MO1, MO2, and MO6 to the Removed metrics inventory Added Redline versions of the following for review by TPTF 2/21/08: - MP10 - Mapping of Resources to Resource Nodes and Resources to EPS Meters is Complete - CO1 - Settle Market for 7 Days and provide appropriate extracts - CO2 - Verify Dispute Process of 168 Hour Test - E5 - Nodal SAS 70 Readiness |
| 2/20/08 | Chris Wilkinson | .06 | Updates to MP10 with comments received form ERCOT. |
| 2/28/08 | Chris Wilkinson | .07 | Updated MP10 and C02 in the active metric inventory based on TPTF feedback received 2/21/08. These were moved out of the working document. Updated CO1 to remove references to the 168 hour test. |

### CO1 - Settle Market for 7 Days and provide appropriate extracts

| Reported By: ERCOT |  |  | EDS: 4 |
| --- | --- | --- | --- |
| Target Completion: EDS-4 Release 9 Complete |  |  |  |
| Metric Description: ERCOT will issue to eligible market participants test DAM settlement statements, test RTM settlement statements, test DAM settlement invoice(s), and test RTM settlement invoice(s) and provide appropriate extracts for consecutive 7 Operating Days. |  |  |  |
| Background: The intent of this metric is to prove ERCOT's ability to settle the DAM and the RTM for 7 consecutive days and determine acceptance by QSEs and CRR Account Holders. |  |  |  |
| Criteria: The Readiness Team will confirm settlement statements and invoices and confirm appropriate extracts were posted and available for download for each eligible market participant for the seven day period. Readiness will be met when QSEs accept the posting of the seven settlement statements and the weekly invoice The Readiness Team will poll the QSEs to obtain their acceptance. Posted Statements: QSE Statements for DAM (7 Initial and one resettlement) for each eligible MP = 8 QSE Statements for RTM (7 Initial and one resettlement) for each eligible MP = 8 QSE Invoices for DAM for each eligible MP = 7 QSE Invoices for RTM for each eligible MP = 1 CRR Invoices for DAM for each eligible MP = 7 CRR Invoices for RTM for each eligible MP = 1 AND Number of QSEs who accept the Test Settlement and Invoice statements > 99% |  |  |  |
| Reporting Data Sources: MIS Posted Settlement Statements and Invoices / ERCOT EDS 4 PM |  |  |  |
| References | TP: 5.4.6 (4), 6.1(g) | TNP: |  |

### E5 - Nodal SAS 70 Readiness

| Reported By: ERCOT |  |  | EDS: Not Defined |
| --- | --- | --- | --- |
| Target Completion: Go Live Activities less 45 days |  |  |  |
| Metric Description: ERCOT shall prepare for the transition from current to nodal SAS 70 requirements by identifying those control objectives which must be changed or modified so that NODAL operations are able to make a Final SAS70 Readiness Declaration. |  |  |  |
| Background: It is the intent of this metric to ensure that ERCOT is prepared for SAS 70 Audits in the Nodal Market. |  |  |  |
| Criteria: The Readiness Team will review documentation that the current to nodal transition SAS 70 control objectives have been updated for nodal operations. The ERCOT Readiness PM will faciltate an impact assessment to determine which control objectives are impacted by Nodal. Each individual department is responsible for updating the control objectives in their respective areas. The ERCOT Readiness PM will monitor progress to this end. The ERCOT Internal Audit department will provide pre-audit consulting services, reviewing the updated control objectives and providing recommendations related to ERCOT’s ability to meet these objectives. Upon review of Internal Audit’s recommendations, the Readiness PM will declare ERCOT’s final readiness status at Go-Live less 45 days. Control Objectives Updated = 100% of Control Objectives identified as requiring a Nodal update ERCOT meets SAS 70 Requirements - This metric will be measured regularly with updates published in conjunction with planned milestones. - Tentative milestones will include: - Control Objectives Impact Assessment (Q1 2008) - Control Objectives Updated (By Business Area) (Q2 2008) - Pre-Audit Assessment (By Business Area) (Q2 / Q3 2008) - Final SAS70 Readiness Declaration (Q4 2008) RAG Rules Red – Failure to meet plan Amber – Behind Training Schedule Green – Meeting Plan |  |  |  |
| Reporting Data Sources: Control Objectives Log revision history / ERCOT Readiness PM |  |  |  |
| References | TP: N/A | TNP: N/A |  |