## Revision History
Date | Version | Description
2007-01-01 | 0.1 | Initial version for the 11.05 TPTF meeting
2007-11-15 | 0.2 | Update for November publication
2007-11-26 | 0.3 | Updates from TPTF 11/26/2007 meeting
2007-11-30 | 0.4 | Added EDS 4 milestones
2007-12-11 | 0.5 | Added EDW, RTR, MIS, clean up of EIP, and updates to EDS schedules
2008-01-04 | 0.6 | Updates from TPTF 12/18/2007
2008-02-01 | 0.12 | Updates in prep for TPTF 02/04/2008
2008-02-15 | 0.13 | Updates in prep for TPTF 02/21/2008
2008-02-29 | 0.14 | Updates in prep for TPTF 03/3/2008

## Legends
Instructions
The center fold and this Excel document should be used in combination, and most of the time will be released at the same time.
The purpose of the Excel document is to add additional details, as well as comments related to each milestone activity.
Legends
Key changes since last TPTF presentation
BOLD and Green | Activity complete or Software deployed in the EDS environment
Blue | Activity in progress
Deployed | The project functionality (e.g. MMS 2) is available in the EDS environment
Completed | The EDS activity is complete
Confidence Factor | Assessment made by Delivery Assurance team based on Vendor delivery and project status. Factor will change as plans solidify/change
Low | Multiple threats to success in various areas - schedule, quality, development, resources etc
Medium | Known threats with established mitigation plans
High | Few threats to meeting milestone
Questions | deliveryAssurance@ercot.com
Raj Chudgar: o: 512-248-6580, c: 832-722-6388

## Working Schedule
Number | Project / System | Phase | Original Name | Current Centerfold short Name | Description / Functionality | Baseline Start (Published in March) | Baseline End (Published in March) | Centerfold v10/12/2007 Start | Centerfold v10/12/2007 End | Current Centerfold v11/30/2007 Start | Current Centerfold v11/30/2007 End | Centerfold v12/14/2007 Start | Centerfold v12/14/2007 End | Current Centerfold v1/4/2008 Start | Current Centerfold v1/4/2008 End | Current Centerfold v1/18/2008 Start | Current Centerfold v1/18/2008 End | Current Centerfold v2/01/2008 Start | Current Centerfold v2/01/2008 End | Current Centerfold v2/15/2008 Start | Current Centerfold v2/15/2008 End | Current Centerfold v2/29/2008 Start | Current Centerfold v2/29/2008 End | Comments | Confidence factor to Finish on time | Dependencies | Ripple Effect
EDS 1
1 | EMS | FAT | N/A | EMS 1 | • Base EMS Platform (Replication, Failover etc.,) • Base EMS Data Models • Base Alarm function • Base SCADA functions • Base State Estimator • Base Network Security Analysis (RT/ST) • Base Power Flow | N/A | N/A | N/A | 2007-02-01 | N/A | 2007-02-01 | N/A | 2007-02-01 | N/A | 2007-02-01 | N/A | 2007-02-01 | N/A | 2007-02-01 | N/A | 2007-02-01 | N/A | 2007-02-01 | > Deployed on schedule | Deployed
2 | EMS | FAT |  | EMS 2A | • OAG 2.4 Base to address dual redundant ICCP from TSP and QSE | N/A | 2007-05-14 | 2007-04-30 | 2007-05-11 | 2007-04-30 | 2007-05-11 | 2007-04-30 | 2007-05-11 | 2007-04-30 | 2007-05-11 | 2007-04-30 | 2007-05-11 | 2007-04-30 | 2007-05-11 | 2007-04-30 | 2007-05-11 | 2007-04-30 | 2007-05-11 | > Deployed on schedule | Deployed | EMS1
3 |  | EDS 1 | N/A | Point to Point Beta | • To test the testing process planned for point-to-point verification of telemetry by ERCOT operators and TSP/QSE operators. • To verify real-time values and status for selected TSP and QSE stations. • To verify that the TSP and QSE substation topology diagrams match the ERCOT one line substation diagrams. • To streamline the point to point testing process and reduce the time to complete by working closely with the operators who perform the test. • To record and analyze systematic issues and to communicate back to TSPs, QSEs and ERCOT operations. • To prepare for the point-to-point testing activity. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | > Started on time and finished on time > Completed milestone > Baseline dates defined in EDS 1 handbook | Completed | EMS2A
4 |  | EDS 1 Release 1 | Alarm Processing | Point to Point Alarm Processing | • To identify the desired alarm process configuration working with ERCOT operators • To design an approach to categorize, organize and prioritize alarms • To gain approval of the alarm configuration design by ERCOT Operations Management • Configure the approved design using the Nodal EMS (COTS) System • Verify the configuration with selected TSPs and QSEs, by having Operators randomly test selected breakers and switches and enter values that exceed selected limits to test message organization/categorization • Implement Alarm Configuration on the Nodal EMS System | 2007-04-01 | 2007-06-30 | 2007-06-01 | Sept. 30, 2007 | 2007-06-01 | 2008-05-01 | 2007-06-01 | 2008-05-01 | 2007-06-01 | 2008-05-01 | 2007-06-01 | 2008-05-01 | 2007-06-01 | 2008-05-01 | 2007-06-01 | 2008-05-01 | 2007-06-01 | 2008-05-01 | > Ongoing effort as new functionality / data is released in EMS system > Testing defects and TSP/QSE functionality > On-going effort due to testing with MPs and ERCOT anytime an EMS release is deployed. > Last EMS release scheduled for April 2008 > List of Alarms that have been completed will be provided by EDS group as requested. List will be updated as ERCOT continues to update functionality | Low | ALL EMS RELEASES | > All EMS releases and 168 hr test will be at risk if not completed
5 |  | EDS 1 Release 2 | Point-to-Point Checkout | Point-to-Point Telemetry | • Verify ICCP performance for each TSP and QSE during failover configurations • Verify ICCP and EMS failover performance at ERCOT • Verify ERCOT’s substation topology diagrams match TSP’s one line diagrams • Perform point-to-point testing by station for all TSPs and QSEs o Verify status by toggling each breaker and switch and verifying change in status and in quality code o Perform analog verification by cross-checking displayed values at ERCOT and at TSPs/QSEs for each telemetered analog point o Verify correct operation of telemetered quality codes by manually replacing selected analog points • Identify issues and request TSPs and QSEs to submit change request to correct errors • Place the SCADA database under a full change control process • Resolve all outstanding PtP testing issues down to an error rate of 3% or less for each MP. | 2007-06-01 | 2007-09-30 | 2007-06-01 | 2007-09-30 | 2007-06-01 | 2007-12-12 | 2007-06-01 | 2007-12-31 | 2007-06-01 | 2008-01-31 | 2007-06-01 | 2008-01-31 | 2007-06-01 | 2008-01-31 | 2007-06-01 | 2008-01-31 | 2007-06-01 | 2008-02-22 | >Testing complete with all MPs > ERCOT will request TPTF to approval completion of EDS 1 Release 2 | High | EMS2A | > State estimator and telemetry criteria/reporting EDS2 R3 is directly tied to the completion of this release
EDS 2
6 | EMS | FAT |  | EMS 2B | • State Estimator o State Estimator Performance Standards • SCADA o Telemetry Performance Standards o RT Weather Zone calculations o Dynamic Ratings for single model o FOD – Actual Outage Detection • NSA o SPS/RAP o Constraint Management (RT Tracking and Archival) | N/A | 2007-07-05 | 2007-08-27 | 2007-09-06 | 2007-08-27 | 2007-09-06 | 2007-08-27 | 2007-09-06 | 2007-08-27 | 2007-09-06 | 2007-08-27 | 2007-09-06 | 2007-08-27 | 2007-09-06 | 2007-08-27 | 2007-09-06 | 2007-08-27 | 2007-09-06 | > All slack in schedule consumed by project. >Vendor functionality delivery lined up to meet EDS schedule (early drop) > Deployed late with defects | Deployed | EMS 2A | > Caused integration between EMS and MMS to be delayed > Tested late, and not corrected all defects > Impacting execution of SE tuning > Impacts exit criteria for EDS 2
7 | NMMS | FAT |  | NMMS 1 | • Full CIM model • Base capability to add changes • Testing initial load from EMS • Testing NMMS to EMS functionality | N/A | 2007-06-25 | 2007-06-05 | 2007-06-25 | 2007-06-05 | 2007-06-25 | 2007-06-05 | 2007-06-25 | 2007-06-05 | 2007-06-25 | 2007-06-05 | 2007-06-25 | 2007-06-05 | 2007-06-25 | 2007-06-05 | 2007-06-25 | 2007-06-05 | 2007-06-25 | > Deployed with defects | Deployed
8 | NMMS | FAT |  | NMMS 2 | • PTC UI • PTC Schema • Interfaces for NOMCR, PMCR • Full Case Builder | N/A | 2007-09-01 | 2007-07-31 | 2007-09-01 | 2007-07-31 | 2007-09-01 | 2007-07-31 | 2007-09-01 | 2007-07-31 | 2007-09-01 | 2007-07-31 | 2007-09-01 | 2007-07-31 | 2007-09-01 | 2007-07-31 | 2007-09-01 | 2007-07-31 | 2007-09-01 | > Deployed with defects | Deployed | NMMS 1
9 | EDW | FAT |  | EDW 1A | SE Reports • Voltage Residuals vs. Telemetry for Critical Buses • MW Residuals vs. RTCA Base Case for Critical Transmission Elements • MW Residuals vs. Telemetry for Major Transmission Elements • MW Residuals vs. Telemetry for Critical Transmission Elements • State Estimator Convergence MMS Reports • Security Violations & Binding Transmission Constraints | N/A | 2007-07-15 | N/A | N/A | N/A | N/A | 2008-01-02 | 2008-01-31 | 2008-02-01 | 2008-02-29 | 2008-02-01 | 2008-02-29 | 2008-02-01 | 2008-03-14 | 2008-02-01 | 2008-03-14 | 2008-02-01 | 2008-03-14 | > If EDS site switching strategy is implemented, RSS' inability to replicate data from different versions of source systems could impact ability to generate reports for EDS 2 > Schedule delayed by a month because of delays in deployment of Replication hardware. Working with Infrastructure to mitigate delays > List of extracts and reports as well as current DRAFT DDLs are listed on the Nodal web site at http://nodal.ercot.com/readiness/reports/index.html > Extending FAT of 1A, pulling FAT end back for 1B. Combined functionality (1A+1B) is now delivered 14 days earlier | Low | EMS 3 A | > Impacts ERCOT's ability to generate SE peformance reports
10 | EDW | FAT |  | EDW 1B | Telemetry Reports • Critical Points Violating Quarterly Availability Standards • ICCP Link Availability Statistics • Monthly Market Participant Real Time Availability Statistics • QSE ICCP Link Availability • TSP ICCP Link Availability • Quarterly Point Availability Statistics State Estimator: Extract • State Estimator Statistics Extract – SESTATS_EXTRACT MMS: Extract • Monthly Energy Deployed by RMR Units Replication • Outage Scheduler Replication: OS FAT to EDW DEV • CRR Replication: CRR EDS to EDW FAT • MMS Replication: MMS FAT to EDW DEV | N/A | 2007-07-15 | N/A | N/A | N/A | N/A | 2008-02-01 | 2008-02-28 | 2008-03-01 | 2008-03-31 | 2008-03-01 | 2008-03-31 | 2008-03-01 | 2008-03-14 | 2008-03-01 | 2008-03-14 | 2008-03-07 | 2008-04-15 | > Lack of hardware for PI causing delays in testing and deploying reports > If EDS site switching strategy is implemented, RSS' inability to replicate data from different versions of source systems could impact ability to generate reports for EDS 2 > Schedule delayed by a month because of delays in deployment of Replication hardware. Working with Infrastructure to mitigate delays > Extending FAT of 1A, pulling FAT end back for 1B. Combined functionality (1A+1B) is now delivered 14 days earlier | Low | EMS 3 A | > Impacts ERCOT's ability to generate Telemetry availability reports
11 | EDW | FAT |  | EDW 1C | EMS Reports • Prevention of Temperature Rating Adjustment • Resource Capacity Factors • Changes To RUC Committed Resources • Dynamic Rating Report • Total Amount of Regulation Service • Actual Resource Output • Commercially Significant Constraints (CSC) – Daily • Zonal Operational Constraints (OC1) • AS Deployments • Tradable Generation Rights (TGR) - Daily Dimensional Maintenance Tool and Replication • ICCP Link Outage Scheduler • Critical/Significant Points Mgmt • Historical Congestion Elements • Critical Buses • Major Transmission Elements Replication • Siebel ITEST to EDW DEV • CMM Replication: CMM ITEST to EDW FAT | N/A | 2007-07-15 | N/A | N/A | N/A | N/A | 2008-03-01 | 2008-03-31 | 2008-04-01 | 2008-04-30 | 2008-04-01 | 2008-04-30 | 2008-03-01 | 2008-03-31 | 2008-03-01 | 2008-03-31 | 2008-03-01 | 2008-04-30 | > If EDS site switching strategy is implemented, RSS inability to replicate data from different versions of source systems could impact ability to generate reports for EDS 2 > Schedule at risk because of delays in deployment of Replication hardware. Working with Infrastructure to mitigate delays | Low | EMS 3 A
12 | NMMS | FAT | N/A | NMMS 2A | • Functionality for Single entry Model for use by TSPs and ERCOT • Functionality for creating models • Functionality in converting operation models to planning models | N/A | N/A | 2007-10-01 | 2007-11-01 | 2008-01-07 | 2008-01-18 | 2007-11-05 | 2008-01-01 | 2008-01-07 | 2008-01-18 | 2008-02-15 | 2008-03-01 | 2008-02-15 | 2008-03-01 | 2008-02-15 | 2008-03-01 | 2008-02-15 | 2008-03-08 | > Patch full rebuild to be deployed 2/15/2008: includes capabilities for OS; All profiles: S&B, Model, NOMCRs (all non-CIM profiles). > NMMS Sandbox opened > Software at ERCOT -- major patch to address Sev 1 defects to be deployed to FAT starting on 1/7 -- DELIVERED 12/13/2007 > Patch deployment into FAT delayed from 12/18 to 1/7 because of hardware dependencies > Signiicant Sev 1 issues preventing completion of FAT as of 1/15/2008 > working with Siemens on getting additional fixes for open defects | Low | NMMS 2 | > Directly impacts the start of EDS 2 Release 4 (11/1/2007) > Need stable model to be sent to MMS and EMS vendors for developing the CIM importers > Potential impact to Single entry model Go Live milestone (3/31/2008)
13 | NMMS | FAT |  | NMMS 3 | • PTC Updates • Time based MP editing model • Case builder to create time based model • Outages • Contingency Editor • Fully defined Model management system • Baseline 2 • SPS/RAPs • Combined cycle • Jointly Owned Units | N/A | 2008-01-01 | 2007-12-01 | 2008-01-15 | 2008-02-15 | 2008-03-15 | 2008-01-15 | 2008-03-15 | 2008-02-15 | 2008-03-15 | 2008-04-01 | 2008-04-15 | 2008-04-01 | 2008-04-15 | 2008-04-01 | 2008-04-15 | 2008-04-01 | 2008-04-15 | > Impacted by delays to NMMS 2A delivery > Estimated duration for testing reduced by 30 days because this is a smaller release > Delivery delayed due to previous delivery issues still open | Low | NMMS 2A | > Single Entry Model Go-Live milestone is dependent on achievement of this milestone
14 |  | EDS 2 Release 3 | SE Verification | State Estimator Verification | Telemetry Verification • Telemetry Performance • Develop ERCOT Operations procedures to detect and correct telemetry issues State Estimator Verification • SE Tuning • Network Topology Builder • SE Performance • Develop ERCOT Operations procedures to detect and resolve SE performance issues • Bus Load Forecast Topology Consistency Analyzer • Verify incorrect status indicators • Verify alarm notification whenever there is a topology inconsistency Forced Outage Detection • Verify alarm notification on change in status of breakers and switches • Verify alarm notification when Resources, transmission lines and transformers, and Load disconnected from the Network Operations Model changes Network Security Analysis • Verify Dynamic Ratings • Overload Alarms Processor • Contingency List • Special Protection Schemes and Remedial Action Plans • Load Rollover • Transmission Constraint Management • Develop Nodal NSA operating procedures • Develop operating procedures for determining validity of constraints using Transmission Constraint Management for input into SCED • Benchmark results against Zonal real-time operations | 2007-08-15 | 2007-11-30 | 2007-09-07 | 2007-12-31 | 2007-09-07 | 2007-12-31 | 2007-09-07 | 2008-02-29 | 2007-09-07 | 2008-03-31 | 2007-09-07 | 2008-03-31 | 2007-09-07 | 2008-03-31 | 2007-09-07 | 2008-03-31 | 2007-09-07 | 2008-03-31 | > Daily SE convergence is between 60% - 100% with 100 MW / MVAR mismatch (standard is 15 MW/MVAR) > Patch to address defects in TCA, RAS/ RAP, Critical Measurements, DRAP to be FAT tested week ending 3/14/08 > Delays in hardware for PI and lack of data for testing EDW reports will impact ability in meeting exit criteria by 3/31 | Low | EMS 2B EMS 3A EDW 1B | > State Estimator convergence is crucial for stability of LMPs.
15 |  | EDS 2 Release 3 | N/A | MIS Available |  | N/A | N/A | 2007-11-01 |  | 2007-11-01 |  | 2007-11-01 |  | 2007-11-01 |  | 2007-11-01 |  | 2007-11-01 |  | 2007-11-01 |  | 2007-11-01 |  | > MIS launched in EDS environment on Nov 01. > EDW reports not currently developed | Deployed
16 |  | EDS 2 Release 3 | N/A | MPs Receive performance reporting | • SE and Telemetry Availability reports published to Market Participants | N/A | N/A | 2007-12-31 |  | 2007-12-31 |  | 2008-02-29 |  | 2008-03-31 |  | 2008-03-31 |  | 2008-03-31 |  | 2008-03-31 |  | 2008-03-31 |  | > Dates changed to match with EDW delivery schedule > Milestone detailed in EDS 2 Handbook > Report availability called out as "MIS Available" in centerfold | Medium | EDW 1B | > Inability to post reports impacts ERCOT's ability to exit EDS 2 Release 3 > In ability to get to 168hr test
17 |  | EDS 2 Release 4 | NOMCR Checkout and Network Model verification | Network Model Verification | Network Model Management System • Verify that the Network Model Management System (NMMS) database has been successfully loaded with: o Network Operations Model database o ICCP modeling point database • Verify that the NMMS database has been placed under change control • Verify NMMS integration with Nodal EMS o Compare pre and post NMMS Telemetry and State Estimator performance o Verify Nodal one-line displays against the Zonal one-line displays Network Operations Model Change Request • Verify Network Operations Model change request process (NOMCR) o Verify submission of NOMCR changes o Verify NOM has been correctly updated o Verify that ERCOT uses an automated process to manage the CIM compliant NOMCRs upload to the ERCOT Network Operations Model o Verify that non-CIM compliant, as utilized by ERCOT, package submittals are rejected o Verify NOMCRs are applied to the NOM in the correct sequence with no adverse affect on downstream applications o Verify specific NOMCR package updates to the NOM o Verify ERCOT procedure to notify NOMCR submitter when updates have been processed and implemented o Verify that the completed NOMCR is posted in CIM format to MIS o Verify the ERCOT procedure to notify NOMCR submitter when there are deficiencies. o Verify updates to clarify NOMCR have been posted to the ERCOT MIS within 3 Business Days of the submission o Verify the ERCOT procedure to approve or reject the NOMCR within 15 Business Days of the submission o Verify the ability for TSPs to submit NOMCRs up to one year prior to the implementation of changes Single Entry Model • Verify that ERCOT has processes in place to use a “single entry point” to maintain both Nodal and Zonal network model databases when MPs submit changes via the NOMCR process • Verify results of a NOMCR submitted change to both Nodal and Zonal systems using the NOMCR process Network Model Export • TSPs and QSEs may review the exported Network Operations Model o Verify that ERCOT shall make available the full transmission model that is used to manage the reliability of the transmission system. o Verify the export is in CIM format and Web-based XML communications | 2007-09-15 | 2008-01-31 | 2007-10-31 | 2008-03-31 | 2008-01-21 | 2008-03-31 | 2008-01-15 | 2008-03-31 | 2008-01-21 | 2008-03-31 | 2008-03-31 | May 31,2008 | 2008-03-17 | May 31,2008 | 2008-03-17 | May 31,2008 | 2008-03-17 | May 31,2008 | > Completed connectivity testing with 9 of 19 MPs as of 1/2/2008 > Data sync activities could take longer than expected, which puts the end date of 3/31/2008 and the Single Entry Model Go-Live at risk > Will not start Market trials functionality testing with any Sev 1 defects (with no patch plans) > Can start Data Sync activities with TSPs once have AREVA data export > Training material for TSPs complete > Training class for all MPs in Beta test mode > Delayed start due to SEV 1 issues. > NMMS pened to TSPs in sandbox, available 01/30/2008 > Moved FAT start date earlier to reflect testing activity is starting with Encore at this date. | Low | NMMS 2A | > Can not start Model integration testing until Release starts. > Can not complete EDS 4 testing without model
EDS 3
18 | COMS | FAT |  | REG 1 | • Registration for MPs • Registration of CRR Account holders • Ability for MPs to submit forms on-line | N/A | 2007-06-01 | 2007-04-01 | 2007-06-23 | 2007-04-01 | 2007-06-23 | 2007-04-01 | 2007-06-23 | 2007-04-01 | 2007-06-23 | 2007-04-01 | 2007-06-23 | 2007-04-01 | 2007-06-23 | 2007-04-01 | 2007-06-23 | 2007-04-01 | 2007-06-23 | > Completed on schedule and deployed to production with texas Set 3.0 due to code constraints | Deployed
19 | MMS | FAT |  | MMS 1 | • SCED • All MMS components used by SCED to compute LMPs • COP • Energy Offer Curves • Inc / Dec offer Curves • Output Schedules | N/A | 2007-06-19 | 2007-05-25 | 2007-06-19 | 2007-05-25 | 2007-06-19 | 2007-05-25 | 2007-06-19 | 2007-05-25 | 2007-06-19 | 2007-05-25 | 2007-06-19 | 2007-05-25 | 2007-06-19 | 2007-05-25 | 2007-06-19 | 2007-05-25 | 2007-06-19 | > Deployed on schedule at accelerated pace | Deployed
20 | EIP | FAT |  | EIP 2 | • SCED Input Interfaces - TPO, COP, Output Schedules and Inc/Dec Offer curves | N/A | 2007-07-31 | Sept 15 2007 | 2007-10-15 | Sept 15 2007 | 2007-10-15 | Sept 15 2007 | 2007-10-15 | Sept 15 2007 | 2007-10-15 | Sept 15 2007 | 2007-10-15 | Sept 15 2007 | 2007-10-15 | Sept 15 2007 | 2007-10-15 | Sept 15 2007 | 2007-10-15 | > Deployed later than scheduled > Delayed due to MMS1 build deployed late to integration environments > Will update the centerfold with a closed triangle on finish going forward | Deployed |  | > No impact to overall schedule
21 | COMS | FAT |  | S&B 1 | • CMM base product • Template for Statements and Invoices | N/A | 2007-09-03 | 2007-06-01 | 2007-09-03 | 2007-06-01 | 2007-09-03 | 2007-06-01 | 2007-09-03 | 2007-06-01 | 2007-09-03 | 2007-06-01 | 2007-09-03 | 2007-06-01 | 2007-09-03 | 2007-06-01 | 2007-09-03 | 2007-06-01 | 2007-09-03 | > Completed on schedule, with defects > Met with COPs in August to finalize statements | Deployed |  | > Statements published to COPs
22 | EMS | FAT |  | EMS 2C | • NSA o Calculation of Shift Factors o MVA to MW conversion for constraints o Constraint Direction • Generation Sub-system o Resource Limit Calculator o SCED Interfaces | N/A | 2007-09-06 | 2007-08-27 | 2007-09-06 | 2007-08-27 | 2007-09-06 | 2007-08-27 | 2007-09-06 | 2007-08-27 | 2007-09-06 | 2007-08-27 | 2007-09-06 | 2007-08-27 | 2007-09-06 | 2007-08-27 | 2007-09-06 | 2007-08-27 | 2007-09-06 | > Deployed with defects | Deployed | EMS 2B | > Needed for beginning Release 5.3 - Integrated SCED execution
23 | MIS | FAT |  | MIS 1 | • Link to EDW (MIR) • Link to public data (ERCOT.com) • Click thru screens • Links to applications as available | N/A | 2007-09-30 | 2007-09-01 | 2007-09-30 | 2007-09-01 | 2007-09-30 | 2007-09-01 | 2007-09-30 | 2007-09-01 | 2007-09-30 | 2007-09-01 | 2007-09-30 | 2007-09-01 | 2007-09-30 | 2007-09-01 | 2007-09-30 | 2007-09-01 | 2007-09-30 | > Completed on time with defects > Future MIS releases being planned to incorporate EDW and Real Time Reports postings. Revised plan will not be available before 12/3/2007 | Deployed |  | > MIS 1 delivery enables posting of LMPs on to the website
24 | EIP | FAT |  | EIP 3 | • EMS to MMS for LMP testing | N/A | 2007-09-30 | 2007-10-01 | 2007-10-26 | 2007-10-01 | 2008-10-26 | 2007-10-01 | 2008-01-31 | 2007-10-01 | 2007-10-31 | 2007-10-01 | 2007-10-31 | 2007-10-01 | 2007-10-31 | 2007-10-01 | 2007-10-31 | 2007-10-01 | 2007-10-31 | > EMS - MMS interface deployed > Market queries moved to EIP 7 scope | Deployed
25 | EMS | FAT | EMS 3 | EMS 3A | Final Build of • State Estimator • RT NSA • TCM | N/A | 2007-11-05 | 2007-11-05 | 2007-11-16 | 2007-11-05 | 2007-11-30 | 2007-11-05 | 2007-11-30 | 2007-11-05 | 2007-11-30 | 2007-11-05 | 2007-11-30 | 2007-11-05 | 2007-11-30 | 2007-11-05 | 2007-11-30 | 2007-11-05 | 2007-11-30 | > Deployed with defects into EDS > Critical defects still open in RAS, TCA, Critical Measurements, DRAP, RLC. Patch expected from AREVA week of 1/11/2008, currently in FAT regresssion testing | Deployed | EMS 2C | > EMS release is needed for complete EDS 2 Release 3 - SE tuning and verification
26 | EMS | FAT | EMS 3 | EMS 3B | • Initial build of LFC • Real Time Reporting | N/A | 2007-11-05 | 2007-11-30 | 2007-12-07 | 2007-11-30 | 2007-12-07 | 2007-12-13 | 2007-12-21 | 2007-12-13 | 2007-12-21 | 2007-12-13 | 2007-12-21 | 2007-12-13 | 2007-12-21 | 2007-12-13 | 2007-12-21 | 2007-12-13 | 2007-12-21 | > Migration to EDS delayed due to hardware dependencies. Have started migration of Habitat 5.7 to new EDS EMS hardware > Added Habitat upgrade 5.7 to enable some EMS functionality -- new to release > Deployed to EDS | Deployed | EMS 3A | > EMS 3B delivery is needed for starting EDS 3 Release 6.1
27 | EMS | FAT | EMS 3 | EMS 3C | • LFC - Responsive Reserve • LFC - Controllable load resources • LFC - Non Spin • AS Capacity Monitoring • RLC - Patch • Resource Qualification Testing • Multiple Frequency Source | N/A | 39391 | 39486 | 39493 | 39486 | 39493 | 39486 | 39493 | 39486 | 39493 | 39503 | 39514 | 2008-02-22 | 2008-04-02 | 2008-02-22 | 2008-04-02 | 2008-02-27 | 2008-04-02 | > Responsive reserve and Controllable load resources - deployment targeted for 3/7/2008 (EMS 3C1) > AS Capacity Monitoring, Non Spin and a RLC patch - deployment targeted for 3/7/2008 (EMS 3C2) > Resource Qualification testing and Multiple Frequency sources - deployment targeted for 4/2/2008 (EMS 3C3) > Working to expedite delivery of RQT monitoring | Medium | EMS 3B | > Cannot complete LFC testing without this build
28 | CDR | FAT |  | CDR 1A | • Seven-Day Forecasts (ERCOT System, Weather Zone, and Load Zone Forecasts for next 7 days, by hour) • Short-Term System Adequacy Report | N/A | 39391 | N/A | N/A | N/A | N/A | 39493 | 39504 | 39493 | 39504 | 39493 | 39504 | 2008-02-15 | 2008-02-26 | 2008-02-15 | 2008-02-26 | 2008-02-22 | 2008-03-07 | > Original RTR, now CDR for "Current day reports" is a new Project under the MIS umbrella charged with developing all Current Day Reports (hourly reports, 5 min reports etc.) > Expediting delivery of reports to meet EDS timelines | Medium |  | > Cannot finish 168hr test without release
29 | CRR | FAT |  | CRR 1 | • Ability to upload Input data or enter them manually via CRR UI • All CRR components necessary to run CRR Markets • CRR Database Subsystem • CRR Calculation Engine • CRR Data Interface Subsystem • CRR Market Operator and Market Participant UI • Ability to run CRR Allocations, Auctions, Bilateral Trades and export results | N/A | 39417 | 39351 | 39468 | 39351 | 39468 | 39351 | 39468 | 39351 | 39468 | 39351 | 39492 | 2007-09-26 | 2008-02-28 | 2007-09-26 | 2008-02-28 | 2007-09-26 | 2008-03-11 | > 4 of 5 testing script groupings will be successfully executed by 2/29 > The las testing script group will be executed while testing CRR 1A and 1B | Low |  | > Needed for EDS 3 Release 7.5, conducting CRR testing with Market Participants
30 | CRR | FAT |  | CRR 1A | • Staging/control tables needed for integration with CMM and S&B CRR->CMM CMM->CRR CRR -> S&B S&B -> CRR • Ability to update entitlement data | [8 empty] | N/A | N/A | 39493 | 39521 | 2008-03-03 | 2008-04-01 | 2008-03-03 | 2008-04-01 | 2008-03-12 | 2008-05-02 | > This drop includes functionality that was not in the original SOW - enhancements needed for Go-Live. > Schedule impacted by delay in CRR 1 (see above) | Low |  | > Needed for EDS Release 7.5
31 | CRR | FAT |  | CRR 1B | • Staging/control tables needed for integration with rest of the systems REG -> CRR NMMS->CRR CRR-MMS • Ability to submit multiple sell offers | [8 empty] | N/A | N/A | 39521 | 39538 | 2008-03-31 | 2008-04-29 | 2008-03-31 | 2008-04-29 | 2008-04-17 | 2008-06-05 | > This drop includes functionality that was not in the original SOW - enhancements needed for Go-Live. > Schedule impacted by delay in CRR 1 (see above) | Low |  | > Needed for EDS Release 7.5
32 | EIP | FAT |  | EIP 4 | • Registration to CRR • CMM to CRR • CRR to CMM • Registration to CMM | N/A | 39083 | 39447 | 39476 | 39447 | 39476 | 39493 | 39522 | 39493 | 39522 | 39493 | 39522 | 3/3/2008 | 3/31/08 | 3/3/2008 | 3/31/08 | 3/3/2008 | 3/31/08 | > Manual workaround capable for EDS testing until integration is complete > Testing of interfaces pushed out due to delayed delivery of interface tables from vendors > EIP 4 updated due to late delivery of CRR staging tables > Currently assessing impact of delays in CRR delivery | Low |  | > Must complete for automated end to end before CRR Go Live
33 | INF | FAT | N/A | MPIM 1 | Market Participant Identity Management • User Interface to create MPIM representation of new Market Participant entities • User Interface to create/modify/terminate MPIM user accounts • User Interface to assign MPIM roles to existing MPIM users. • Auto-Provision to the Enterprise/MIS/Siteminder/Zonal LDAP | N/A | N/A | N/A | N/A | 39401 | 39423 | 39401 | 39423 | 39401 | 39423 | 39401 | 39423 | 2007-11-15 | 2007-12-07 | 2007-11-15 | 2007-12-07 | 2007-11-15 | 2007-12-07 | > Deployed to Sandbox on Dec 06, 2007. | Deployed
34 | INF | FAT | N/A | MPIM 2 | Integrated Market Participant Identity Management • Integration with VeriSign Automation Project • Auto-provisioning NMMS (IMM) Active Directory • Seeding from Zonal Portal • Incorporate top priority enhancements from MP feedback received by 12/31/07 | N/A | N/A | N/A | N/A | N/A | N/A | 39475 | 39510 | 39475 | 39510 | 39475 | 39510 | 2008-01-28 | 2008-03-10 | 2008-01-28 | 2008-03-10 | 2008-01-28 | 2008-03-10 | > MPIM integrated with Nodal applications > Will not be able to integrate into Siebel until after December 2008 > 1 week delay in order to release with Siebel/Retail release in March to production | Medium |  | > Impacts integrated capability to issue Digital Certs
35 |  | EDS 3 Release 5.1 | Upload Offers | SCED connectivity and validation rules checkout | • Provide a SCED environment for Market Participant EDS Activities • Verify QSEs ability to submit 3 Part Offers , COP, and Output Schedules • Verify QSEs understanding of SCED input validation rules • Utilize both the User Interface and Web Services interfaces for SCED inputs | N/A | 2007-10-01 | 2007-08-24 | 2007-10-04 | 2007-08-24 | 2007-10-04 | 2007-08-24 | 2007-10-04 | 2007-08-24 | 2007-10-04 | 2007-08-24 | 2007-10-04 | 2007-08-24 | 2007-10-04 | 2007-08-24 | 2007-10-04 | 2007-08-24 | 2007-10-04 | > Completed on Schedule > Shown in March Timeline as "Upload Offers" | Completed | MMS 1, MIS 1, EIP 4, EIP 3
36 |  | EDS 3 Release 5.2 | Registration | Nodal Registration Data | • Review Resource Asset Registration data and upload into EDS • Provide feedback to Market Participants on RARF issues, naming standards, Nodal changes for upload into test systems. • Establish initial test data for specific Network Model components • Provide EDS base data back to Market Participants for upload into systems for EDS testing • Setup predefined Offer Curves for testing • Ensure QSEs can submit submission items for all resources on a daily basis • Correct any registration and curve data to finalize a baseline set of input data • Begin SCED execution with a full set of MP input data | N/A | N/A | 2007-10-17 | 2007-10-31 | 2007-10-17 | 2007-10-31 | 2007-10-17 | 2007-10-31 | 2007-10-17 | 2007-10-31 | 2007-10-17 | 2007-10-31 | 2007-10-17 | 2007-10-31 | 2007-10-17 | 2007-10-31 | 2007-10-17 | 2007-10-31 | > Sufficent number of MPs have completed, ~5% outstanding as of 11/1/2007 > Data required for MMS, NMMS, and connectivity of systems > Shown in March Timeline as "Registration" | Completed | REG 1 | > Must be completed to complete model deployment (NMMS Go Live) > Must be complete before EDS 4 testing is complete
37 |  | EDS 3 Release 5.3 | SCED testing | Integrated SCED Execution Real Time ICCP | • Use RT Telemetry data • Use SCED Market Participant Offer Methodology (align with RT operations) • Verify SCED inputs from real-time operations • Verify QSE ability to receive correct Resource Base Points and LMPs via ICCP • Review SCED produced Base Points, LMPs and SPPs for reasonability (including the LMPs for Hubs and Load Zones) • For QSEs under test, allow Offers through API or UI (according to methodology - TBD) • Execute SCED and distribute test output to the QSEs participating in EDS • Review SCED output data | N/A | N/A | 2007-11-01 | 2008-01-11 | 2007-11-01 | 2008-01-31 | 2007-11-01 | 2008-01-11 | 2007-11-01 | 2008-01-31 | 2007-11-01 | 2008-02-15 | 2007-11-01 | 2008-02-15 | 2007-11-01 | 2008-02-15 | 2007-11-01 | 2008-02-15 | >EDS team working to resolve issues in sending LMPs and Basepoints over ICCP > Upgrading to production grade hardware to ensure stability of SE and RTCA > Number of Issues with ICCP data from Market Participants > Software issues with RLC being worked on currently > Achieving the milestones is contingent on fixing the above mentioned hardware, software and data issues > Note initial LMP deployment is without NMMS integration (not planned until later this year) | Low | MMS 1, MIS 1, EIP 4, EIP 3, EDS 3 Release 5.1 | > Can not start 6 month LMP posting without this release completing
38 |  | EDS 3 Release 5.4 | 6 month LMP Posting | 6 Month LMP Posting | • LMP reasonability attainment verified • Publish LMPs and other data available as required in the Nodal Protocols • Begin six months of SCED execution and LMP posting | N/A | 2008-07-15 | 2008-01-14 | 2008-07-15 | 2008-02-01 | 2008-08-01 | 2008-01-14 | 2008-07-15 | 2008-02-01 | 2008-08-01 | 2008-02-15 | Aug. 15, 2008 | 2008-02-15 | Aug. 15, 2008 | 2008-02-15 | Aug. 15, 2008 | 2008-02-15 | Aug. 15, 2008 | > 6 month LMP clock started on 2/15/2008 | Low | EDW 3 Release 5.3 | > Can not move to 168hr test without completing LMP reasonability
39 |  | EDS 3 Release 6.1 | LFC Comms and Testing | ACE calculation and preconditions | • QSE has completed AS Attestation documentation • Compare continuously for 7 days Nodal ACE results with Zonal ACE results for accuracy • Validate completion of all communication system testing • Verify calculations of HASL, LASL, SURAMP, SDRAMP, HDL, LDL • Verify ability to calculate and issue Emergency Base Points to QSEs | 2008-01-01 | 2008-03-31 | 2008-01-07 | 2008-03-31 | 2008-01-07 | 2008-02-28 | 2008-01-07 | 2008-02-28 | 2008-01-07 | 2008-02-28 | 2008-01-17 | 2008-02-28 | 2008-01-17 | 2008-02-28 | 2008-01-17 | 2008-02-28 | 2008-01-17 | 2008-02-28 | > Shown in March Timeline as "LFC Comms and Testing" > Start testing with MPs on 1/17/2008 | Medium | EMS 3A | > Can not start Relesae 6.2 without completing this release
40 |  | EDS Release 6.2A | LFC Testing | n/a | • Shakeout period for early adopters to start LFC shakeout before formal testing is started. This will be staggered for QSEs as the Phase 6.2 starts. | n/a | n/a | n/a | n/a | 2008-02-25 | 2008-03-01 | 2008-02-25 | 2008-03-01 | 2008-02-25 | 2008-03-01 | 2008-02-25 | 2008-03-01 | 2008-02-25 | 2008-03-01 | 2008-02-25 | 2008-03-01 | 2008-02-25 | 2008-03-01 | > Not shown in centerfold > Early adopters will start shake out testing with ERCOT before testing begins (similar to Point to Point checkout concept) | Low | EMS 3B, EDS Release 6.1
41 |  | EDS 3 Release 6.2 | LFC Testing | LFC testing - individual QSE | • Verify for each QSE and Resource attesting to provide Reg Up and Reg Down in Nodal, the ability to provide individual response and Regulation Control on Nodal Systems. | 2008-04-01 | 2008-06-30 | 2008-04-01 | 2008-05-25 | 2008-03-01 | 2008-05-25 | 2008-03-01 | 2008-05-25 | 2008-03-01 | 2008-05-25 | 2008-03-01 | 2008-05-25 | 2008-03-01 | 2008-05-25 | 2008-03-01 | 2008-05-25 | 2008-03-01 | 2008-05-25 | > Shown in March Timeline as "LFC Testing" > Confidence Factor based on EMS delivery > All QSEs should be be able to test LFC by April 11th 2007 > Accelerate QRT monitor | Low | EMS 3B, EDS 3 Release 6.1 | > Can not start Relase 6.3 without exiting this release
42 |  | EDS 3 Release 6.3 | N/A | LFC testing ERCOT system | Verify for all QSE and Resource can maintain and control total system frequency on Nodal System. • 2 Hr Test • 8 Hr Test • 48 Hr Test | N/A | 2008-06-30 | 2008-06-02 | 2008-06-30 | 2008-06-01 | 2008-06-30 | 2008-06-01 | 2008-06-30 | 2008-06-01 | 2008-06-30 | 2008-06-01 | 2008-06-30 | 2008-06-01 | 2008-06-30 | 2008-06-01 | 2008-06-30 | 2008-06-01 | 2008-06-30 | > New milestone detailed in LFC handbook | Low | EMS 3C, EDS 3 Release 6.2 | > Can not finish EDS 4
43 |  | EDS 3 Release 7.0 | N/A | Registration, Allocation pre-work, Training | • Registration of MPs as CRR Account Holders • Assign MP CRR Digital Certificate rights • NOIE contract receipt and entitlement creation in the system • NOIE load zone identification | N/A | N/A | 2007-12-01 | 2008-02-02 | 2007-12-01 | 2008-02-02 | 2007-12-01 | 2008-02-02 | 2007-12-01 | 2008-02-02 | 2007-12-01 | 2008-02-02 | 2007-12-01 | 2008-02-01 | 2007-12-01 | 2008-02-01 | 2007-12-01 | 2008-02-01 | > Paperwork, no system demands. Data configuration > Split into multiple phases of testing as detailed in the CRR handbook | Completed |  | > Required for EDS 3 Release 7.1 start
44 |  | EDS 3 Release 7.1 | CRR data validation | UI connectivity, data upload/download | • Validate MP CRR Digital Certificate rights • Validate AH system connection – uploads and downloads | 2008-01-02 | 2008-07-15 | 2008-02-02 | 2008-02-18 | 2008-02-02 | 2008-02-18 | 2008-02-02 | 2008-02-18 | 2008-02-02 | 2008-02-18 | 2008-02-02 | 2008-02-18 | 2008-02-04 | 2008-02-18 | 2008-02-04 | 2008-02-14 | 2008-02-04 | 2008-02-14 | > Split into multiple phases of testing as detailed in the CRR handbook Note: 90% of Market Participants completed connectivity testing. | Completed | None | > All future EDS 3 R7 releases dependent on completion of this release
45 |  | EDS 3 Release 7.2 | N/A | Mock monthly allocation and auction (ERCOT-provided data) | • Conduct mock CRR monthly auction – ERCOT directed bids • Conduct mock CRR monthly allocation – AH created nominations • Verify market result download • Verify bilateral trade functionality | 2008-01-02 | 2008-07-15 | 2008-02-18 | 2008-03-14 | 2008-02-18 | 2008-03-14 | 2008-02-18 | 2008-03-14 | 2008-02-18 | 2008-03-14 | 2008-02-18 | 2008-03-07 | 2008-02-18 | 2008-03-07 | 2008-02-18 | 2008-03-07 | 2008-02-18 | 2008-03-07 | > Split into multiple phases of testing as detailed in the CRR handbook | High | EDS 3, Release 7.1 | > All future EDS 3 R7 releases dependent on completion of this release
46 |  | EDS 3 Release 7.3 | Trial operations of CRR | Mock monthly auction (MP-created data) | • Conduct mock CRR monthly auction – AH determined bids • Conduct secondary trading – AH directed • Verify Credit constraint in optimization | 2008-04-15 | 2008-07-15 | 2008-03-14 | 2008-04-20 | 2008-03-14 | 2008-04-20 | 2008-03-14 | 2008-04-20 | 2008-03-14 | 2008-04-20 | 2008-03-10 | 2008-03-28 | 2008-03-10 | 2008-03-28 | 2008-03-10 | 2008-03-28 | 2008-03-10 | 2008-03-28 | > Split into multiple phases of testing as detailed in the CRR handbook | Medium | EDS 3, Release 7.2 | > All future EDS 3 R7 releases dependent on completion of this release
47 |  | EDS 3 Release 7.4 | N/A | Mock Annual allocation and auction (MP-created data) | • Conduct mock CRR annual auction – AH determined bids • Conduct mock CRR annual allocation – AH created nominations | 2008-04-15 | 2008-07-15 | 2008-04-20 | 2008-05-19 | 2008-04-20 | 2008-05-19 | 2008-04-20 | 2008-05-19 | 2008-04-20 | 2008-05-19 | 2008-03-31 | 2008-05-02 | 2008-03-31 | 2008-05-02 | 2008-03-31 | 2008-05-02 | 2008-03-31 | 2008-05-02 | > Split into multiple phases of testing as detailed in the CRR handbook | Medium | EDS 3, Release 7.2 | > All future EDS 3 R7 releases dependent on completion of this release
48 |  | EDS 3 Release 7.5 |  | Integration testing | • Optional phase to be confirmed. | N/A | N/A | TBD | 2008-07-10 | TBD | 2008-07-10 | TBD | 2008-07-10 | TBD | 2008-07-10 | 5/5/2008 (TBD) | 5/23/2008 (TBD) | 5/5/2008 (TBD) | 5/23/2008 (TBD) | 5/5/2008 (TBD) | 5/23/2008 (TBD) | 5/5/2008 (TBD) | 5/23/2008 (TBD) | > At high risk of starting 7.5 ontime, due to delays in vendor delivery > Split into multiple phases of testing as detailed in the CRR handbook > TBD due to dependencies as mentioned | Low | CRR1A, CRR 1B CRR 1C, EIP 4 (Reg-CRR, CRR-CMM, CMM-CRR only), EIP 6 (CRR-S&B, S&B-CRR only), Release 7.4 | > All future EDS 3 R7 releases dependent on completion of this release
EDS 4
49 | COMS | FAT |  | S&B 2 | • Settlements & Billing, Statements & Invoices - Core Calculations | N/A | 2007-12-15 | 2007-11-01 | 2007-12-15 | 2007-11-01 | 2007-12-15 | 2007-11-01 | 2007-12-31 | 2007-11-01 | 2008-01-15 | 2007-11-01 | 2008-01-15 | 2007-11-01 | 2008-01-15 | 2007-11-01 | 2008-01-15 | 2007-11-01 | 2008-01-15 | > Settlements and Billing core calculations will be covered in this release. All error handling and bug fixes will be released as part of S&B 3 > Completed testing round and waiting on HW to deploy | Ready to Deploy |  | > Must have for settlements and billing as well as CMM > can not perform EDS 4 R8 without all pieces
50 | COMS | FAT |  |  | • CMM Core Calculations | [8 empty] | 2007-11-01 | 2008-01-15 | 2007-11-01 | 2008-01-15 | 2007-11-01 | 2008-01-15 | 2007-11-01 | 2008-01-15 | 2007-11-01 | 2008-01-15 | > CMM testing in progress, expected to complete testing by end of December. Finished FAT n early Jan | Deployed
51 | MMS | FAT |  | MMS 2 | • External Interfaces • Background Process; Data Templates and Validation Rules; MOI; and MPI • DAM; DEF; HRUC; DRUC; POD; SCED Additional; and SFT • NPRR 012, 016, 033, 064, 069 • WPIDA 009 • Partial CR 010, 057 • Partial NPRR 005, 006, 035, 065, 079, • Partial WPIDA 003, 007, 015, 021, 041 • Additional Settlements Interface Tables (DAM/RUC/SCED output populated) | 2007-09-25 | 2007-10-31 | 2007-12-03 | 2008-01-11 | 2007-12-03 | 2008-01-11 | 2007-12-03 | 2008-01-11 | 2007-12-03 | 2008-01-11 | 2007-12-03 | 2008-01-25 | 2007-12-03 | 2008-01-25 | 2007-12-03 | 2008-01-25 | 2007-12-03 | 2008-01-25 | > Completed regression testing for SCED and testing of DAM / RUC validation rules > FAT end extended to include correction of defects and new round of regression test. | Deployed |  | > Enables us to begin EDS 4 to validate MP submission items
52 | MIS | FAT |  | MMS UI | New MMS UI for market submission items and queries • CRR Offer • PTP Obligation • Three-Part Supply Offers for Energy (all three parts) • Capacity Trade • Energy Trade • AS Trade • DAM Energy-Only Offer • DAM Energy Bid • AS Self Arrangement • AS Offer • Self Schedule • DC Tie Schedule • Current Operating Plan (COP) • Three-Part Offer (TPO) • Output Schedule • Inc/Dec Offer | [6 empty] | N/A | N/A | 2007-12-27 | 2008-01-15 | 2007-12-27 | 2008-01-18 | 2007-12-27 | 2008-01-18 | 2007-12-27 | 2008-01-18 | 2007-12-27 | 2008-01-18 | > Finishing FAT, deploying to to EDS and integration environment at the same time > Will correct performance issues as patches are defects are corrected | Deployed |  | > Replaces existing MMS UI with the new UI shown during UI subgroup meetings > QSE testing UI functionality only will be delayed until the new UI is deployed
53 | EIP | FAT |  | EIP 5 | External Web Services to support EDS 4 • Three Part Supply Offers (to include Start-Up and Min Energy costs) • DAM Energy Only Offers • A/S Offers • CRR Offers • DAM Energy Bid • PTP Obligation Bid • Capacity trade • Energy Trade • AS Trade • AS Self-Arrangement • DC-Tie Schedules | N/A | N/A | N/A | N/A | N/A | N/A | 2008-12-27 | 2008-01-11 | 2008-01-02 | 2008-01-11 | 2008-01-02 | 2008-01-11 | 2008-01-02 | 2008-01-11 | 2008-01-02 | 2008-01-11 | 2008-01-02 | 2008-01-11 | > Deployed to EDS | Deployed |  | > Enables us to begin EDS 4 to validate MP submission items
54 | MIS | FAT |  | MIS 2a | • Landing Pages for Real Time and Day Ahead • Graphics Updates • CRR Reporting Portlets • CRR Application Launch • NMMS Model on Demand Application Link | N/A | N/A | N/A | N/A | N/A | N/A | 2008-01-11 | 2008-01-25 | 2008-01-11 | 2008-01-25 | 2008-01-11 | 2008-01-25 | 2008-01-11 | 2008-01-25 | 2008-01-11 | 2008-01-25 | 2008-01-11 | 2008-01-25 | > Deployed to EDS to enable launching of MMS UI and CRR | Deployed | MMS CRR | > Enables us to start EDS 4 Release 9 and EDS 3 Release 7
55 | MIS | FAT |  | MIS 2b | • Rest of the MIS Landing Pages • Wind Generation Portlets • LMP Contour Map | N/A | N/A | N/A | N/A | N/A | N/A | 2008-01-11 | 2008-01-25 | 2008-01-11 | 2008-01-25 | N/A | N/A | 2008-02-06 | 2008-02-13 | 2008-02-06 | 2008-02-13 | 2008-02-06 | 2008-02-13 | > New delivery to support launch of LMP contour map and Wind generation portlets | Deployed
56 | MIS | FAT |  | MIS 3a | • Landing Pages – Grid: Long-Term Planning, Generation; Market: Settlements, Data Aggregation, Metering, Load Profiling, Retail; • LMP Contour Map (Dashboard) – content will dynamically updated | N/A | N/A | N/A | N/A | N/A | N/A | 2008-02-11 | 2008-02-22 | 2008-02-11 | 2008-02-22 | 2008-02-11 | 2008-02-22 | 2008-02-11 | 2008-02-22 | 2008-03-17 | 2008-02-22 | 2008-03-17 | 2008-03-21 | > Delays caused by lack of hardware | Medium
57 | MIS | FAT |  | MIS 3b | Support for Current Day Reports Release 1A | [12 empty] | N/A | N/A | 2008-03-24 | 2008-03-07 | 2008-03-24 | 2008-04-04 |  | Medium
58 | MIS | FAT |  | MIS 4 | Portlets enabling launch of DAM / RUC Reports, Settlement Statements templates and other functionality needed for EDS 4 | N/A | N/A | N/A | N/A | N/A | N/A | 2008-03-11 | 2008-03-24 | 2008-03-11 | 2008-03-24 | 2008-03-11 | 2008-03-24 | 2008-03-11 | 2008-03-24 | 2008-03-24 | 2008-03-24 | 2008-03-24 | 2008-04-04 |  | Medium | RTR 1B | > Needed for displaying DAM/RUC Reports
59 | MIS | FAT |  | MIS 5 | MIS release to support Settlements statements, DAM / RUC reports | N/A | N/A | N/A | N/A | N/A | N/A | 2008-04-14 | 2008-04-24 | 2008-04-14 | 2008-04-24 | 2008-04-14 | 2008-04-24 | 2008-04-14 | 2008-04-24 | 2008-04-14 | 2008-04-24 | 2008-04-14 | 2008-04-24 |  | Medium | RTR 2 | > Needed for displaying settlements statements
60 | MIS | FAT |  | MIS 6 | Support for Disputes | N/A | N/A | N/A | N/A | N/A | N/A | 2008-05-09 | 2008-05-21 | 2008-05-09 | 2008-05-21 | 2008-05-09 | 2008-05-21 | 2008-05-09 | 2008-05-21 | 2008-05-09 | 2008-05-21 | 2008-05-09 | 2008-05-21 |  | Medium | S&B 4 | > Needed for EDS 4 Release 8.5
61 | MIS | FAT |  | MIS 7 | Final Build of MIS - includes patches / bug fixes for all previous MIS releases | N/A | N/A | N/A | N/A | N/A | N/A | 2008-06-13 | 2008-06-27 | 2008-06-13 | 2008-06-27 | 2008-06-13 | 2008-06-27 | 2008-06-13 | 2008-06-27 | 2008-06-13 | 2008-06-27 | 2008-06-13 | 2008-06-27 |  | Medium |  | > Needed to start 168 hour test
62 | MMS | FAT |  | OS | • Nodal Outage Scheduler Full functionality | N/A | 2007-12-14 | 2008-01-21 | 2008-02-01 | 2008-01-21 | 2008-02-01 | 2008-01-21 | 2008-02-01 | 2008-01-21 | 2008-02-01 | 2008-02-11 | 2008-03-07 | 2008-02-11 | 2008-03-07 | 2008-02-21 | 2008-03-20 | 2008-02-21 | 2008-03-20 | > Outage Scheduler working model installed at ERCOT week ending 1/4/2008. > Pre-FAT at vendor site started on 1/7/2008 > longer than expected in PRE-FAT due to additional testing required and defects > Private WAN access to be established | Low |  | > Can not complete EDS 4 R9 testing without OS > Can not complete NMMS R3 and NMMs Go Live without functionality
63 | MIS | FAT |  | OS RUI | New OS RUI for Outage Scheduler | [12 empty] | 2008-03-07 | 2008-03-14 | 2008-03-07 | 2008-03-14 | 2008-03-25 | 2008-03-31 | > Delivery of Outage Scheduler UI being re-planned to align with EDS priorities | Low | OS | Required for EDS4 release 9.2
64 | CDR | FAT |  | CDR 1B | • Daily Electrical Bus Load Distribution Factors • Day Ahead Market Ancillary Service Offers • Day Ahead Market Hourly LMPs • Day Ahead MCPC • Aggregated Ancillary Service Offer Curve • Day Ahead Market Settlement Point Prices • Day Ahead Market Shadow Prices • Day Ahead Market Total Energy Bought • Day Ahead Market Total Energy Sold • Ancillary Service Plan • Ancillary Service Schedule Obligations • Weather to Forecast ERCOT System Conditions & Dynamic Ratings Processor • Active and Binding Transmissions Constraints • Ancillary Service Capacity Monitor • Outage Scheduler Reports • All Proposed Transmission Outages • Withdrawn Approved Transmission Facility Outages and Rescheduling of Approved Outages • All Approved, Accepted, or Rejected Transmission Outages | N/A | N/A | N/A | N/A | N/A | N/A | 2008-03-17 | 2008-04-01 | 2008-03-17 | 2008-04-01 | 2008-03-17 | 2008-04-01 | 2008-03-17 | 2008-04-01 | 2008-03-17 | 2008-04-01 | 2008-03-17 | 2008-04-01 |  | Medium |  | > Needed for EDS 4 Release 9.3 (Initial DAM / RUC Execution)
65 | EIP | FAT |  | EIP 6 | • Settlements & Billing Interfaces | N/A | N/A | 2008-01-01 | 2008-03-01 | 2007-11-01 | 2008-03-04 | 2008-02-18 | 2008-05-12 | 2008-02-18 | 2008-05-12 | 2008-02-18 | 2008-05-12 | 2008-03-01 | 2008-05-12 | 2008-03-01 | 2008-05-12 | 2008-03-01 | 2008-05-12 | > Being developed in 5 iterations with deliveries from February to May 2008. | Low | EMS 4 MMS 3 NMMS 3 CRR | > Can not test static shadow settlements wihout this system and can not test MMS to COMS connections without this system
66 | EIP | FAT |  | EIP 7 | • Web services to support EDS 4 Release 9.2 and Release 9.3 • EMS - MMS for RUC • CRR - MMS • OS - NMMS • OS - EMS • OS - WGRPP • CMM - MMS • Market Queries | N/A | 2008-03-01 | 2007-11-01 | 2008-03-04 | 2008-02-28 | 2008-03-20 | 2008-02-01 | 2008-05-08 | 2008-02-01 | 2008-05-08 | 2008-02-01 | 2008-05-08 | 2008-02-01 | 2008-05-08 | 2008-02-01 | 2008-05-08 | 2008-02-01 | 2008-05-08 | > Interfaces will be deployed to EDS as FAT testing is complete > Testing of interfaces is dependent on delivery of interfaces tables from projects | Low |  | > Completion of EMS - MMS interface will enable us to start EDS 4 Release 9.3
67 | CDR | FAT |  | CDR 2 | Real time reports needed for Settlements • Permanent Removal of Electrical Bus within Hub Bus • Deselected Contingencies • Temporarily Removed Contingencies • ERCOT System Demand from Real-Time Operations per Settlement Interval • Real-time Load Forecast Distribution Factors for MPs to calculate Electrical Bus Loads • Notification to QSEs of No Output Schedule or Energy Offer Curve • Real-Time Prices Parameters • RMR Services Quantities • SASM MCPC • Shift Schedules • System-Wide Load Forecasts • Total Ancillary Service Procured in SASM • Total ERCOT System Demand • Updated Electrical Bus Load Distribution Factors • Validated Output Schedules • Voltage Schedules • The sum of ERCOT generation from the State Estimator • Flow on the DC Ties from the State Estimator • Binding Transmission Constraints with Causal Contingency or Overloaded Element Pairs • Breaker and Switch Status -- Network Security Analysis • Day-Ahead Market CRR Offer - Minimum Reservation Price • Customer Load Profile • Derated CRRs • Market MCPCs • Load Distribution Factors • Competitive Constraints • Dynamic rating deviation data • Dynamic Ratings • Voltage Profiles • RRS deployment - RRS Deployment Instruction for non-controllable load resources • RRS Deployment Instruction for non-controllable load resources • Total ERCOT Generation Operating Reserve • Total Regulation • Unit Availability • Active SCED Contingencies • Undeployed Reg-Up and Reg-Down • Binding Constraints • Forecasted Load Frequency • Market Totals • Real-Time System Load • Shift Factors • Startup and Shutdown Instructions • Average monthly Dynamic deviation • All real-time contingency violations • Ancillary Services Capacity Monitor | N/A | N/A | N/A | N/A | N/A | N/A | 2008-04-08 | 2008-04-24 | 2008-04-08 | 2008-04-24 | 2008-04-08 | 2008-04-24 | 2008-04-08 | 2008-04-24 | 2008-04-08 | 2008-04-24 | 2008-04-08 | 2008-04-24 |  | Medium |  | > Needed for EDS 4 Release 9.4
68 | EDW | FAT |  | EDW 2 | Shadow Settlements Extracts • Day Ahead Market Settlements & Billing Extract • Day Ahead Consolidated Operating day Extract • Real Time Market Consolidated Operating Day Extract • Real Time Market Operating Day Extract • Lodestar Parser • Lodestar Replication | N/A | 2007-12-15 | N/A | N/A | N/A | N/A | 2008-05-15 | 2008-06-14 | 2008-05-15 | 2008-06-14 | 2008-05-15 | 2008-06-14 | 2008-05-15 | 2008-06-14 | 2008-05-15 | 2008-06-14 | 2008-05-15 | 2008-06-14 |  | Low | S&B 2 Business requirements | > Needed for shadow settlement verification
69 | EMS | FAT |  | EMS 4 | Final Build of • MTLF • Wind Power Forecasting • VSAT • TSAT • Dynamic Ratings • Forced Outage Detection • Interfaces • Study Mode SE • Support RT Stability Analysis • TCM • PF Trouble Shooting • Zonal Migration (SPR / SIR / Projects) | N/A | 2008-02-22 | 2008-01-28 | 2008-02-15 | 2008-01-28 | 2008-02-15 | 2008-01-28 | 2008-02-15 | 2008-01-28 | 2008-02-15 | 2008-02-25 | 2008-03-14 | 2008-02-06 | 2008-05-10 | 2008-02-22 | 2008-05-10 | 2008-02-22 | 2008-05-10 | > EMS 4.1 VSAT/TSAT - Target deployment 3/7/08 > MTLF is expected to complete FAT by 3/14/2008 > EMS 4.2 TCM, FOD, Dynamic Ratings, Interfaces, Study Appls, DRAP, Study servers, and Wind Power Short term Forecasting - Target deployment 3/7/08 > EMS 4.3 PF trouble shooting and Zonal migration - target deployment 5/10/08 >All functions with the exception of PF Trouble Shooting will be delivered by 3/7/2008 in-time for EDS 4.9.3 (Initial DAM / RUC Execution) | Low | EMS 3C | > Needed for running the RUC market > Required for testing the CIM import from NMMS into EMS
70 | EMS | FAT |  | EMS | • EMS CIM Importer | [8 empty] | N/A | N/A | TBD | TBD | 2008-04-07 | 2008-04-25 | 2008-04-07 | 2008-04-25 | 2008-04-07 | 2008-04-25 | > Delivery of CIM importer at risk due to the dependency on other systems and newness of the AREVA product. | Low |  | > EDS 4.9.3 (Initial DAM/RUC Execution) will have to start with a work around for uploading the Network Model into EMS
71 | EDW | FAT |  | EDW 3 | All Non-Shadow Settlement Extracts, Reports & Web Services Reports • ERCOT Summary Dispute Report • Missing Consumption Report EDW Outage Scheduler Reports • Resource Outage Statistics on Planned vs. Actual • Transmission Outage Statistics on Planned vs. Actual Extracts • ESI ID Service History & Usage Extract • Recorder Extract • Resource Identifier Extract • Market Participant Dispute Extract • Settlement Calendar Extract • Settlement Input Data Extract • CRR Auction Revenue Distribution (CARD) Extract • DAM Late Fee Extract • Real Time Market Late Fee Extract • Monthly Energy Deployed by RMR Units Extract Web Services • Provide all ESI ID extract records • Provide data aggregation records • Provide ESI ID extract records for logical keys • Provide ESI IDs where IDR usage data not loaded for a trade date • Provide IDR transaction data for ESI IDs I own • Provide IDR usage data for a trade date • Provide IDR usage data for particular ESI IDs I own | N/A | N/A | N/A | N/A | N/A | N/A | 2008-07-01 | 2008-08-31 | 2008-07-01 | 2008-08-31 | 2008-07-01 | 2008-08-31 | 2008-07-01 | 2008-08-31 | 2008-07-01 | 2008-08-31 | 2008-07-01 | 2008-08-31 | > Reports and extracts will be deployed into EDS as testing completes | Low |  | > Required before starting 168hr test
72 | EMS | FAT |  | EMS 5A | • Outage Evaluation • Outage Sensitivity Calculations | N/A | 2008-04-11 | 2008-03-05 | 2008-03-31 | 2008-03-05 | 2008-03-31 | 2008-03-05 | 2008-03-31 | 2008-03-05 | 2008-03-31 | 2008-05-08 | 2008-05-29 | 2008-05-08 | 2008-05-29 | 2008-05-08 | 2008-05-29 | 2008-05-08 | 2008-05-29 |  | Low | EMS 4 | > Required before starting 168hr test
72a | EMS | FAT |  | EMS 5B | • Voltage Support | [14 empty] | 2008-05-08 | 2008-05-29 | 2008-07-07 | 2008-07-31 | > Working with vendor to resolve schedule slippage | Low |  | > Required before starting 168hr test
73 | MMS | FAT |  | MMS 3 | • Includes functionality from MMS 2 release plus: • SASM • Settlements and Billing snapshots • Spring DST, Fall DST | N/A | N/A | 2008-01-24 | 2008-02-14 | 2008-02-18 | 2008-03-14 | 2008-02-18 | 2008-03-14 | 2008-02-18 | 2008-03-14 | 2008-02-18 | 2008-03-14 | 2008-02-18 | 2008-03-14 | 2008-02-18 | 2008-03-14 | 2008-02-18 | 2008-03-14 |  | High |  | > Required for EDS4 release 9 testing and 168 hour test
74 | MMS | FAT |  | MMS 3a | • MMS CIM importer (no dual model support) as related to the power flow and CIM data dictionary v1.7 | [8 empty] | N/A | N/A | 2008-02-18 | 2008-03-14 | 2008-02-18 | 2008-03-14 | 2008-02-18 | 2008-03-14 | 2008-02-18 | 2008-03-14 | > Delivery of CIM importer at risk due to dependency impacts | Low | NMMS 2A | > This is required for testing the import of the CIM xml from NMMS into MMS
75 | COMS | FAT |  | S&B 3 | • Interfaces with settlements and finance • Testing of banking statements • Registration (Siebel) Clean-up fields for downstream applications to work • Settlements and Billing - Baseline 1 and Baseline 2 • Settlements and Billing - Bugfixes > CMM/CRR integration. FAT start 2/15 and FAT end 2/28 | N/A | N/A | 2008-01-01 | 2008-03-01 | 2008-01-01 | 2008-03-01 | 2008-01-01 | 2008-03-01 | 2008-01-01 | 2008-03-01 | 2008-01-21 | 2008-03-01 | 2008-01-21 | 2008-03-01 | 2008-01-21 | 2008-03-01 | 2008-01-21 | 2008-03-01 | > New milestone added for FT deployment, and S&B cleanup due to 4.7 release | Medium |  | > Required for EDS4 Release 9 testing and 168 hr test
76 | EIP | FAT |  | EIP 8 | • Deployment of Common Services to monitor CIM importers • Siebel to NMMS • Siebel to OS | N/A | N/A | 2008-01-01 | 2008-03-01 | N/A | N/A | 2008-04-07 | 2008-05-09 | 2008-04-07 | 2008-05-09 | 2008-04-07 | 2008-05-09 | 2008-04-07 | 2008-05-09 | 2008-04-07 | 2008-05-09 | 2008-04-07 | 2008-05-09 | > Includes EIP 1 scope from previous centerfolds | Low | EMS 4 MMS 2 NMMS 3 | > Required for EDS4 Release 9 testing and 168 hr test
77 | CDR | FAT |  | CDR 3 | All other remaining Real Time reports not deployed as part of RTR 1 and RTR 2 • Hourly Demand Forecast • Topology Consistency Analyzer Incorrect Breaker and Switch Status • Output Schedule of Changes/Adjustments • SCED Shadow Prices • Shadow Prices on Binding Transmission Constraints • State Estimator Transmission Flows and Voltages • State Estimator 15-minute Load Averages on Electrical Buses • Individual transmission Load on Electrical Buses from the State Estimator • State Estimator Transformer Flows, Voltages and Tap Position • LMPs by Resource Node • Sum of the Load on each Electrical Bus in each Load Zone from the State Estimator • Total Load on Electrical Buses in the ERCOT System from the State Estimator | N/A | N/A | N/A | N/A | N/A | N/A | 2008-06-03 | 2008-06-30 | 2008-06-03 | 2008-06-30 | 2008-06-03 | 2008-06-30 | 2008-06-03 | 2008-06-30 | 2008-06-03 | 2008-06-30 | 2008-06-03 | 2008-06-30 |  | Medium |  | > Required before starting 168hr test
78 | COMS | FAT |  | S&B 5 | • Commercial Systems Integration | [10 empty] | N/A | N/A | 2008-04-15 | 2008-07-31 | 2008-04-15 | 2008-07-31 | 2008-04-15 | 2008-07-31 | >initial release to EDS will not have full functionality due to late delivery of multiple dependent project drops > Continue to build up functionality as available from source systems > First release planning to iTEST in March 2008 (~50% bill determinants) | Medium |  | > Required for EDS4 release 8 and 9 testing and 168 hour test
79 | COMS | FAT | Dis | S&B 4 | • Financial Transfer • Disputes and Disputes Processes • Verifiable Costs (FAT end March '08) | N/A | 2008-05-31 | 2008-03-01 | 2008-05-31 | 2008-03-01 | 2008-05-31 | 2008-03-01 | 2008-05-31 | 2008-03-01 | 2008-05-31 | 2008-03-01 | 2008-05-31 | 2008-03-01 | 2008-05-31 | 2008-03-01 | 2008-05-31 | 2008-03-01 | 2008-05-31 | > Was shown as "DIS" in March Timeline > Might be in June due to conjunction with Retail release to Prod | High |  | > Not needed until 168 hr test
80 | MMS | FAT |  | MMS 4 | All functionality needed for 168 hour test including Baseline 1 & 2 • CCT • NSLR • DC Tie • VDI • WRUC • Remaining B1&2 items | N/A | N/A | 2008-04-07 | 2008-05-28 | 2008-04-22 | 2008-06-30 | 2008-04-22 | 2008-06-30 | 2008-04-22 | 2008-06-30 | 2008-04-22 | 2008-06-30 | 2008-04-22 | 2008-06-30 | 2008-04-22 | 2008-06-30 | 2008-04-22 | 2008-06-30 | > Vendor committed to delivery dates | Medium |  | > Need to re-test Settlements after NPRR 35 has been implemented by ABB as part of MMS 4
81 |  | EDS 4 Release 8.1: |  | CMM and CRR Invoices | > Post CP Credit limit on MIS > Post mock CRR auction invoices > Post CRR auction invoices based on actual CRR testing results | TBD | TBD | TBD | TBD | 2008-03-01 | 2008-08-31 | 2008-03-01 | 2008-08-31 | 2008-03-01 | 2008-08-31 | 2008-03-01 | 2008-08-31 | 2008-03-01 | 2008-08-31 | 2008-03-01 | 2008-08-31 | 2008-03-01 | 2008-08-31 | > May 1 is the target start for Mock settlements and July 1 is the target start date for integrated settlements with extracts | Medium
82 |  | EDS 4 Release 8.2: |  | DAM Settlements and Invoices | > Post mock DAM Settlement Statements and Invoices > Post mock CRR balancing account invoices, CARD Invoices, Late Fee Invoices > Post DAM Settlement Statements and Invoices based on EDS DAM testing results > Validate DAM Re-settlement Statements and Invoices | TBD | TBD | TBD | TBD | 2008-05-01 | 2008-08-31 | 2008-04-01 | 2008-08-31 | 2008-04-01 | 2008-08-31 | 2008-04-01 | 2008-08-31 | 2008-01-29 | 2008-08-31 | 2008-01-29 | 2008-08-31 | 2008-01-29 | 2008-08-31 | > Settlement statements templates (with test data) will be available for download by Apr 01, 2008 > May 1 is the target start for Mock settlements and July 1 is the target start date for integrated settlements with extracts > Posted DAM Statement example format (XSL), invoices are in progress | Medium
83 |  | EDS 4 Release 8.3 |  | RTM Settlements and Invoices | > Post mock RT Settlement Statements and Invoices > Post RT Settlement Statements and Invoices based on EDS RTM testing results > Post settlement extracts | TBD | TBD | TBD | TBD | 2008-05-01 | 2008-08-31 | 2008-04-01 | 2008-08-31 | 2008-04-01 | 2008-08-31 | 2008-04-01 | 2008-08-31 | 2008-04-01 | 2008-08-31 | 2008-04-01 | 2008-08-31 | 2008-04-01 | 2008-08-31 | > Settlement statements templates (with test data) will be available for download by Apr 01, 2008 > May 1 is the target start for Mock settlements and July 1 is the target start date for integrated settlements with extracts | Medium
84 |  | EDS 4 Release 8.4 |  | Verifiable Costs | > Verifiable costs | TBD | TBD | TBD | TBD | 2008-03-01 | 2008-08-31 | 2008-03-01 | 2008-08-31 | 2008-03-01 | 2008-08-31 | 2008-03-01 | 2008-08-31 | 2008-03-01 | 2008-08-31 | 2008-03-01 | 2008-08-31 | 2008-03-01 | 2008-08-31 | > Will need to work with MPs on "real" verifiable cost versus EDS verifiable cost information > changes will be packaged with Retail release to production | Medium
85 |  | EDS 4 Release 8.5 |  | Disputes | > Disputes | TBD | TBD | TBD | TBD | 2008-06-01 | 2008-08-31 | 2008-06-01 | 2008-08-31 | 2008-06-01 | 2008-08-31 | 2008-06-01 | 2008-08-31 | 2008-06-01 | 2008-08-31 | 2008-06-01 | 2008-08-31 | 2008-06-01 | 2008-08-31 | > Changes are packaged with retail release to production | Medium
86 |  | EDS 4 Release 9.1 |  | DAM / RUC Submission testing | > MP submission of > Three Part Supply Offers (to include Start-Up and Min Energy costs) > DAM Energy Only Offers > A/S Offers > CRR Offers > DAM Energy Bid > PTP Obligation Bid > Capacity trade > Energy Trade > AS Trade > AS Self-Arrangement > DC-Tie Schedules | TBD | TBD | TBD | TBD | 2008-01-15 | 2008-03-31 | 2008-01-15 | 2008-03-31 | 2008-01-15 | 2008-03-31 | 2008-01-15 | 2008-03-31 | 2008-01-15 | 2008-03-31 | 2008-01-15 | 2008-03-31 | 2008-01-15 | 2008-03-31 | > Started testing with MPs on Jan 14,2008 on schedule | Medium
87 |  | EDS 4 Release 9.2 |  | Outage Scheduler submission testing | > Outage Scheduler submission testing | TBD | TBD | TBD | TBD | 2008-03-18 | 2008-08-15 | 2008-03-18 | 2008-08-15 | 2008-03-18 | 2008-08-15 | 2008-03-18 | 2008-08-15 | 2008-03-18 | 2008-08-15 | 2008-03-18 | 2008-08-15 | 2008-04-01 | 2008-08-01 | > At risk due to delays in development of new OS UI > Seeking TPTF guidance on duration of dual-entry | Low
88 |  | EDS 4 Release 9.3 |  | Initial DAM / RUC Execution | > Execution of DAM > Execution of RUC > Posting of DAM and RUC results (QSE A/S Obligations, Load Profiles, Hourly Load Forecast (MTLF), Distribution Loss Factors, Wind Generation Renewable , Production Potential, Post Available Credit Limits (ACL), Post System Wide Offer Caps) > Dynamic Ratings | TBD | TBD | TBD | TBD | 2008-04-01 | 2008-05-15 | 2008-04-01 | 2008-05-15 | 2008-04-01 | 2008-05-15 | 2008-04-01 | 2008-05-15 | 2008-04-01 | 2008-05-15 | 2008-04-01 | 2008-05-15 | 2008-04-01 | 2008-05-15 | > low confidence in starting this release with an integrated EMS, MMS and NMMS for CIM > ABB CIM Importer could be delayed because of delays in receiving CIM XML and associated Powerflow from NMMS > Cross team effort to populate CIM extensions in MMS | Low
89 |  | EDS 4 Release 9.4 |  | DAM, RUC and Adj Period Execution | > ERCOT perform pre-DAM evaluation and posting > QSE submission of DAM/RUC bids/offers > ERCOT execution of DAM and posting of results > QSE submission of updates to COP and Trades > ERCOT execution of DRUC and posting of results > ERCOT Adjustment Period Activities, Hour Ahead Sequence > QSE submissions continue for Adjustment Period > ERCOT executes HRUC > ERCOT executes SASM > ERCOT Operating Hour Activities, including SCED | TBD | TBD | TBD | TBD | 2008-05-01 | 2008-06-30 | 2008-05-01 | 2008-06-30 | 2008-05-01 | 2008-06-30 | 2008-05-01 | 2008-06-30 | 2008-05-01 | 2008-06-30 | 2008-05-01 | 2008-06-30 | 2008-05-01 | 2008-06-30 |  | Low
90 |  | EDS 4 Release 9.5 |  | Execute full Nodal Integrated System | > Fully integrated Nodal system | TBD | TBD | TBD | TBD | 2008-07-01 | 2008-08-31 | 2008-07-01 | 2008-08-31 | 2008-07-01 | 2008-08-31 | 2008-07-01 | 2008-08-31 | 2008-07-01 | 2008-08-31 | 2008-07-01 | 2008-08-31 | 2008-07-01 | 2008-08-31 |  | Low
MP Activities
91 |  | MP Activities |  | RARF 2 |  | N/A |  | N/A |  | 2007-11-09 |  | 2007-11-09 |  | 2007-11-09 |  | 2007-11-09 |  | 2007-11-09 |  | 2007-11-09 |  | 2007-11-09 |  |  | Submitted to ERCOT
92 |  | MP Activities |  | RARF 3 |  | N/A |  | N/A |  | 2007-12-31 |  | 2007-12-31 |  | 2007-12-31 |  | 2007-12-31 |  | 2007-12-31 |  | 2007-12-31 |  | 2007-12-31 |  |  | Submitted to ERCOT
93 |  | MP Activities |  | NMMS Sandbox available | [13 empty] | 2008-01-30 |  | 2008-01-30 |  | 2008-01-30 |  | > Sandbox opened up for TSPs to start learning about the tool
94 |  | MP Activities |  | RARF Complete |  | N/A |  | N/A |  | 2008-04-01 |  | 2008-04-01 |  | 2008-04-01 |  | 2008-04-01 |  | 2008-04-01 |  | 2008-04-01 |  | 2008-04-01 |  |  | N/A
95 |  | MP Activities |  | Begin 6 Month LMP Posting |  | N/A |  | N/A |  | 2008-02-01 |  | 2008-01-15 |  | 2008-02-01 |  | 2008-02-15 |  | 2008-02-15 |  | 2008-02-15 |  | 2008-02-15 |  | > Impacted because of delays in proving LMP reasonableness
96 |  | MP Activities |  | DAM Readiness | > Ability to input the following transactions into MMS system > Three Part Supply Offers (to include Start-Up and Min Energy costs) > DAM Energy Only Offers > Ancillary Service Offers > CRR Offers > DAM Energy Bid > PTP Obligation Bid > Capacity trade > Energy Trade > Ancillary Service Trade > Ancillary Service Self-Arrangement > DC-Tie Schedules | N/A |  | N/A |  | 2008-01-15 |  | 2008-01-15 |  | 2008-01-15 |  | 2008-01-15 |  | 2008-01-15 |  | 2008-01-15 |  | 2008-01-15
97 |  | MP Activities |  | Begin LFC 6.2 testing | > Start MP level LFC testing. All MPs should be ready to test LFC with ERCOT | N/A |  | N/A |  | 2008-03-01 |  | 2008-03-01 |  | 2008-03-01 |  | 2008-03-01 |  | 2008-03-01 |  | 2008-03-01 |  | 2008-03-01
98 |  | MP Activities |  | LFC Readiness | > Prepare to demonstrate the ability of Resources to respond correctly to the UDBP’s as calculated by LFC > Ability to receive Responsive reserve deployment signal, update Responsive Reserve Ancillary Service Schedule(s) and provide updated schedules to ERCOT | N/A |  | N/A |  | 2008-04-11 |  | 2008-04-11 |  | 2008-04-11 |  | 2008-04-11 |  | 2008-04-11 |  | 2008-04-11 |  | 2008-04-11
99 |  | MP Activities |  | Begin LFC 6.3 testing | > Start of full market testing of LFC | N/A |  | N/A |  | 2008-06-01 |  | 2008-06-01 |  | 2008-06-01 |  | 2008-06-01 |  | 2008-06-01 |  | 2008-06-01 |  | 2008-06-01
100 |  | MP Activities |  | CRR Readiness | > Register as a CRR Account Holder and complete the ERCOT CRR Training | N/A |  | N/A |  | 2008-01-15 |  | 2008-01-15 |  | 2008-01-15 |  | 2008-01-15 |  | 2008-01-15 |  | 2008-01-15 |  | 2008-01-15
101 |  | MP Activities |  | Begin CRR Testing | > Start full CRR auction testing | N/A |  | N/A |  | 2008-02-02 |  | 2008-02-02 |  | 2008-02-02 |  | 2008-02-02 |  | 2008-02-02 |  | 2008-02-02 |  | 2008-02-02 |  | > Milestone currently at risk because of hardware dependencies.
102 |  | MP Activities |  | PCRR Allocation | > PCRR allocation before 1st CRR Monthly auction | N/A |  | N/A |  | 2008-10-01 |  | 2008-10-01 |  | 2008-10-01 |  | 2008-10-01 |  | 2008-10-01 |  | 2008-10-01 |  | 2008-10-01
Go-Live Activities
103 |  | Go-Live Activities |  | MP Interface Spec. |  | 2007-03-31 |  | 2007-03-31 |  | 2007-03-31 |  | 2007-03-31 |  | 2007-03-31 |  | 2007-03-31 |  | 2007-03-31 |  | 2007-03-31 |  | 2007-03-31 |  |  | N/A
104 |  | Go-Live Activities |  | Single-Entry Model |  | 2008-03-31 |  | 2008-03-31 |  | 2008-03-31 |  | 2008-03-31 |  | 2008-03-31 |  | 2008-05-31 |  | 2008-05-31 |  | 2008-05-31 |  | 2008-05-31 |  | > At risk because of delays in starting EDS 2 Release 4 due to software issues > Further delays could be caused because of data synchronization activities with TSPs | N/A
105 |  | Go-Live Activities |  | 1st CRR Monthly Allocation |  | N/A | N/A | 2008-11-03 |  | 2008-11-03 |  | 2008-11-03 |  | 2008-11-03 |  | 2008-11-03 |  | 2008-10-22 |  | 2008-10-22 |  | 2008-10-22 |  |  | N/A
106 |  | Go-Live Activities |  | 168-Hour test |  | 2008-08-31 |  | 2008-08-31 |  | 2008-08-31 |  | 2008-08-31 |  | 2008-08-31 |  | 2008-08-31 |  | 2008-08-31 |  | 2008-08-31 |  | 2008-08-31 |  |  | N/A
107 |  | Go-Live Activities |  | RTM Go-Live |  | 2008-12-01 |  | 2008-12-01 |  | 2008-12-01 |  | 2008-12-01 |  | 2008-12-01 |  | 2008-12-01 |  | 2008-12-01 |  | 2008-12-01 |  | 2008-12-01 |  |  | N/A
108 |  | Go-Live Activities |  | DAM Go-Live |  | 2008-12-08 |  | 2008-12-08 |  | 2008-12-08 |  | 2008-12-08 |  | 2008-12-08 |  | 2008-12-08 |  | 2008-12-08 |  | 2008-12-08 |  | 2008-12-08 |  |  | N/A
Formulas:
Current Centerfold v11/30/2007 End = [Current Centerfold v1/4/2008 End]
Current Centerfold v11/30/2007 Start = [Current Centerfold v1/4/2008 Start]
Current Centerfold v2/15/2008 Start = [Current Centerfold v2/29/2008 Start]