| # Proposed Flight Schedule for MarkeTrak Phase 2 in 2008 |  |
| --- | --- |
| Activity | ## Calendar Date |
| Script Sub Team review first draft of scripts | #### Mar 7, 2008 |
| Script Sub Team review second draft of scripts | ## Mar 14, 2008 |
| MarkeTrak Task Force review scripts | ## Mar 26, 2008 |
| Deadline for feedback for MarkeTrak test scripts | #### Mar 31, 2008 |
| Texas Test Plan Team Meeting to finalize scripts. MarkeTrak Task Force will be included in meeting. | #### Mar 31, 2008 |
| Notice from ERCOT Retail Client Services to notify market participants of MarkeTrak Testing for Retail Market Testing sent to ERCOT lists.ercot.com distribution | ### Apr 7, 2008 |
| Publish scripts | #### Apr 10, 2008 |
| MarkeTrak Task Force Meeting | #### Apr 17, 2008 |
| Deadline to sign up for voluntary GUI testing. All API will be mandatory. | #### May 1, 2008 |
| Communication from ERCOT Flight Administrator of testing participants to each TDSP and CR | #### May 7, 2008 |
| MarkeTrak Task Force Meeting | #### May 8 - 9, 2008 |
| TDSPs communicate test beds for all releases to ERCOT and CRs. | #### May 14, 2008 |
| Kick off of API connectivity and Sandbox | #### May 20, 2008 |
| MarkeTrak Task Force first draft of Users Guide | #### May 22, 2008 |
| MarkeTrak Task Force finalize Users Guide and send to ERCOT | #### Jun 12, 2008 |
| 21 Day comment period for Users Guide begins | #### Jun 13, 2008 |
| Sandbox loaded with data for Release 1 | Jun 16, 2008 |
| Users Guide presented to RMS for approval | Jul 9, 2008 |
| Sandbox loaded with data for Release 2 | ##### Jul 9, 2008 |
| Sandbox closes | ##### Jul 28, 2008 |
| Sandbox loaded with data for Release 3 | ##### Oct 13, 2008 |