|  |  | System Planning Division |
| --- | --- | --- |
|  |  | Monthly Status Report to Reliability and Operations Subcommittee for February 2008 |
|  | Report Highlights |  |
| Item |  |  |
| 1. | ERCOT is currently tracking 233 active generation interconnection requests totaling over 103,000 MW. This includes almost 46,000 MW of wind generation. |  |
| 2. | New Interconnect Agreements signed: Sherbino Mesa Wind Farm (06INR0012) for 300 MW in Pecos County Coyote Run Wind Farm (07INR0036) for 184 MW in Borden County |  |
| 3. | The 2007 CSC Utilization Report was presented to WMS on February 20. Details at: http://www.ercot.com/meetings/wms/keydocs/2008/0220/06._CSCuseJan-Dec_20080219.ppt |  |
| 4. | Regional Planning is currently reviewing proposed transmission improvements with a total cost of $180.00 M. |  |
| 5. | The final results of the Wind Impact Study presented to the ROS Wind Impact Task Force on Feb. 27 are posted at: http://www.ercot.com/calendar/2008/02/20080227-WIND.html |  |
| 6. | Annual Load Data Request (ALDR) Process Underway |  |

Table of Contents

1.	Generation Interconnection	1

1.1.	New Generation Beginning Commercial Operations	1

1.2.	New Signed Interconnection Agreements (also found in 1.4 Table) 	1

1.3.	Summary of Active Generation Interconnection Requests	1

1.4.	Potential Future Generation Interconnections	1

2.	Regional Planning Group Project Reviews	3

3.	Other Notable Activities	4

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://oldercot.ercot.com/tmaps.

## New Generation Beginning Commercial Operations

None for February

## New Signed Interconnection Agreements (also found in 1.4 Table)

- 06INR0012, Sherbino Mesa Wind Farm for 300 MW in Pecos County

- 07INR0036, Coyote Run Wind Farm for 184 MW in Borden County

## Summary of Active Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY BEING PROCESSED |
| --- |
| Currently tracking 233 active generation interconnection or change requests As of February 29, 2008 |
|  | North | South | West | Total |
| Security Screening Study |  | 5 | 8 | 19 | 38 |
| SSS Completed |  | 9 | 9 | 10 | 28 |
| Full Interconnect Study |  | 27 | 31 | 70 | 128 |
| FIS Completed |  | 0 | 1 | 2 | 3 |
| Interconnect Agreement Completed |  | 8 | 6 | 23 | 37 |
| Capacity for Grid, MW |  | 28,389 | 31,370 | 43,518 | 103,277 |
| Wind Capacity, MW |  | 2,463 | 4,237 | 39,923 | 46,623 |

| Fuel | Public (MW) | Non-public (MW) | Total (MW) |
| --- | --- | --- | --- |
| Natural gas | 4,990 | 27,298 | 32,288 |
| Nuclear | 9,186 | 6,400 | 15,586 |
| Coal | 4,841 | 3,514 | 8,355 |
| Wind | 10,276 | 36,347 | 46,623 |
| Other |  | 425 | 425 |
| Totals | 29,293 | 73,984 | 103,277 |

## Potential Future Generation Interconnections

The table below summarizes the publicly known potential future generation projects for the ERCOT region.  (IA=Interconnect Agreement, PL=Public Letter)

| Future Generation Interconnections (Public Projects) as of February 29, 2008 |
| --- |
| INR # | Site Name | Status | County | Region | Fuel | In Service Date | MW into Grid | Change from Last Report |
| 07INR0049 | J T Deely Upgrade | PL | South | 80 | Coal | Nov-07 | 80 |  |
| 03INR0034 | Silver Star Project - Clipper | IA | North | 60 | Wind | Apr-08 | 60 |  |
| 07INR0028 | Goat Wind | IA | West | 150 | Wind | Apr-08 | 150 |  |
| 07INR0030 | Louis (Buffalo Gap 3) | IA | West | 138 | Wind | Apr-08 | 138 |  |
| 06INR0036 | Quail Run Energy Center 2 | IA | West | 275 | Gas | May-08 | 275 |  |
| 06INR0035 | Colorado Bend Energy Center 2 | IA | South | 275 | Gas | Jun-08 | 275 |  |
| 07INR0022 | Airtricity Panther Creek Wind Farm | IA | West | 150 | Wind | Jun-08 | 150 |  |
| 07INR0027 | South Houston Green Pwr Exp | IA | South | 244 | Gas | Jun-08 | 244 | Date Change |
| 08INR0028 | McAdoo Energy Center | IA | North | 300 | Wind | Jul-08 | 300 |  |
| 03INR0030 | Wild Horse Wind Farm 2 | IA | West | 39 | Wind | Aug-08 | 39 |  |
| 04INR0011b | Mesquite Wind Phase 4 | IA | West | 136 | Wind | Aug-08 | 136 |  |
| 04INR0011c | Cottonwood Wind | IA | West | 100 | Wind | Aug-08 | 100 |  |
| 04INR0017 | Ocotillo Wind Farm 1 | IA | West | 59 | Wind | Aug-08 | 59 |  |
| 08INR0038 | M Bar Wind | PL | West | 194 | Wind | Sep-08 | 194 |  |
| 06INR0012 | Sherbino Mesa Wind Farm | IA | West | 300 | Wind | Oct-08 | 300 | New IA |
| 07INR0025 | Airtricity Lamesa Wind Plant | IA | West | 183 | Wind | Oct-08 | 183 |  |
| 07INR0034 | Wolf Ridge Wind Farm | IA | North | 201 | Wind | Oct-08 | 201 |  |
| 07INR0037 | Bull Creek Wind Plant | IA | West | 180 | Wind | Oct-08 | 180 |  |
| 07INR0045a | Airtricity Pyron Wind Farm | IA | West | 303 | Wind | Nov-08 | 303 |  |
| 07INR0045b | Airtricity Inadale | IA | West | 212 | Wind | Nov-08 | 212 |  |
| 04INR0011e | Hackberry Wind Farm | IA | West | 165 | Wind | Dec-08 | 165 |  |
| 05INR0015a | Gulf Wind 1 | IA | South | 283 | Wind | Dec-08 | 283 |  |
| 06INR0022a | Penascal Wind Farm 1 | IA | South | 202 | Wind | Dec-08 | 202 |  |
| 07INR0005 | Notrees-1 | IA | West | 150.75 | Wind | Dec-08 | 151 |  |
| 07INR0011 | Turkey Track Energy Center | IA | West | 300 | Wind | Dec-08 | 300 |  |
| 07INR0029 | South Trent Wind Farm | IA | West | 101.2 | Wind | Dec-08 | 101 |  |
| 08INR0018 | Gunsight Mountain | IA | West | 120 | Wind | Dec-08 | 120 |  |
| 08INR0025 | Pistol Hill Energy Center | PL | West | 300 | Wind | Dec-08 | 300 |  |
| 08INR0037 | Airtricity Panther Creek 2 | IA | West | 220 | Wind | Dec-08 | 220 |  |
| 08INR0053 | Elbow Creek Wind Project | IA | West | 117.3 | Wind | Dec-08 | 117 |  |
| 08INR0059 | Gray Wind Project | PL | West | 141 | Wind | Dec-08 | 141 |  |
| 09INR0026a | Sterling Energy Center | PL | West | 200 | Wind | Dec-08 | 200 |  |
| 07INR0036 | Coyote Run Wind Farm | IA | West | 184 | Wind | Mar-09 | 184 | New IA |
| 08INR0046 | Bosque Expansion | IA | North | 255 | Gas | Mar-09 | 255 |  |
| 08INR0065 | Buffalo Gap 4 and 5 | PL | West | 465 | Wind | Mar-09 | 465 |  |
| 08INR0040 | Lenorah Project | PL | West | 350 | Wind | May-09 | 350 |  |
| 09INR0028 | V H Braunig 6 | PL | South | 185 | Gas | May-09 | 185 |  |
| 09INR0060 | Wind Tex Stephens Wind Farm | PL | West | 141 | Wind | May-09 | 141 |  |
| 08INR0035 | Cedar Bayou 4 | IA | South | 539 | Gas | Jun-09 | 539 |  |
| 09INR0026 | Sterling Energy Center | PL | West | 300 | Wind | Jun-09 | 300 |  |
| 09INR0027 | Winchester Peaking Plant | PL | South | 178 | Gas | Jun-09 | 178 |  |
| 09INR0036 | McAdoo Energy Center II | PL | West | 500 | Wind | Jun-09 | 500 |  |
| 09INR0045 | Sand Hill Peakers | PL | South | 90 | Gas | Jun-09 | 90 |  |
| 08INR0003 | Sandow 5 | IA | North | 581 | Coal | Jul-09 | 581 |  |
| 05INR0015b | Gulf Wind 2 | PL | South | 400 | Wind | Sep-09 | 400 |  |
| 09INR0015 | Comanche Peak 1&2 Upgrade | PL | North | 86 | Nuclear | Oct-09 | 86 |  |
| 03INR0030 | Wild Horse Wind Farm 1 | IA | West | 60 | Wind | Nov-09 | 60 |  |
| 09INR0006 | Oak Grove SES 1 | IA | North | 855 | Coal | Nov-09 | 855 |  |
| 09INR0034 | Gatesville Wind Farm | PL | North | 200 | Wind | Dec-09 | 200 |  |
| 10INR0010 | Jack County 2 | PL | North | 499 | Gas | Jan-10 | 499 |  |
| 09INR0037 | Scurry County Wind III | PL | West | 350 | Wind | Mar-10 | 350 |  |
| 06INR0006 | Cobisa-Greenville | PL | North | 1750 | Gas | May-10 | 1,750 |  |
| 09INR0006 | Oak Grove SES 2 | IA | North | 855 | Coal | May-10 | 855 |  |
| 09INR0002 | J K Spruce 2 | IA | South | 750 | Coal | Jun-10 | 750 |  |
| 05INR0015c | Gulf Wind 3 | PL | South | 400 | Wind | Sep-10 | 400 |  |
| 09INR0001 | Sandy Creek 1 | IA | North | 925 | Coal | Sep-10 | 925 |  |
| 06INR0026 | Wild Horse Mountain | IA | West | 120 | Wind | Dec-10 | 120 |  |
| 12INR0003 | Throckmorton Wind Farm | PL | West | 400 | Wind | Dec-10 | 400 |  |
| 11INR0007 | Mountain Creek | PL | North | 700 | Gas | Apr-11 | 700 |  |
| 11INR0001 | Twin Oaks 3 | PL | North | 630 | Coal | Jun-11 | 630 |  |
| 07INR0004 | Pampa Energy Center | PL | West | 165 | Coal | May-12 | 165 |  |
| 09INR0024 | B&B Panhandle Wind | PL | West | 1001 | Wind | Jun-12 | 1,001 |  |
| 12INR0004 | Fort Concho Wind Farm | PL | West | 400 | Wind | Jul-12 | 400 |  |
| 11INR0011 | Victoria City Nuclear | PL | South | 3200 | Nuclear | Jan-15 | 3,200 |  |
| 15INR0002 | Comanche Peak 3 and 4 | PL | North | 3200 | Nuclear | Jan-15 | 3,200 |  |
| 15INR0008 | STP 3 and 4 | PL | South | 2700 | Nuclear | Jan-15 | 2,700 |  |
|  |  |  |  |  |  | Total | 29,293 |  |

# Regional Planning Group Project Reviews

- Luminant has submitted two interrelated, yet independent projects for review.  The first project is the planned upgrade of the Tyler Northeast to Tyler East 138 kV line, which was planned to be complete in May 2012, but will be accelerated to May 2009 with an estimated total project cost of $4 M.  The second related project is the addition of the Tyler Grande (Tyler Southeast) 345/138 kV autotransformer and an increase in the planned capacity of Tyler Grande (Southeast) to Tyler South from 326 MVA to 400 MVA.  The second project is planned to be complete in May 2009 with a cost of approximately $10 M and will require ERCOT Board approval due to the new 345/138 kV Tyler Grande switching station and associated autotransformer. The ERCOT review of this project is complete and will be presented to TAC on March 6, 2008 and the ERCOT Board of Directors on March 18, 2008.

- Oncor submitted a two phase project to relieve congestion that will occur when two new Wind units are connected to the transmission system in the Lamesa area.  The first phase of the project will upgrade both ends, but not the middle of the Lamesa to Bluff Creek 138 kV line, rebuild the Bluff Creek to China Grove 138 kV line, rebuild the Lamesa to Ackerly Vealmoor 69 kV line to 138/69 kV double circuit, rebuild the Lamesa 138 kV switching station, and build a new 138 kV Ackerly Vealmoor station.  All transmission rebuilds will utilize double circuit construction with one circuit in place, except the Lamesa to Ackerly Vealmoor 138/69 kV double circuit.  The cost of the first phase of these upgrades is $40.3 M.  The second phase of the project has additional work to be done if a third wind unit signs and interconnect agreement that will add second circuits to all rebuilt lines and include station upgrades at China Grove and Big Spring.  The additional cost of the second phase upgrades is $40.5 M.  The first phase was included as an economic project in the 2007 Five Year Plan.  The second phase will be studied separately.  Both phases of this project are still being reviewed.

- Oncor submitted a two part project based on the 2007 Five Year Plan that will replace the 517 MVA 345/138 kV autotransformer at Roanoke Switch with a 600 MVA autotransformer in 2009 at a cost of $7.25 M.  In 2010 the old Roanoke auto will be installed at Eagle Mountain which showed high congestion levels in the Five Year Plan at a cost of $2.0 M.  The review of this two-part project is complete and a RPG Acceptance Letter was mailed on or around February 25, 2008.

- Oncor submitted a project to upgrade the Payne to Collin 138 kV to a rating of 326 MVA using double circuit structures with one circuit in place for a cost of $19 M.  This project is currently in ERCOT Independent Review.

- Oncor submitted a project to construct the Krum Tap Switching Station and rebuild the Krum – Decatur 69 kV line and the Krum Tap 138 kV line as a 138 kV double-circuit line with one circuit in place using a conductor with a minimum rating of 214 MVA. The estimated cost of this project is $17.8 M and is currently in ERCOT Independent Review.

- LCRA submitted a project to add a 3rd 345/138 kV autotransformer at the Zorn substation.  This project should be complete by summer peak 2013 and cost is estimated at $15 M.  This project is currently in ERCOT Independent Review.

- Oncor submitted a project to upgrade the Midland East – Stanton East – Big Spring West – Big Spring Switch 138 kV line.  The proposed upgrade will replace the existing 4/0 ACSR 84 MVA circuit with a single circuit line with a long-term emergency rating of 394 MVA.  The estimated completion date is peak 2010 with a cost of approximately $ 24 M.

# Congestion Management

2007 CSC Utilization Report:  for the details of the table below (intervals, flows / limits, costs and quantities) see the CSCuseJan-Dec_20080219 presentation to the February 20 WMS (Item 6 in the Key Documents) at the following link: http://www.ercot.com/calendar/2008/02/20080220-WMS.html

| $Million | E_N | N_H | S_H | S_N | N_W | W_N | N_S | TOTAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 01/2008 | -- | -- | -- | -2.0 | .1 | 6.6 | 2.6 | 7.3 |
| 2007 total | -- | 39.8 | 12.5 | -1.5 | 5.1 | 4.4 | -- | 60.2 |
| 2006 total | 7.4 | 8.4 | 31.4 | 1.5 | 3.0 | 0.2 | -- | 52.0 |

Settlement quality data available through November 2007

# Other Notable Activities

All postings referred to below can be found at http://oldercot.ercot.com/tmaps unless otherwise indicated.

GE gave the final presentation on the Wind Impact/Ancillary Services Study on February 27 at the MET Center.  A copy of the presentation is available at:

http://www.ercot.com/calendar/2008/02/20080227-WIND.html

  - GE is preparing a final report describing the assumptions, methodology and results of their study.  A draft copy of this final report is expected on March 15.  Stakeholder comments on the report will be accepted through March 21, and the final Wind Impact Study report will be due on March 28.

CREZ Study (SB20) continues

System Planning is analyzing transmission solutions as part of the CREZ Transmission Optimization Study.  The next RPG-CREZ Task Force meeting will be held on March 10 in room 206.

The ‘ERCOTFebruaryTPITNoCost02012008’ report was posted February 29.  The 1999 – 2005 project information is posted separately as filename ‘ERCOTTPIT1999 – 2005’.  Both these files can be found in the Transmission Project & Information Tracking (TPIT) folder.

Texas Renewable Energy Credit Trading Program enhancements to the program software required by Senate Bill 20 have been successfully designed and implemented. Details are in the PUCT substantive rule 25.173 found at: http://www.puc.state.tx.us/rules/subrules/electric/index.cfm .  Enhancements include:

  - Increased targets for renewable energy in Texas to 5,000 MW by year 2015. This includes a target of 500 MW of non-wind renewables

  - Compliance premiums to incent non-wind development

  - Redefined REC Aggregators and their responsibilities

As a reminder, ALDR information was due to ERCOT by March 1, 2008. The final ALDR will be ready for SSWG by the end of March.