## 2009 Recommendations
MORO Merged 2009 Project Prioritization - PUCT, Market and ERCOT Projects
Source | Committee | Prog Area | Source Doc | Project | Project No. | Current Status | 2009 Priority | 2009 Rank | 2009 Budget Range | 2009 Running Range | Summary Description | Benefit Summary
Market | RMS | RO | SCR749 | MarkeTrak Enhancements (Workflow & Reporting) | 70007_01 | Planning | 0 - Previously Approved | 0.1 | <$100k |  | Planned Enhancements to the functionality of MarkeTrak | Reduce manual workarounds for efficient use of Retail Customer Choice resources, improve reporting capabilities, enhance workflows and improve validations for ERCOT and Market Participants.
ERCOT | MO | MO |  | ERCOT System Throughput for IDR (Advanced Metering) | 70057_01 | Planning | 0 - Previously Approved | 0.2 | <$100k |  | Planned: Provide incremental increases in IDR processing capability for ERCOT systems.
ERCOT | RO | RO |  | Data Research and Reporting (formerly ETS Transition to EDW) | 50088_01 | Planning | 0 - Previously Approved | 0.3 | <$100k |  | Planned: Transition of ETS reporting from Data Archive to Enterprise Data Warehouse | Improved reporting and analysis efficiency (7 hours per workday); Improved development efficiencies (16 hours per workday)
ERCOT | RO | RO |  | EDW EAI Transition (inc. PaperFree & NAESB) | 50061_01 | On Hold | 0 - Previously Approved | 0.4 | $100k-$250k |  | Transition of EAI reporting from Data Archive to Enterprise Data Warehouse | Fewer ad hoc data requests (4 hours per workday), less production support of data archive (4 hours per workday), improved daily research of Siebel service order changes (8 hours per workday)
Market Legislature | RMS | RO | HS | Small Renewables/Distributed Generation - RMWG | 80028_01 | Not started | 0 - Previously Approved | 0.5 | $250k-$500k
Market | RMS | RO |  | Advanced Metering - RMWG/TX SET | 80027_01 | Not started | 0 - Previously Approved | 0.6 | $250k-$500k
ABOVE THIS LINE --Projects expected to carry over from 2008
ERCOT/Market | PUCT |  |  | Advance Metering Infrastructure | new | Not started | 1 - Critical | 1 | $3M-5M |  | This project will begin implementation of the solution agreed upon as part of the Longer Term Conceptual Designeffort of 70057_01
Market | COPS | MO | PRR478 PR385 | Use of Lagged Dynamic Samples for New Load Profiles & DLC Implementation / Demand Response for Settlement | 40056_01 | Not started | 1 - Critical | 2 | $500k-$750k |  | This is a change to the method for creating Load Profiles allowing for the use of lagged dynamic samples for new profiles adopted subsequent to market open.
ERCOT | MO | MO |  | Verifiable Cost Automation | New | Not started | 1 - Critical | 3 | $100k-$250k |  | Enhancements to automate Verifiable cost submission in Siebel. Automation functionality is not directly in the protocols and the automation would be a nice to have after Go Live
ERCOT | MO | MO |  | Web-enabled Registration | New | Not started | 1 - Critical | 4 | $100k-$250k |  | Web-enabling registration forms (including RARF, NOI, interconnect, etc.) - total of around 50 forms. Nodal Go-live manual process.
ERCOT | MO | MO |  | MPIM integration with Siebel | New | Not started | 1 - Critical | 5 | $100k-$250k |  | Eliminate manual workaround and dual entry (2009 deferral necessary due to Siebel freeze)
ERCOT | MO | RO |  | TML Transition to MIS | New | Not started | 1 - Critical | 6 | $250k-$500k |  | Migration from TML to MIS of functions that support the Retail market and/or Zonal-related reporting that will continue past Nodal Go-Live. The item is not included in the approved MIS requirements. Both the Retail Market Subcommittee and ERCOT business reps have requested holding off on this effort for at least 6 months after Nodal Go-live
ERCOT | MO | MO |  | Nodal.ercot.com Retirement | New | Not started | 1 - Critical | 7 | $250k-$500k |  | Migration of content from nodal.ercot.com website to ERCOT.com website; retirement of nodal.ercot.com website.
Market | COPS | MO |  | API for Disputes | New | Not started | 1 - Critical | 8 | $250k-$500k |  | MPs (from COPs) have requested that ERCOT create an API to programmatically submit disputes. The API would interface with Siebel and would be created in the integration layer.
ERCOT | TPTF | MO |  | Additional Post-Nodal Efforts | New | Not started | 1 - Critical | 9 | TBD |  | Additional post-nodal efforts - not yet defined
ERCOT | MO | MO |  | COMS Extract, Report & Web Services Monitoring & Usage Statistics | 80032_01 | Not started | 2 - High | 10 | $250k-$500k |  | Provide research capabilities for Commercial Operations extract, report and web services data for internal business users, which include monitoring functionality and usage analysis capabilities.
ERCOT | RO | RO |  | Exception Reporting / Monitoring Enhancements | 70008_01 | Not started | 2 - High | 11 | $500k-$750k |  | Automate current exception reporting to monitor protocol compliance for processing exceptions. Create new exception reports using new data available from RBP and/or EDW projects. | Exception reporting in Retail Customer Choice has been very manual. There are protocol requirements that may not be met due to the lack of logging after the processing occurs.
ERCOT | RO | RO |  | Systematic Exception Reprocessing Functionality | 70009_01 | Not started | 2 - High | 12 | $250k-$500k |  | Automate current exception processing to meet protocol. Create reporting features after processing occurs. | Exception processing in Retail Customer Choice has been very manual. There are protocol requirements that may not be met due to the manual efforts.
ERCOT | RO | RO |  | EDW EAI Transition (inc. PaperFree & NAESB) | 50061_02 | Not started | 2 - High | 13 | $100k-$250k
ERCOT | RO | RO |  | EDI Transaction logging | 60062_01 | Not started | 2 - High | 14 | $100k-$250k |  | Change the Paper Free application system to log all ANSI records to TRLOG and to log all TXSET records to a new table which will better support current and future business needs. | Improve performance and accessibility of data. The suggested changes in the logging details will allow users to access the data without needing a cross-reference sheet telling them what the columns are in TRLOG and what data (per transaction type) is be
ERCOT | RO | RO |  | 814 inbound XML rewrite (impacts input from portal only) | 60043_01 | Not started | 2 - High | 15 | $100k-$250k |  | Re-Write of Inbound 814 XML maps to Increase Efficiency, Reliability and Stability of ERCOT transaction data processing. | Our experience with splitting the inbound 814 X12 maps has shown that reducing the complexity of the map (by implementing clean flowing logic) can reap significant performance gains. The time to analyze and correct any logic errors has been decreased by
ERCOT | RO | RO |  | Commercial Apps - Calendar Consolidation | 60033_01 | Not started | 2 - High | 16 | $250k-$500k |  | Develop single business calendar for use by all retail applications | Reduced rework for both market and ERCOT by eliminating possibility of out of sync conditions between multiple business calendars (50 hours per year of data repair activity for CRs and TDSPs)
ERCOT | RO | RO |  | Name to DUNS conversion | 60059_01 | Not started | 2 - High | 17 | $100k-$250k |  | Change the Paper Free application system to utilize DUNS numbers as opposed to Market Participant company names. | Consistent naming standards within Paperfree system.
ERCOT | RO | RO |  | MP configuration Table | 60060_01 | Not started | 2 - High | 18 | $100k-$250k |  | Remove all of the MPDB.conf files in the MB/PF systems and consolidate all of the configurations into a single table. The complexity of adding new MP to the system must be reduced in order to remove the number of errors that are encountered when adding / | The complexity of adding new MP to the system must be reduced in order to remove the number of errors that are encountered when adding / modifying MP information.
ERCOT | RO | RO |  | MarkeTrak Phase 3 | 80030_01 | Not started | 2 - High | 19 | $100k-$250k
ERCOT | RO | RO |  | Retail Application Upgrades | 80031_01 | Not started | 2 - High | 20 | $1M
ERCOT | RO | RO |  | Enrollment Postcard Notification Process | 80029_01 | Not started | 2 - High | 21 | $100k-$250k