## MO 2008 Recommendations
MORO Merged 2008 Project Prioritization - PUCT, Market and ERCOT Projects
Source | Committee | Prog Area | Source Doc | Project | Project No. | Current Status | 2008 Priority | 2008 Rank | 2008 Budget Range | 2008 Running Range | Comments | Project Description | CBA Score | Net Benefit | Benefit Summary
ERCOT | MO | MO |  | Maestro Replacement - Phase 2 | 50137_02 | Closing | 0 - Previously Approved | 0.5 | <$10k | $1M-$2M | Unplanned Carryover Reason: Closing Phase ONLY Go-Live Completed: 12/14/2007 | This project will replace ERCOT’s current batch job scheduling software. The current scheduling software, Maestro, experiences issues outlined below: • Maestro is currently not supported – Major upgrade required • Maintenance cost expensive due to CPU Pr | 1.95 | 380296 | Able to upgrade database on job scheduling server; Able to upgrade server operating system on job scheduling server; Allows schedule/job changes at any time
ERCOT | MO | MO |  | ERCOT.com Registered Access | 60077_01 | Execution | 0 - Previously Approved | 0.7 | <$100k | $1M-$2M | Unplanned Carry Over Reasons: Dependency on Nodal for Google search engine adevelopment Go-Live Forecast: Q108 | This project will enhance the Operations and System Planning Data section on the ERCOT website by changing the look and feel of the section to match the ERCOT website, improve navigation and bring the security aspects into compliance. | 18 | 950746 | Better outward communications improves ERCOT relationship with market participants; clarity, consistency of website content improves overall user experience; website response to market and business needs/changes signal ERCOT overall
ERCOT | MO | MO |  | COGNOS Infrastructure (aka Enhancements to SCR727 - Ph2) | 50024_02 | Execution | 0 - Previously Approved | 0.8 | <$100k | $1M-$2M | Unplanned Carry Over Nodal Impacts: Resources - Carry over due to extended stabilization of COGNOS Reports Go-Live Completed: 11/03/2007 | Subproject to provide market-requested enhancements to SCR727 data extract | 15 | 3500000 | Currently, CRs do not receive usage rows from backdated LSE changes that add the CR as REP of Record. The modifications requested in SCR740 as detailed in the "Business Objectives" section below will facilitate an enhanced supply / reporting capability of ESIID-level data to market participants for improved auditing capabilities.
ERCOT | MO | MO |  | Collage Infrastructure Redesign | 70038_01 | Execution | 0 - Previously Approved | 0.9 | $100k-$250k | $1M-$2M | Planned Carry Over Go-Live Forecasted: 02/15/2008 | Software that supports ERCOT.com deployments is taking too long to run through its process each night. This puts us at risk of not having current information on the website. | 2.5 | 600000 | Communication with the Market; Accuracy and timeliness of information; ERCOT's overall responsivness to the Market; ERCOT's reputation; Success of Transition to the Nodal Market; Compliance with PUCT and Protocols
ERCOT | MO | MO |  | MV90xi System Upgrade Project | 70048_01 | Execution | 0 - Previously Approved | 0.91 | <$10k | $1M-$2M | Unplanned Carry Over Reasons: Build out of iTest delayed due to resource constraints with AIX and Nodal efforts. Go-Live Forecasted: 03/28/2008 | Perform replacement of non-standard hardware and upgrade of software for ERCOT’s MV90xi system. | 0 | -130000 | Align current HW environment with ERCOT standard IT policies; Ensure software compliance with vendor (Itron), and maintain future application support; Additional application functionality allowing for Market Participants to utilize latest metering technologies
ERCOT | MO | MO |  | Lodestar Upgrade | 40066_04 | Planning | 0 - Previously Approved | 0.92 | $250k-$500k | $1M-$2M | Planned Carry Over Nodal Impacts: Nodal Dendency on upgrade Go-Live Forecasted: Early Q208 | Maintain efficiency, and reliability of the LodeStar application to enable ERCOT to meet Energy Aggregation and Billing & Settlements business needs | 19 | 26444 | Batch performance improvements expected (perhaps up to 25%)
ERCOT | MO | MO |  | ERCOT System Throughput for IDR (Advanced Metering) | 70057_01 | Planning | 0 - Previously Approved | 0.96 | $100k-$250k | $2M-$3M | Planned for 2008 (Initiated early in 2007) Go-Live Forecasted: Q408 | This project involves the analysis and implementation of the current retail and wholesale systems to determine possible enhancements that could result in increases to the volume of IDR. Extracts and ODS analysis will be included in the analysis effort. Short-term effort for any configuration scaling will be delivered in 2008 and a Conceptual Design for Long-term solution will be provided with this project as well. | 0 | -500000 | The project improves the efficiency of ERCOT retail transaction systems. It provides incremental increases in IDR processing capability for ERCOT systems. Support market's transition to demand response-type programs.
ABOVE THIS LINE --Projects carry over from 2007
Below THIS LINE --Projects deferred to 2009 or cancelled
Market | COPS | MO | PRR478 PR385 | Use of Lagged Dynamic Samples for New Load Profiles & DLC Implementation / Demand Response for Settlement | 40056_01 | Deferred | N/A |  |  |  | Short term solution will be done in 2008 outside project process. Long term to be deferred to 2009 Due to Nodal based on COPS Consensus Discussion | This is a change to the method for creating Load Profiles allowing for the use of lagged dynamic samples for new profiles adopted subsequent to market open. |  |  | 1.The time lag between approving a new profile and being able to settle ESI IDs using the new profile will be reduced. 2. New profiles are expected to be subject to significant population change as new ESI IDs are identified for inclusion in the profile; lagged-dynamic samples will accommodate these changes more quickly, accurately and efficiently than is possible with adjusted static models. 3. Use of lagged dynamic samples will allow the market to audit ESI IDs being assigned to new profiles and will create an incentive for CRs using the profile to limit the inclusion of ESI IDs to those appropriate to the profile.
ERCOT | MO | MO |  | COMS Extract, Report & Web Services Monitoring & Usage Statistics | 80032_01 | Deferred | N/A |  |  |  | Resource and Environment constraint in 2008 | Provide research capabilities for Commercial Operations extract, report and web services data for internal business users, which include monitoring functionality and usage analysis capabilities. | 5.24 | 2185793 | Will create an infrastructure to allow access to broader information from ERCOT systems to our customers; Utilizing the standard EIS Business Intelligence layer, this offering will work to align our reporting capabilities and help to eliminate future fragmented solutions; Removal of manual processes and their inherent risks of dependency on skilled resources; Information security is guaranteed via automation methods; Information may be accessible in ways not currently available. Uses will have abilities to access and format data as needed, without the need of development resources
[7 empty] | MO 2008 Projected Spend |  | $613K
[7 empty] | MO 2008 Approved Funding |  | $1.2M
[8 empty] | MO Variance | 587K