## 2009 Recommendations
MO 2009 Project Prioritization - PUCT, Market and ERCOT Projects
Source | Committee | Prog Area | Source Doc | Project | Project No. | Current Status | Project Manager | 2009 Priority | 2009 Rank | 2009 Budget Range | 2009 Running Range | Summary Description | CBA Score (avail for those prior to 2008) | Net Benefit | Benefit Summary
ERCOT | MO | MO | PUCT 34610 | ERCOT System Throughput for IDR (Advanced Metering) | 70057_01 | Planning | H. Day | 0 - Previously Approved | 0.1 | <$100k | <$1M | Planned carry over for closing: Provide incremental increases in IDR processing capability for ERCOT systems. | 0 | -500000 | The project improves the efficiency of ERCOT retail transaction systems. It provides incremental increases in IDR processing capability for ERCOT systems. Support market's transition to demand response-type programs.
ABOVE THIS LINE --Projects expected to carry over from 2008
Market | COPS | MO | PRR478 PR385 | Use of Lagged Dynamic Samples for New Load Profiles & DLC Implementation / Demand Response for Settlement | 40056_01 | Not started | 2 - High | 1 - Critical | 1 | $500k-$750k | $500k-$1M | This is a change to the method for creating Load Profiles allowing for the use of lagged dynamic samples for new profiles adopted subsequent to market open. | 0 | TBD | 1.The time lag between approving a new profile and being able to settle ESI IDs using the new profile will be reduced. 2. New profiles are expected to be subject to significant population change as new ESI IDs are identified for inclusion in the profile; lagged-dynamic samples will accommodate these changes more quickly, accurately and efficiently than is possible with adjusted static models. 3. Use of lagged dynamic samples will allow the market to audit ESI IDs being assigned to new profiles and will create an incentive for CRs using the profile to limit the inclusion of ESI IDs to those appropriate to the profile.
Market/ERCOT | TPTF | MO | NPR 5&12 | Verifiable Cost Management System | New | Not started |  | 2 - High | 2 | $100k-$250k | $500k-$1M | Creation of the Verifiable Cost Management System (VCMS), the interface QSEs will use for submitting and tracking their verifiable costs requested by TPTF. | 0 | TBD | The VCMS will satisfy ERCOT’s needs for managing (submission, receipt, storage, and tracking) VC submissions and their related documentation. Reduce manual efforts for processing and monitoring verifiable cost.
Market/ERCOT | TPTF | MO |  | Web-enabled Registration | New | Not started |  | 2 - High | 3 | $100k-$250k | $500k-$1M | Create an Interface and provide web-enabling registration forms (including RARF, NOI, interconnect, etc.) - total of around 50 forms. Nodal Go-live manual process. | 0 | TBD | Reduce manual efforts for processing and monitoring web-enabling registration forms.
ERCOT | MO | MO |  | MPIM integration with Siebel | New | Not started |  | 2 - High | 4 | $100k-$250k | $500k-$1M | Eliminate manual workaround and dual entry (2009 deferral necessary due to Siebel freeze) | 0 | TBD | Reduce manual efforts.
ERCOT | MO | MO |  | Nodal.ercot.com Retirement | New | Not started |  | 2 - High | 5 | $250k-$500k | $1M-$2M | Migration of content from nodal.ercot.com website to ERCOT.com website; retirement of nodal.ercot.com website. | 0 | TBD | Anticipated efficiencies from maintaining a single repository system.
Market | COPS | MO |  | API for Disputes | New | Not started |  | 2 - High | 6 | $500k-$1M | $1M-$2M | MPs (from COPs) have requested that ERCOT create an API to programmatically submit disputes. The API would interface with Siebel and would be created in the integration layer. | 0 | TBD | TBD
ERCOT | TPTF | MO |  | NPRRs and Mandates | New | Not started |  | 2 - High | 7 | $2M-$3M | $3M-$4M | Additional post-nodal efforts - not yet defined and not covered under stabilization or operating and Maintenance. | 0 | TBD | TBD
ERCOT | MO | MO |  | COMS Extract, Report & Web Services Monitoring & Usage Statistics | 80032_01 | Not started |  | 2 - High | 8 | $250k-$500k | $4M-$5M | Provide research capabilities for Commercial Operations extract, report and web services data for internal business users, which include monitoring functionality and usage analysis capabilities. | 0 | TBD | Will create an infrastructure to allow access to broader information from ERCOT systems to our customers; Utilizing the standard EIS Business Intelligence layer, this offering will work to align our reporting capabilities and help to eliminate future fragmented solutions; Removal of manual processes and their inherent risks of dependency on skilled resources; Information security is guaranteed via automation methods; Information may be accessible in ways not currently available. Uses will have abilities to access and format data as needed, without the need of development resources
[8 empty] | 2009 Forecast: |  | $4.3M