## MORO 2008 Recommendations
MORO Merged 2008 Project Prioritization - PUCT, Market and ERCOT Projects
Source | Committee | Prog Area | Source Doc | Project | Project No. | Current Status | 2008 Priority | 2008 Rank | 2008 Budget Range | 2008 Running Range | Comments | Project Description | CBA Score | Net Benefit | Benefit Summary
PUCT/MKT | RMS | RO | PRR672 PRR707 PUCT Project 33049 | Terms and Conditions requirements, not limited to Texas SET changes, Performance Measures | 60008_01 | Planning | 0 - Previously Approved | 0.1 | $250k-$500k | $250k-$500k | Planned Carry over Reasons: Nodal Impacts: Test Environment planning around schedule Go-Live Forecast: Scheduled 05/10/2008 | This project to address transaction timing and prioritization changes identified with PRR672 and PRR707 as well as PUCT Project 33049 for Additions to the Performance Measures reporting. | 4.3 | 5000000 | Terms & Conditions Task Force reached consensus that these changes were needed to successfully implement PUCT Project 29637. The PUCT requires implementation by 7/1/2007. Consumers will be able to rely on standard Move In and pay $10 rather than $89 for Priority Move Ins. Will allow ERCOT to expedite the processing of orders as prioritized by the Market and to comply with Section 39.151 of PURA, which states that one of the primary functions of an ISO is to "ensure that information relating to a customer's choice of retail electric provider is conveyed in a timely manner to the persons who need that information." Will allow CRs to provide customers with a more accurate estimate for completion of services. Reduce the number of MarkeTrak issues requiring ERCOT's intervention. Provides the TDSP with as much time as possible to more accurately schedule and manage daily workload. Will allow Consumers to get their service on as quickly as possible.
PUCT | RMS | RO | PUCT Project 24462 | Performance Measures Reporting Requirements (changes to Project 24462) | 60007_01 | Cancelled | 0 - Previously Approved | 0.15 | 0 | $500k-$1M | Project Cancelled Project Scope moved to PR60008 |  | NA | NA | NA
Market | RMS | RO | SCR745 | ERCOT Outage Evaluation and Resolution (TDTWG)--Phases I and II | 60006_01 | Execution | 0 - Previously Approved | 0.2 | <$100k | $250k-$500k | Unplanned Carry Over Reasons: Issues discovered in test with SAN Fencing, transaction integration, and low availability from HP Support causing delays in resolution of issues to complete testing in 2007. Go-Live Forecast: Rescheduled 03/08/2008 | Identify market facing servers without redundancy. Implement new code and hardware when possible to eliminate single points of failure. This will include clustering market facing servers and implementing code which will be able to switch from one system | 24 | -1500000 | Customer service benefit / reduced call volume / reduced complaints; Increased confidence in ERCOT's system reliability; Positive impact on MP cash flow; Protocol timing compliance improvement capability; Reduced number of emergency outages; Hardware maintenance can occur without requiring a market outage
Market | RMS | RO | SCR749 | MarkeTrak Enhancements (Workflow & Reporting) | 70007_01 | Planning | 0 - Previously Approved | 0.3 | $1M-$2M | $1M-$2M | Planned Carry over Reasons: Execution not starting until 2008. Nodal Impacts: Environment (Siebel Nodal Code Freeze) Go-Live Forecast: Scheduled thru 2008 | Enhancements to the functionality of MarkeTrak requested under SCR749 | 1.8 | 740000
Market | RMS | RO | SCR748 | Website Enhancements for ERCOT Outages | 70006_01 | Closing | 0 - Previously Approved | 0.4 | <$10k | $1M-$2M | Unplanned Carryover Reasons: Closing Phase ONLY Go-Live Completed: 11/22/2007 | To add functionality on the ERCOT website for: • Calendar of dates/times for planned outages affecting retail. • Unplanned Outage Alert with web message capability • Log of outages | 10 | 3466866.6147
ERCOT | MO | MO |  | Maestro Replacement - Phase 2 | 50137_02 | Closing | 0 - Previously Approved | 0.5 | <$10k | $1M-$2M | Unplanned Carryover Reason: Closing Phase ONLY Go-Live Completed: 12/14/2007 | This project will replace ERCOT’s current batch job scheduling software. The current scheduling software, Maestro, experiences issues outlined below: • Maestro is currently not supported – Major upgrade required • Maintenance cost expensive due to CPU Pr | 1.95 | 380296 | Able to upgrade database on job scheduling server; Able to upgrade server operating system on job scheduling server; Allows schedule/job changes at any time
ERCOT | RO | RO |  | MO SAS 70 Procedures Optimization (fka EIS Siebel to Lodestar Comparison | 70005_01 | Execution | 0 - Previously Approved | 0.6 | $250k-$500k | $1M-$2M | Unplanned Carry Over Reasons: Delays in receiving hardware and software in 11/2007 Go-Live Forecast: 02/15/2008 | This project will implement hardware, software and licenses that are needed to implement the SAS 70 procedures optimization tool (System Audit Standards) this will lay the foundation to create an improved processes to perform retail data comparisons (ie. Siebel to Lodestar). | 2.3 | 390000
ERCOT | MO | MO |  | ERCOT.com Registered Access | 60077_01 | Execution | 0 - Previously Approved | 0.7 | <$100k | $1M-$2M | Unplanned Carry Over Reasons: Dependency on Nodal for Google search engine adevelopment Go-Live Forecast: Q108 | This project will enhance the Operations and System Planning Data section on the ERCOT website by changing the look and feel of the section to match the ERCOT website, improve navigation and bring the security aspects into compliance. | 18 | 950746 | Better outward communications improves ERCOT relationship with market participants; clarity, consistency of website content improves overall user experience; website response to market and business needs/changes signal ERCOT overall
ERCOT | MO | MO |  | COGNOS Infrastructure (aka Enhancements to SCR727 - Ph2) | 50024_02 | Execution | 0 - Previously Approved | 0.8 | <$100k | $1M-$2M | Unplanned Carry Over Nodal Impacts: Resources - Carry over due to extended stabilization of COGNOS Reports Go-Live Completed: 11/03/2007 | This project will implement hardware, software, and transition of COGNOS reports from verson 1.1 to 8.1. Brings version into compliance and provides application clustering for redundancy. | 15 | 3500000 | Currently, CRs do not receive usage rows from backdated LSE changes that add the CR as REP of Record. The modifications requested in SCR740 as detailed in the "Business Objectives" section below will facilitate an enhanced supply / reporting capability of ESIID-level data to market participants for improved auditing capabilities.
ERCOT | MO | MO |  | Collage Infrastructure Redesign | 70038_01 | Execution | 0 - Previously Approved | 0.9 | $100k-$250k | $1M-$2M | Planned Carry Over Go-Live Forecasted: 02/15/2008 | Software that supports ERCOT.com deployments is taking too long to run through its process each night. This puts us at risk of not having current information on the website. | 2.5 | 600000 | Communication with the Market; Accuracy and timeliness of information; ERCOT's overall responsivness to the Market; ERCOT's reputation; Success of Transition to the Nodal Market; Compliance with PUCT and Protocols
ERCOT | MO | MO |  | MV90xi System Upgrade Project | 70048_01 | Execution | 0 - Previously Approved | 0.91 | <$10k | $1M-$2M | Unplanned Carry Over Reasons: Build out of iTest delayed due to resource constraints with AIX and Nodal efforts. Go-Live Forecasted: 03/28/2008 | Perform replacement of non-standard hardware and upgrade of software for ERCOT’s MV90xi system. | 0 | -130000 | Align current HW environment with ERCOT standard IT policies; Ensure software compliance with vendor (Itron), and maintain future application support; Additional application functionality allowing for Market Participants to utilize latest metering technologies
ERCOT | MO | MO |  | Lodestar Upgrade | 40066_04 | Planning | 0 - Previously Approved | 0.92 | $250k-$500k | $1M-$2M | Planned Carry Over Nodal Impacts: Nodal Dendency on upgrade Go-Live Forecasted: Early Q208 | Maintain efficiency, and reliability of the LodeStar application to enable ERCOT to meet Energy Aggregation and Billing & Settlements business needs | 19 | 26444 | Batch performance improvements expected (perhaps up to 25%)
ERCOT | RO | RO |  | Registration Data Model Enhancement (formerly ESIID Account Table Split) | 60015_01 | Planning | 0 - Previously Approved | 0.93 | $1M-$2M | $1M-$2M | Unplanned Carry Over Reasons: Delays due to Procurement negotiations of Vendor Contracts with Oracle Go-Live Forecasted: Q108 (Data Model Assessment ONLY) | Normalize type of data associated to business objects. Multiple business objects are using the same tables which are growing large causing performance and scalability issues. | 6.5 | 930000 | Faster integration; Better performance; Easier maintenance; Vendor supporability
ERCOT | MO | MO |  | ERCOT System Throughput for IDR (Advanced Metering) | 70057_01 | Planning | 0 - Previously Approved | 0.96 | $100k-$250k | $2M-$3M | Planned for 2008 (Initiated early in 2007) Go-Live Forecasted: Q408 | This project involves the analysis and implementation of the current retail and wholesale systems to determine possible enhancements that could result in increases to the volume of IDR. Extracts and ODS analysis will be included in the analysis effort. Short-term effort for any configuration scaling will be delivered in 2008 and a Conceptual Design for Long-term solution will be provided with this project as well. | 0 | -500000 | The project improves the efficiency of ERCOT retail transaction systems. It provides incremental increases in IDR processing capability for ERCOT systems. Support market's transition to demand response-type programs.
ERCOT | RO | RO |  | Data Research and Reporting (formerly ETS Transition to EDW) | 50088_01 | Planning | 0 - Previously Approved | 0.97 | $500k-$1M | $2M-$3M | Planned Carry Over Reasons: Delays due to resource constraints from AIX and Nodal EDW efforts Go-Live Forecasted: 2009 | Deliver a data research and reporting tool for ERCOT Commercial Operations. The project will provide accurate, complete, and efficient reporting and research capabilities of retail transaction data. | 2.5 | 1200000 | Reliability - utilizing the standard EIS Business Intelligence layer, this offering will work to align our reporting capabilities and help to eliminate future fragmented solutions. Data Management - Timely report delivery. Data Management - Reliable and accurate reports. Data Management - Timely exception identification. Flexibility - Information may be accessible in ways not currently available. Users will have ability to access and format data as needed, without the need of development resources. Standard integration - Integrates with Enterprise information delivery strategic initiatives. Maintenance Costs - Maintenance of database servers - could move to an existing machine. Partition strategy. Performance of reporting. Real-time reporting instead of batch . .
ERCOT | RO | RO |  | EDW EAI Transition (inc. PaperFree & NAESB) | 50061_01 | On Hold | 0 - Previously Approved | 0.98 | <$100k | $2M-$3M | Planned Carry Over Reasons: Currently "ON HOLD" Status due to resource and enviornment constraints with AIX ODS implementation Go-Live Forecast: TBD until comes "Off Hold" | This project will transition of Paperfree and NAESB Data to the Operational Data Store (ODS), configure replication tool for these databases as well, and build COGNOS subject Area views for reporting. | 3.3 | 700000 | Reliability - Utilizing the standard EIS Business Intelligence layer, this offering will work to align our reporting capabilities and help to eliminate future fragmented solutions. Automation - Removal of manual processes and their inherent risks of dependency of skilled resources. Security - Information security is guaranteed via automation methods. Flexibility - Information may be accessible in ways not currently available. Users will have ability to access and format data as needed, without the need of development resources. Standard Integration - Integrates with Enterprise information delivery strategic initiatives
ABOVE THIS LINE --Projects carry over from 2007
Market / Legislature | RMS | RO | HB3693 | Small Renewables - RMWG | 80028_01 | Not Started - 2008 | 1 - Critical | 1 | <$500k | $3M-$4M |  | This project recognizes any settlement-type effort needed for the distributed generation/small renewables project.
Market | RMS | RO |  | Advanced Metering - TX SET Changes | 80027_01 | Not Started - 2008 | 1 - Critical | 2 | <$500k | $4M-$5M | Placeholder awaiting TX SET required changes | This project to address any TX SET changes resulting from Advanced Metering
ERCOT | RO | RO |  | Website Enhancements for ERCOT Outages Ph II | 70006_02 | Not Started - 2008 | 3 - High / Medium | 3 | $250k-$500k | $4M-$5M | Dependent on IO PR60055 Enterprise Service Management Tool (Remedy) and Openview Monitoring tools delivered under Nodal. | ERCOT requested enhancements to automate the email notification and the helpdesk alert. | 0.1 | -400000 | This project will reduce the number of manual steps required to post Outage alerts on ERCOT.com; This project will reduce the time required to post Outage alerts on ERCOT.com
ABOVE THIS LINE --Projects for 2008: Below this line are Projects deferred to 2009 or cancelled
Market | COPS | MO | PRR478 PR385 | Use of Lagged Dynamic Samples for New Load Profiles & DLC Implementation / Demand Response for Settlement | 40056_01 | Deferred | 2 - High |  | $500k-$750k |  | Short term solution will be done in 2008 outside project process. Long term to be deferred to 2009 Due to Nodal based on COPS Consensus Discussion | This is a change to the method for creating Load Profiles allowing for the use of lagged dynamic samples for new profiles adopted subsequent to market open. |  |  | 1.The time lag between approving a new profile and being able to settle ESI IDs using the new profile will be reduced. 2. New profiles are expected to be subject to significant population change as new ESI IDs are identified for inclusion in the profile; lagged-dynamic samples will accommodate these changes more quickly, accurately and efficiently than is possible with adjusted static models. 3. Use of lagged dynamic samples will allow the market to audit ESI IDs being assigned to new profiles and will create an incentive for CRs using the profile to limit the inclusion of ESI IDs to those appropriate to the profile.
ERCOT | MO | MO |  | COMS Extract, Report & Web Services Monitoring & Usage Statistics | 80032_01 | Deferred | 9 - Parking Lot |  | $250k-$500k |  | Resource and Environment constraint in 2008 | Provide research capabilities for Commercial Operations extract, report and web services data for internal business users, which include monitoring functionality and usage analysis capabilities. | 5.24 | 2185793 | Will create an infrastructure to allow access to broader information from ERCOT systems to our customers; Utilizing the standard EIS Business Intelligence layer, this offering will work to align our reporting capabilities and help to eliminate future fragmented solutions; Removal of manual processes and their inherent risks of dependency on skilled resources; Information security is guaranteed via automation methods; Information may be accessible in ways not currently available. Uses will have abilities to access and format data as needed, without the need of development resources
ERCOT | RO | RO |  | Exception Reporting / Monitoring Enhancements | 70008_01 | Deferred | 9 - Parking Lot |  | $250k-$500k |  | Resource and Environment constraint in 2008 | Automate current exception reporting to monitor protocol compliance for processing exceptions. Create new exception reports using new data available from RBP and/or EDW projects. | 2.2 | 400000
ERCOT | RO | RO |  | Systematic Exception Reprocessing Functionality | 70009_01 | Deferred | 9 - Parking Lot |  | $250k-$500k |  | Resource and Environment constraint in 2008 | Automate current exception processing to meet protocol. Create reporting features after processing occurs. | 1.1 | 40000 | Reduce the number of transactions that fail to meet protocol timings.
ERCOT | RO | RO |  | EDW EAI Transition (inc. PaperFree & NAESB) | 50061_02 | Deferred | 9 - Parking Lot |  | $100k-$250k |  | Resource and Environment constraint in 2008 | This project will configure the 997 and Load Loss reports to pull from the NAESB/PFREE ODS rather than the source database. | 23 | 856900.2309 | Utilizing the standard EIS Business Intelligence layer, this offering will work to align our reporting capabilities and help to eliminate future fragmented solutions; Removal of manual processes and their inherent risks of dependency on skilled resources; Information security is guaranteed via automation methods; Information may be accessible in ways not currently available. Uses will have abilities to access and format data as needed, without the need of development resources; Integrates with Enterprise information delivery strategic initiatives
ERCOT | RO | RO |  | EDI Transaction logging | 60062_01 | Deferred | 9 - Parking Lot |  | $100k-$250k |  | Resource and Environment constraint in 2008 | Change the Paper Free application system to log all ANSI records to TRLOG and to log all TXSET records to a new table which will better support current and future business needs. | 1.3 | 70000 | Requirements for new data elements can be easily deployed; Current EDI 997 performance would be improved due to the reduction of noise data; Data tracking would be enhanced
ERCOT | RO | RO |  | 814 inbound XML rewrite (impacts input from portal only) | 60043_01 | Deferred | 9 - Parking Lot |  | $100k-$250k |  | Resource and Environment constraint in 2008 | Re-Write of Inbound 814 XML maps to Increase Efficiency, Reliability and Stability of ERCOT transaction data processing. | 3.6 | 440000 | Some transaction sets are currently not maintainable via this mapping
ERCOT | RO | RO |  | Commercial Apps - Calendar Consolidation | 60033_01 | Deferred | 9 - Parking Lot |  | $250k-$500k |  | Resource and Environment constraint in 2008 | Develop single business calendar for use by all retail applications | 3.1 | 740000 | Using one consisten calendar; Reduction in data repair due to out of sync calendar would improve reputation; Best practice; Supports SOA architecture; TCR program when calendar problems occurred, MP paid invoices late, incurred late fees
ERCOT | RO | RO |  | Name to DUNS conversion | 60059_01 | Deferred | 9 - Parking Lot |  | $100k-$250k |  | Resource and Environment constraint in 2008 | Change the Paper Free application system to utilize DUNS numbers as opposed to Market Participant company names. | 3.6 | 440000 | None listed
ERCOT | RO | RO |  | MP configuration Table | 60060_01 | Deferred | 9 - Parking Lot |  | $100k-$250k |  | Resource and Environment constraint in 2008 | Remove all of the MPDB.conf files in the MB/PF systems and consolidate all of the configurations into a single table. The complexity of adding new MP to the system must be reduced in order to remove the number of errors that are encountered when adding / | 1 | 0 | Reduce implementation errors, increase accuracy; Reduce time to implement new trading partner; Add Operations flexibility; Add Operations visibility
ERCOT | RO | RO |  | MarkeTrak Phase 3 | 80030_01 | Deferred | 9 - Parking Lot |  | $100k-$250k |  | Dependent on MarkeTrak Phase 2 | ERCOT requested project to expand capabilities and efficiencies of the MarkeTrak Retail Issue Resolution System that are not currently part of MarkeTrak Phase 2. | 1.4 | 80000 | Implement Mass Update; Automate DEV LSE Siebel changes in MarkeTrak; Add MP ability to produce market wide metrics on issues without the ability to view issue details; Automate retrieval of relevant retial information from ERCOT systems to MarkeTrak for expedidition of issue resolution; Automate generation of ERCOT Initiated Issues for Siebel Exceptions; Upgrade Serena Team Track Application; Increase reporting metrics related to MarkeTrak SLA; Increase efficiencies of Workflows and Application Adapters
ERCOT | RO | RO |  | Retail Application Upgrades | 80031_01 | Deferred | 9 - Parking Lot |  | $1M |  | Resource and Environment constraint in 2008 | This project is necessary to allow ERCOT to plan and implement upgrades to systems not currently within another project on the PPL to maintain compliance. In addition, the impact analysis done during planning would provide risk management of other projects/releases. | None listed | None listed | Planned impact analysis, requirements, testing, and delivery to mitigate negative impacts to business processes
ERCOT | RO | RO |  | Enrollment Postcard Notification Process | 80029_01 | Deferred | 9 - Parking Lot |  | $100k-$250k |  | Resource and Environment constraint in 2008 | This is an enhancement to the method for generating Enrollment Postcard Notification and Customer Objection files processing within ERCOT (starting at the point of receiving file from vendor; stopping at the point of vendor pickup). | 0 | -100000 | Improved production support (including creation of a Service Level Agreement); Improved exception handling; Education of new team members; Improve Testing capabilities
Market | RMS | RO | SCR745 | ERCOT Outage Evaluation and Resolution (TDTWG)--Phase III | 60006_02 | Cancel?? |  |  |  |  | ERCOT recommends cancelling this project as the SCR scope to deliver high-availablilty database was addressed with AIX. | Deliver high available Database systems | NA | NA | This phase was to address Database availablilty specifically that are under infrastructure changes in the AIX Project Effort.
ERCOT | RO | RO |  | Create Retail XML Transaction Format to MPs - set the national standard | 60065_01 | Cancelled |  |  |  |  | ERCOT will cancel this project in next CART Voting Meeting due to limited drive and supporting information | Create a Market Standard XML with coordination with other industry standard groups. | NA | NA | ERCOT has cancelled this project i2/22 due to limited drive and supporting information
ERCOT | RO | RO |  | NAESB Failover - TDTWG | New | Pending Cancel |  |  |  |  | Pending confirmation for TDTWG, ERCOT will cancel this project in next CART Voting Meeting due to limited drive and supporting information. Have not seen any global events requiring a need for a 2nd protocol. | Create transport protocol failover for submission from ERCOT to Market Participants. Will require a defintion for transport SLA. | NA | NA | ERCOT will cancel this project in next CART Voting Meeting due to limited drive and supporting information. Have not seen any global events requiring a need for a 2nd protocol.
[7 empty] | Current Combined 08 Projected Spend: |  | $4.7M
[7 empty] | 2008 Combined 08 Variance: |  | $2.6M