| Proposed MarkeTrak Phase 2 Activity and Meeting Schedule 2008 |  |  |
| --- | --- | --- |
| Activity | Location | Calendar Date |
| MarkeTrak Taskforce Meeting: review proposed activity and meeting schedule, release buckets, review remaining D2D and DEV user guide sections | ERCOT – Room 168 | Feb 21, 2008 |
| 21 Day comment period for Users Guide begins |  | Mar 5, 2008 |
| MarkeTrak Taskforce Meeting: Conceptual Design Discussion, new reporting functionality, assign user guide to be updated for release 1 and 2 updates | ERCOT – Room 168 | Mar 6, 2008 |
| Script Sub Team review first draft of scripts | ERCOT – Room 211 | Mar 7, 2008 |
| Give MarkeTrak update at RMS | ERCOT | Mar 12, 2008 |
| Script Sub Team review second draft of scripts | CNP - Houston | Mar 14, 2008 |
| Script Sub Team review draft of scripts | CNP – Houston | Mar 17, 2008 |
| MarkeTrak Task Force Meeting Morning: review scripts, Initial Parms due for new reporting functionality Afternoon: Technical Review | TXUE Dallas | Mar 26, 2008 |
| 21 Day comment period for Users Guide ends |  | Mar 26, 2008 |
| Deadline for feedback for MarkeTrak test scripts |  | Mar 31, 2008 |
| Texas Test Plan Team Meeting to finalize scripts. MarkeTrak Task Force will be included in meeting. | ERCOT | March 31 |
| Market Notice for Workshop for Release 1 |  | Apr 4, 2008 |
| Notice from ERCOT Retail Client Services to notify market participants of MarkeTrak Testing for Retail Market Testing sent to ERCOT lists.ercot.com distribution |  | Apr 7, 2008 |
| Give MarkeTrak update at RMS | ERCOT | Apr 9, 2008 |
| MarkeTrak Task Force Meeting – Review User Guide sections | Austin – hotel by ERCOT | Apr 10, 2008 |
| Publish scripts to file cabinet, email out the scripts |  | Apr 10, 2008 |
| WSDL Release for 1 |  | April 28, 2008 |
| MarkeTrak Task Force Meeting – Review User Guide sections | ERCOT – Room 168 | Apr 29, 2008 |
| Deadline to sign up for voluntary GUI testing. All API will be mandatory. |  | May 1, 2008 |
| Reminder Market Notice for Workshop – Release 1 |  | May 2, 2008 |
| Training material sent and posted– Release 1 changes |  | May 2, 2008 |
| Communication from ERCOT Flight Administrator of testing participants to each TDSP and CR |  | May 7, 2008 |
| MarkeTrak Task Force Meeting – Review User Guide Sections | CNP - Houston | May 8, 2008 |
| MarkeTrak Task Force Meeting – Review User Guide Sections | CNP - Houston | May 9, 2008 |
| TDSPs communicate test beds for all releases to ERCOT and CRs. |  | May 14, 2008 |
| Give MarkeTrak update at RMS | ERCOT | May 14, 2008 |
| USA’s request digital certificates for testing – individuals and if you are using the API |  | No later than May 12 |
| Market Notice for Trainings for Release 2 |  | May 13, 2008 |
| MarkeTrak Training Workshop – includes items in Release 1 | ERCOT | May 16, 2008 |
| ERCOT – UAT |  | May 19 – Jun 6 2008 |
| Kick off of API connectivity and Sandbox – Release 1 |  | May 20, 2008 |
| MarkeTrak Task Force first draft of Users Guide | Austin – hotel near ERCOT | May 22, 2008 |
| WSDL Release for 2- A |  | June 2 |
| Technical Review Meeting for WSDL Release 2 – A | ERCOT – room 168 | June 5 |
| MarkeTrak Release 1 Production |  | June 14 |
| Reminder Market Notice for Trainings – Release 2 |  | June 10, 2008 |
| Training material sent and posted – Release 2 changes |  | June 10, 2008 |
| Give MarkeTrak update at RMS | ERCOT | June 11, 2008 |
| MarkeTrak Task Force finalize Users Guide and send to ERCOT | ERCOT Room 168 | Jun 12, 2008 |
| Sandbox loaded with data for Release 2 - A |  | Jun 20, 2008 |
| 21 Day comment period for Users Guide begins |  | Jun 19, 2008 |
| ERCOT – UAT section 1 of Release 2 - A |  | Jun 20 – Jul 7, 2008 |
| WSDL Release for 2- B |  | June 23 |
| Training – Release 2 CNP | Houston | Jun 24, 2008 |
| Training – Release 2 TXUE | Irving | Jun 26, 2008 |
| Training – Release 2 ERCOT | Austin | Jun 30, 2008 |
| Technical Review Meeting for WSDL Release 2 – B | ERCOT – room 168 | July 1, 2008 |
| Sandbox loaded with data for Release 2 - B |  | Jul 10, 2008 |
| Market Participants have Bulk Insert templates updated |  | July 9 |
| Give MarkeTrak update at RMS | ERCOT | July 9, 2008 |
| ERCOT – UAT section 2 of Release 2 - B |  | Jul 10 – Aug 1, 2008 |
| Market Participants test updated templates in sandbox |  | July 10 – July 28 |
| MarkeTrak Taskforce meeting to be determined |  | July |
| Sandbox closes |  | Jul 28, 2008 |
| Market CERT Test for Release 2 |  | Aug 4 – Aug 8, 2008 |
| Market Test – Contingency test period |  | Aug 8 – Aug 14, 2008 |
| Give MarkeTrak update at RMS | ERCOT | Aug 13, 2008 |
| Production – Release 2 |  | Aug 16, 2008 |
| Release 2 Stabilization Period |  | Aug 17 – Aug 31, 2008 |
| MarkeTrak Taskforce meeting |  | Aug 21, 2008 |
| Give MarkeTrak update at RMS | ERCOT | Sept 10, 2008 |
| MarkeTrak Taskforce meeting – Review User Guide changes |  | Sept 11, 2008 |
| Sandbox opens for Release 3 |  | Sept 22 |
| WSDL Release for 3 |  | Sept 22 |
| MarkeTrak Taskforce meeting – Review draft of User’s Guide |  | Sept 25, 2008 |
| MarkeTrak Task Force finalize Users Guide and send to ERCOT |  | Oct 9, 2008 |
| Market Notice for Workshop – Release 3 |  | Oct 10, 2008 |
| Sandbox loaded with data for Release 3 |  | Oct 13, 2008 |
| ERCOT – UAT Release 3 |  | Oct 13 – Nov 14, 2008 |
| Give MarkeTrak update at RMS | ERCOT | Oct 15, 2008 |
| 21 Day comment period for Users Guide begins |  | Oct 16, 2008 |
| Reminder Market Notice for Workshop – Release 3 |  | Nov 7, 2008 |
| Training material sent and posted– Release 3 changes |  | Nov 7, 2008 |
| Sandbox ends |  | Nov 10, 2008 |
| Give MarkeTrak update at RMS | ERCOT | Nov 12, 2008 |
| Market CERT Test for Release 3 |  | Nov 17 – Nov 21, 2008 |
| Training – MarkeTrak Workshop - includes items in Release 3 | ERCOT | Nov 21, 2008 |
| Market Test – Contingency test period for Release 3 |  | Nov 24 – Dec 3, 2008 |
| Production – Release 3 |  | Dec 6, 2008 |
| Release 3 stabilization Period |  | Dec 6 – Jan 12, 2009 |
| Give MarkeTrak update at RMS | ERCOT | Dec 10, 2008 |