## Slide 1: SCR 748 - Website Enhancements for ERCOT Outages Update Retail Market Subcommittee March 12, 2008
Kevin Tanner - Project manager
ERCOT

## Slide 2: (SCR 748) PR 70006_01 - Overview
Background:
Scope from SCR748 to provide a central location for outage information is needed and that this information should be kept on the ERCOT website. The scope would include the enhancements below.
Scope Description from SCR748 | Goal Achieved
Calendar of dates/times for planned outages affecting retail | Yes – posted manually by ERCOT thru Collage. Automation to be delivered with Phase 2.
Unplanned Outage Alert with web message capability | Yes - Web Alert Flag delivered with link to canned web message on ERCOT.com. Flag and web message posted manually thru Collage. Automation to be delivered with Phase 2. **Automated email generation not delivered. Will be delivered with Phase 2. Outage email delivered manually by ERCOT in the interim during business hours.
Log of outages | Yes – Log posted Nov. 22, 2007 forward manually by ERCOT thru Collage
Anticipated Market benefit from SCR748, IA and CBA:
Proactive visibility for planned and unplanned outages from a centralized location
MPs would have to have fewer resources involved in monitoring outage info.

## Slide 3: (SCR 748) PR 70006_02 - Overview
Background:
This project is the phase 2 effort that will implement a solution to complete the automation for ERCOT Outage Notifications as defined in SCR748. The scope for this project is expected to deliver the following:
    Automatic posting of the outage alert to ERCOT.com once SLA expires.
    Automatic initial email notification (limited information) of outage 24/7. (follow as needed by official notice from Client services)
    Automatic alert to Remedy Incident Management System from the System Openview Monitoring. Some validation with Commercial Operations is still expected for false positive alerts.

## Slide 4: (SCR 748) PR 70006_02 Phase 2 - Overview
System Impacts:
ERCOT.com (Collage)
ERCOT Helpdesk (Remedy) PR60055_01
System monitoring (HP Openview)
Anticipated ERCOT/Market Benefits:
ERCOT benefit: Reduce the number of manual steps required to post a Outage notice.
Market benefit: Increase the accuracy and timeliness of Outage Notices.
Budget Range for 2008 PPL
$250k – 500K
2008 Recommended Rank - 3

## Slide 5: Current System Outage process as delivered with PR70006_01

## Slide 6: Proposed Future System Outage process as Delivered with PR70006_02