## Sheet1
| Document Name: | TN PC Nodal DMS Conceptual System DesignV0.9
Sr # | Issuing Entity | Page Number | Description | Accepted / Rejected / Response | Reviewer | Reason
1 | LCRA |  | All comments reference the document page number. There are several spelling errors that need attention | Accepted | Art Deller | all references to Trade Date with Operating Date
2 | LCRA | Page 7, 8 and 9 | It would be a better design to have ERCOT communicate back to the Market Participant (MP) that the dispute is incomplete and give the MP the opportunity to correct the information submitted for the dispute. Currently, the flowchart shows “Is all required Info Present?” If No, then “ERCOT denies the Dispute” and then it is “sent to ADR.” We suggest that after “Is all required Info Present?” and No, a new box reads “Communicate to MP that more complete information is needed”, and then circle back to “Is all required info present?”. | Accepted | Art Deller | Updated the Dispute process diagrams with updated diagrams
3 | LCRA | Page 19 – | In the bullets for Status and Activity Type | Accepted | Art Deller | These values are used for internal processing steps
4 | LCRA | Page 22 – 3.2.4 | What is the difference between the Operating Day and the Trade Day? MPs need to see SR# 6, 8, 9, 24, 25 | Accepted | Art Deller | Changed all reference to Trade Day to Operating day
5 | LCRA | Page 25 | Attribute List: MPs need to see SR# 4, 5 ,6, 23. There is an “end trade day” but no “start trade day”. | Accepted | Art Deller
6 | LCRA | Page 24 | Disputes may be filed by a Market Participant who meets all the following criteria: | Accepted | Art Deller | catch table. Section corrected
7 | LCRA | Page 27 – Multi day disputes | Table does not show the trade days being submitted. Does the Operating Day = Trade Day? Also in this table, there are columns labeled “Dispute Id” and “Sub Dispute Id”. This column heading/label is not referenced in the previous tables in this document. We think that disputes will be assigned a Dispute Id, but it is not mentioned except in this table. | Accepted | Art Deller | Operating day = trade day. Dispute Id: Added in the table. (present for Single day as well as multiday dispute) Sub Dispute Id : Added in the table. (present for multiday dispute) Once the MP submits the disputes this Id is generated. This Id is use ful to query the dispute after couple of days and verify the status