## Slide 1: CIM Update
Raj Chudgar
Program Director for Market Redesign

## Slide 2: Objectives
Provide transparency to TPTF about the status of CIM integration
Provide explanations of issues and difficulties
Provide explanations for the workaround planned for 4/1

## Slide 3: Major challenge for Nodal is the successful integration of CIM data between NMMS, EMS, MMS and other Nodal systems
CIM critical dependency is on successful model integration of EMS, MMS and NMMS
Challenges for CIM include:
  First implementation of CIM model integration in the world
  ERCOT CIM extended significantly beyond standard
  Coordination of solution across several project teams and several vendors
1
2
3
4
5
7
6

## Slide 4: EDS for NMMS is currently in progress and we are working on resolving outstanding defects
1
NMMS product deployed to EDS with known defects
EDS 2 Release 4 started Market Trials with NOMCRs testing on March 17, 2008
NMMS Team working with AREVA for initial load export data since April 2007
NMMS consuming AREVA Export file from Zonal since November 2007
NMMS generates CIM File that can be imported by MMS
EMS not able to fully import CIM, since it is still under development
Feature | Planned date
All Sev 1 & 2 defects fixed | Apr 15, 2008
Baseline 1 and Baseline 2 Requirements complete | June 2008
Note: MMS & EMS must be able to consume CIM File prior to June 02, 2008 Single-entry Go-Live

## Slide 5: MMS CIM importer has successfully imported data
2
Market Management System (MMS) deployed to EDS for SCED, DAM and RUC testing
Capability of MMS CIM importer to process CIM file (V1.8) through application database (RDB) and to solve a power flow in the current MMS has been proven
MMS (e.g., SCED, DAM, RUC) have not been tested using the CIM file data
MMS designs are being reviewed to identify additional issues that may require modeling changes
There are still data issues with the CIM file as it is processed by the MMS applications, and issues are being passed back to NMMS
Feature | Planned date
Start Pre-FAT test for MMS workflows with CIM file data | Apr 2, 2008
Start FAT test for MMS workflows with CIM | Apr 22, 2008
ABB/MMS team planning to test the CIM data into applications in MMS 4

## Slide 6: EMS CIM importer is currently under development with known challenges
3
EMS deployed to EDS and testing in progress for SCADA, SE, RLC, TCM LFC, AS Capacity Monitor
EMS CIM Importer currently under development
  Areva has built 3 out of 7 components
  All remaining components are in progress
There are data issues with the CIM file as it is processed by the EMS applications, and issues are being passed back to NMMS
ERCOT CIM XML will be used to build the ERCOT EMS MOMs during Pre-FAT
ERCOT resources will be onsite at Areva during Pre-FAT of CIM Importer
Feature | Planned date
Development Complete | Mar 21, 2008
Pre-FAT start | Mar 24, 2008
Pre-FAT end | Apr 4, 2008
FAT start | Apr 7, 2008
FAT End | Apr 18, 2008
AREVA management team has committed to deliver the CIM importer on the schedule specified

## Slide 7: Outage Scheduler development for application and CIM integration underway
4
Outage Scheduler FAT testing is in progress – expected completion 3/21/2008
NMMS sending Equipment List to OS
Outage scheduler will be tested against the equipment list from NMMS in the last week of March 08
OS will use the NMMS equipment list for Market trials
Development of OS sending Outages to NMMS to be included in data passed to CRR underway

## Slide 8: MIS will be the location for MPs to pick up CIM models
5
MIS currently deployed to EDS
NMMS has capability of producing CIM/XML model files for posting
Developing drop off points and folder structure for posting

## Slide 9: Generation data into NMMS comes in through Registration and RARFs
6
Registration (Siebel) is deployed in production
Registration enhancements for integration with NMMS is in iFAT testing (XML files)
The process to load additional RARF data through NOMCRs by ERCOT is being developed
Once all RARF data within NMMS, ERCOT is planning to “audit” NMMS to ensure all RARF data is defined

## Slide 10: CIM data is converted in NMMS to PSS/E for CRR consumption
7
CRR application is in EDS testing mock auctions in Market Trials
Currently, CRR in EDS Market Trials is using a manually augmented PSS/E RAWD file that was derived from the seasonal planning case for Summer ’09
Future business process is that CRR will receive an Augmented PSS/E RAWD file from NMMS for monthly and annual auctions. Siemens is developing the software for this, and it will be ready for testing in April.
For Go-Live, CRR requires the Augmented PSS/E RAWD file from NMMS in October, to run the first monthly auction in November.

## Slide 11: In the absence of integrated systems, we are introducing a work-around for April 1 commencement of EDS (Release 9.3)
Pros | Cons
Testing with Market Participants on schedule. More Production-Like Network Model than is in EDS today. Begin Processing Awards and Obligations through EIP | SMEs time divided between workaround and permanent solution
Can begin running DAM with Full Network Model | Manually Synchronize EMS and MMS Network Models.
 | Short Term Solution
Work-around for 4/1
Work-around definition:
  Data stubs are required since full integration is not complete for highlighted Yellow items
  Data Verification is required of the data between systems i.e. comparing the network model in EMS and MMS to ensure they are the same
  Once data creation is complete, both Real time and Day Ahead markets will be tested in MMS before exposing to Market Participants in EDS