## Slide 1: MMS Update for TPTF March 20, 2008 Murray Nixon Sai Moorty

## Slide 2: Agenda
MMS release schedule
Key driver for proposed deferrals (reminder)
Proposed deferrals update
MMS3 FAT status

## Slide 3: MMS Release Schedule
RELEASE | CONTENTS | PLANNED START DATE | PLANNED END DATE
MMS2 FAT | DAM, DEF, HRUC, DRUC, POD, SFT, SCED extensions, partial implementation of baseline 1&2 items | 3Dec07 Actual: 3Dec07 | 11Jan08 Actual: 25Jan08
MMS3 pre-FAT | SASM, DST, S&B snapshots, CIM importer | 4Feb08 Actual: 4Feb08 | 15Feb08 Actual: 15Feb08
MMS3 FAT | SASM, DST, S&B snapshots, CIM importer | 18Feb08 Actual: 18Feb08 | 14Mar08 Actual: 14Mar08
MMS4 pre-FAT | CCT, NSLR, DC Tie, VDI, WRUC, remaining baseline 1&2 items, CIM importer components not available for MMS3 | 2Apr08 | 16Apr08
MMS4 FAT | CCT, NSLR, DC Tie, VDI, WRUC, remaining baseline 1&2 items, CIM importer components not available for MMS3 | 22Apr08 | 30Jun08

## Slide 4: Key Driver for Proposed Deferrals
Ensure the final MMS FAT completes by 30Jun08, allowing 2 months for integration & EDS4 activities prior to the 168 hour test start on 1Sep08
  This was the direction provided to the ERCOT & ABB MMS teams by the Nodal and ABB executives on 28Nov07
  The proposed deferrals will help MMS meet the Nodal program timeline

## Slide 5: Proposed Deferrals Update
Summary Description | Status | Binding Document
Automated interface for QSEs with resources to update resource parameters (e.g. ramp rates) in MMS | No longer deferred; will be delivered as part of MMS4 No documentation changes required | Requirements Document
Dynamically scheduled resource incremental and decremental energy offer curves | Interpretation issue; ERCOT implemented functionality based on their original interpretation; further discussion yielded a new interpretation for ERCOT that will require a change to the requirements and design Propose going live with the functionality as designed and implemented; requires no documentation changes until new functionality implemented Workaround extremely labor intensive for QSEs Work to begin as soon as resources are available; continuing to work with ABB to determine feasibility of earlier implementation Requirements document updates will be drafted, reviewed and presented for approval once timeline for implementation is finalized No protocol change required | Requirements Document
S&B information only calculations | No proposed workaround Work will begin as soon as resources are available after the delivery of MMS4 into FAT Implementation targeted for after go-live; date will be determine by Nodal program and TPTF NPRR115 gray-boxing the change in the implementation date of these calculations has been drafted; out for review with target for approval through TPTF & PRS in April | Protocol

## Slide 6: Proposed Deferrals Update (cont’d)
Summary Description | Status | Binding Document
MMS multiple network models | MMS does not currently have the capability to concurrently support separate network models for Operating Day and Day-Ahead MMS processes (DAM & RUC) Work will begin as soon as resources are available after the delivery of MMS4 into FAT Implementation targeted for after go-live; date will be determined by ERCOT, Nodal program and TPTF For period between go-live and implementation of multiple network model (Operating Day and Day-Ahead), MMS will use one network model (Operating Day) for both Operating Day and Day-Ahead processes (DAM & RUC). On rare occasions where the impact is deemed significant (new transmission at 345KV level), ERCOT will implement a workaround such as using a combination of incorporating changes earlier into a model and working with TSPs to enter outages for the days prior to actual energization. The workaround process have been verbally discussed and are pending formalization within ERCOT operations. No expected changes to the protocols | Protocol (not explicit)
Co-optimizing energy and AS for self-committed resources in DAM | TPTF has approved requirements to incorporate sub-group items 1 & 2 TPTF to review proposed changes for item 3 at 20Mar TPTF meeting MMS to submit approved requirements for sub-group items 1 & 2 to ABB for evaluation & estimate Based on approved requirements document changes, protocol changes should be drafted for review and approval Current plan is for the work to be prioritized along with other work scheduled to begin as soon as resources are available after the delivery of MMS4 into FAT | Protocol; Requirements Document

## Slide 7: MMS3 FAT Status
MMS3 FAT started on 18Feb08 with a targeted completion of 14Mar08
151 structured tests completed with an 83% pass rate
One severity 1 defect remained that was written against the EDS environment; workaround is available but cumbersome; working with ABB to deliver a fix by end of this week
14Mar formal FAT exit approved by Eileen Hall on 18Mar08
MMS3 was earlier deployed to various downstream systems (e.g., EDS, EIP, INT)