## Slide 1: Distributed Renewable Generation Profile Implementation Plan

## Slide 2: DRG Background
HB 3693 requires that ERCOT implement the settlement of distributed renewable generation as of 1/1/2009.
TAC, during their Feb 7, 2008 meeting, directed PWG to develop a profiling solution to address recommendation #3 of the Distributed Generation Task Force (DGTF)
PWG has developed Load Profile ID assignments and Profile Models to be applied to small distributed renewable generation
New Load Profiles require a market notice of at least 150 days prior to their implementation.

## Slide 3: DRG Future Timeline
LPGRR Timeline
Normal Timeline:
    Post by 3/27
    PWG Review 4/23
    PWG IA Review 5/28
    COPS Review 6/10
    TAC Review 6/26
    BOD Review 7/15 (if there are impacts to ERCOT)
Urgent Timeline: (Recommended approach to meet deadline for 150 day notice )
    PWG Review and send to post 3/26
    Urgency Request/Email Vote
    COPS Review (with IA) 4/8
    TAC Review 5/8
    Board Review 5/20 (if there are impacts to ERCOT)
  Market Notice announcing DRG Profile Segments 08-03-2008
12-31-2008 150 day notice ends
01-01-2009 Implementation date
    12-29-2008 ERCOT will begin posting Forecasted Load Profiles
    01-02-2009 ERCOT will begin posting Backcast Load Profiles

## Slide 4: DRG Future Timeline
PRR Timeline
PRS Granted Urgency 3/20/2008 and recommended approval of amended language
    COPS Review (IA and CBA) 4/8 – this step is only because there is a CBA associated with this PRR and COPS will probably want to review it prior to going to PRS. It does not slow down the timeline.
    PRS Review (IA and CBA; assign priority and rank) 4/18
    TAC Review 5/8
    Board Review 5/20 (meets deadline for 150 day notice )
  Market Notice announcing DRG Profile Segments 08-03-2008
12-31-2008 150 day notice ends
01-01-2009 Implementation date
    12-29-2008 ERCOT will begin posting Forecasted Load Profiles
    01-02-2009 ERCOT will begin posting Backcast Load Profiles

## Slide 5: DRG Profile Transition
07-01-2008 TDSP’s to begin sending in documentation to ERCOT initiating DRG Profile Segment assignments
07-01-2008 to 12-31-2008 ERCOT will accumulate and validate change requests
  ERCOT will notify submitter of any invalid request
01-02-2009 ERCOT will send files of change requests to TDSPs
01-02-2009 TDSPs can begin to submit 814-20 transactions changing to DRG Profile Segments with effective date of a meter reading on or after 01-01-2009

## Slide 6: DRG Profile Ongoing process
01-02-2009 TDSP’s continue sending in documentation to ERCOT initiating DRG Profile Segment assignments
01-02-2009 ERCOT begins sending validated change requests to TDSPs
  ERCOT will notify submitter of any invalid request
01-02-2009 After receipt of requests, TDSPs will submit 814-20 transactions on or before the second regularly scheduled meter read date
April 2009 ERCOT will begin performing quarterly validations of DRG Profile Segment assignments
  ERCOT will verify that profile segment assignments for ESIIDs in Lodestar are consistent with documentation submitted

## Slide 7: DRG Profile Ongoing process
(Continued)
If a REP of record discovers that a previously approved ESI ID has become ineligible to be served under a DRG Profile Segment, the REP of record shall notify the TDSP and ERCOT that a Profile Segment change is required.
If a TDSP discovers that a previously approved ESI ID has become ineligible to be served under a DRG Profile Segment, the TDSP of record shall notify ERCOT and also change the Profile Segment to the appropriate default Profile Segment as if the ESI ID represented a new premise without DRG.
TDSPs shall make reasonable effort to effect the change using the appropriate Texas SET process as soon a possible after they become aware that the premise is no longer eligible to be served under a DRG Profile Segment.

## Slide 8: DRG Profile Ongoing process
(Continued)
As specified in LPG Section 8.1 Routine and Non-Routine Profile Model Evaluations, on an annual basis ERCOT shall review DRG profile segments to determine whether model updates are appropriate and make recommendations to the PWG.
  review will be based on usage level characteristics and information submitted