## Slide 1: 2009 Project Prioritization
Troy Anderson
ERCOT Program Management Office
April 4, 2008

## Slide 2: PMO Update
Agenda
  2007 Project Financial Results
  2009 Project Prioritization

## Slide 3: PMO Update – 2007 Results
2007 CART Funding Status ** Unaudited– Updated 2/27/08 **
CART | Initial 2007 Funding | Changes | Final 2007 Funding | 2007 Actuals | Variance
CO | 4,250,000 | +1,883,693 | 6,133,693 | 6,133,693 | 0
IO | 5,294,500 | +4,190,908 | 9,485,408 | 8,886,677 | - 598,731
MO | 1,500,000 | - 400,000 | 1,100,000 | 1,010,066 | - 89,934
RO | 7,000,000 | - 3,898,558 | 3,101,442 | 3,101,442 | 0
SO | 4,500,000 | - 1,776,043 | 2,723,957 | 2,723,957 | 0
Nodal | 21,455,500 | 0 | 21,455,500 | 21,435,952 | - 19,548
Total | 44,000,000 | 0 | 44,000,000 | 43,291,787 | - 708,213
Excess funding transfers that were not utilized have been returned to the originating CART

## Slide 4: PMO Update - 2009 Project Prioritization Schedule
2009 Project Prioritization Schedule - Overview
  January 2008
    CARTs revise 2009 Initiative Lists
  February 2008
    Initial review at Market Subcommittee meetings
      MO - COPS (February 12)
      RO - RMS (February 13)
      SO - ROS, WMS (February 14 / February 20)
  March 2008
    Approval by market subcommittees
      MO - COPS (March 11)
      RO - RMS (March 12)
      SO - ROS, WMS (March 13 / March 19)
      CO, IO, MO, RO, SO – PRS (March 20)
  April 2008
    Approval by TAC (April 3)
    Available for F&A and Board review (April 15)

## Slide 5: 2009 Project Priority List / Funding Level Review
2009 Project Approval Status by Program Area
  All 5 lists have been reviewed and approved by ERCOT Strategic Review Team (SRT) and Executive Committee (EC)
  CO (Corporate Operations) - Modified & approved by ERCOT EC on 3/17/08
  IO (IT Operations) - Approved by ERCOT EC on 3/17/08
  MO (Market Operations) - Modified and approved by COPS on 3/11/08
  RO (Retail Operations) - Approved by RMS on 3/12/08
  SO (System Operations)
    Modified by ROS on 3/13/08
      ROS didn’t formally approve the list – they think it is premature to estimate the post-Nodal effort and fear the recommended funding might not be sufficient
      ROS did not identify any efforts to be added to the 2009 list
      ROS did not identify any projects on the list that are not important
    WMS did not suggest any modifications on 3/19/08 – they concur with the reservations noted by ROS that the funding level for post-Nodal Go-Live might not be sufficient
  PRS reviewed all lists on 3/20/08 – they expressed the same reservations about post-Nodal Go-Live funding

## Slide 6: 2009 Project Priority List / Funding Level Review
2009 Project Budgets and Counts by Program Area
Program Area | Budget Request | Projects Started in 2008 | New 2009 Projects
CO | $ 3,550,000 | 13 | 7
CO – Met Center | $ 20,400,000 | 1 | 0
IO | $ 8,350,000 | 0 | 9
MO | $ 4,300,000 | 1 | 8
RO | $ 3,500,000 | 5 | 5
SO | $ 7,500,000 | 4 | 12
Total | $ 47,600,000 | 24 | 41

## Slide 7: 2009 Project Priority List / Funding Level Review
2009 Project Prioritization Notes by Program Area
  CO ($23.95M)
    Large, multi-year project to replace the Met Center ($20.40M)
      Approved by Board of Directors on 2/19/2008
    Other projects limited to most critical needs ($ 3.55M)
  IO ($8.35M)
    Keeping up with computing infrastructure needs
  MO ($4.30M)
    Increased funding request for post-Nodal Go-Live enhancements
  RO ($3.50M)
    Reduced funding request compared to previous years (but in line with prior year actual spending)
    Several projects in support of PUCT rulemakings
  SO ($7.50M)
    Increased funding request for post-Nodal Go-Live enhancements
    Includes funds for implementing functionality that will be developed by the Nodal team in 2008 but won’t be included in Go-Live

## Slide 8: 2009 Project Priority List / Funding Level Review
2009 Project Prioritization – Nodal Stabilization
  ERCOT has budgeted $6.5M for Nodal stabilization in 2009
    This will fund O&M efforts to resolve post-Go-Live Nodal issues
    These funds are separate and distinct from project funding on the PPL
    It has been noted that market input will be needed to assist ERCOT in prioritizing Nodal stabilization activities
    The 2009 ERCOT budget is not yet complete and approved
  Summary of funds available for post-Go-Live work
    Nodal Stabilization O&M Funds $ 6.5M
    SO CART Project Funds $ 7.5M
    MO CART Project Funds $ 4.0M
    Total $18.0M
  In addition, significant stabilization effort is expected to come from ERCOT staff
  ERCOT is committed to the proper operation of the Nodal system. We will address concerns of the market as quickly as possible and work to resolve issues that are identified.

## Slide 9: 2009 Project Priority List / Funding Level Review
2009 Project Prioritization – Additional Comments
  Documentation completeness
    Full documentation = $29.4M
    Limited documentation = $18.2M
    Where possible, ERCOT is working to reduce the limited documentation amount by completing required documents prior to final Board and PUCT consideration
  The impact of the Met Center Disposition project on the System Admin Fee is not yet known because various financing options are being considered
  As reported previously, the project lists will be revisited later in 2008 to complete remaining documentation, consider new additions to the lists, and reprioritize as needed

## Slide 10: 2009 Project Priority List / Funding Level Review
Project Budget History by Program Area
Program Area | 2009 Budget Request | 2008 | 2007 | 2006
CO | $ 3,550,000 | $ 8,450,000 | $ 4,250,000 | $ 2,500,000
CO - Met Center | $ 20,400,000 | $12,000,000 | $ 0 | $ 0
IO | $ 8,350,000 | $ 6,400,000 | $ 5,250,000 | $ 7,200,000
MO | $ 4,300,000 | $ 1,200,000 | $ 1,500,000 | $ 2,500,000
RO | $ 3,500,000 | $ 6,100,000 | $ 7,000,000 | $ 6,700,000
SO | $ 7,500,000 | $ 50,000 | $ 4,500,000 | $ 5,200,000
Nodal * | $ 0 | $ 5,300,000 | $21,500,000 | $10,200,000
Total | $ 47,600,000 | $39,500,000 | $44,000,000 | $34,300,000
Previous Year Budgets
* Portion of Nodal project funded by Zonal project budget as approved by the Board in 2006

## Slide 11: 2009 Project Priority List / Funding Level Review
Questions?