## Slide 1: TPTF Update for TAC April 4, 2008 Trip Doggett
http://nodal.ercot.com <number>
Notes: <number>

## Slide 2: Agenda
http://nodal.ercot.com <number>
Item | Description | Purpose
1. Meeting Summary | Summary of recent TPTF activities | For review
2. Next Meetings | Upcoming activities | For review
3. Approval of Readiness Metrics | Request TAC approval for ERCOT to move forward with changes to: Metric CO1, Settle Market for Seven Days and Provide Appropriate Extracts, as submitted to TPTF on March 3, 2008. Metric E5, Nodal Statement on Auditing Standards (SAS) 70 Readiness, as submitted to TPTF on March 21, 2008. | For Vote
4. Approval of Milestones | Request TAC acknowledge TPTF completion of the following Milestone– EMS-MMS MOTE Requirements (B2) v0.12 complete COMS Disputes Management System CSD v0.03 complete | For Vote
Notes: <number>

## Slide 3
http://nodal.ercot.com <number>
Meeting Summary – March 3
Meetings March 3-5 and March 20-21.
On March 3, TPTF discussed the following:
  Nodal Program Update
  Nodal Timeline Update
  Readiness Metric Update
    On March 3, TPTF endorsed moving forward with the revision to Metric CO1, Settle Market for Seven Days and Provide Appropriate Extracts, as submitted to TPTF on March 3, 2008. The motion carried by roll-call vote, with 100% in favor and one abstention (J. Aron and Co.). The Consumer Market Segment was not represented for the vote.
  Process for Managing Protocol Content
  NPRR104 - Corrections and Clarifications for Real Time Settlements and Ancillary Service Net Obligations
  DAM Subgroup Issues
    On March 3, TPTF approved the TPTF changes to the DAM Subgroup comments to the MMS DAM and SASM Requirements (B2) v2.0, as modified on March 3, 2008, and to assign a preliminary status to these changes of “needed for go-live functionality.” TPTF requests ERCOT to provide an impact analysis on the project schedule and cost to make these changes to the DAM and report back to TPTF no later than May 15, 2008. The motion carried by unanimous roll-call vote. The Independent Generator and Consumer Market Segments were not represented for the vote.
Notes: <number>

## Slide 4
http://nodal.ercot.com <number>
Meeting Summary – March 4
On March 4, TPTF discussed the following:
  EDS Update
    Status of State Estimator
  Market Operations Update
    Processes for Voltage Studies
  Outage Scheduler Update
    Discuss Dual-Entry OS Issues
  Quality Center Update
  EMS Update
    Status of EMS CIM Importer
  NPRR097, Changes to Section 8 to Incorporate Role of TRE, the IMM, and the Concept of Market Compliance
  NPRR107, Nodal Emergency Interruptible Load Service
  CRR Update
    Update on Market Participant CRR Testing
    Discuss WMS-approved proposal for CRR naming convention
  Registration Update
    Update on RARF obligations for QSEs
Notes: <number>

## Slide 5
http://nodal.ercot.com <number>
Meeting Summary – March 4 (continued)
On March 4, TPTF discussed the following:
  EMS/MMS Market Operations Testing Environment Requirements
    On March 4, TPTF approved the EMS-MMS MOTE Requirements (B2) v0.12 as submitted. The motion carried by unanimous roll-call vote. The Independent Generator and Consumer Market Segments were not represented for the vote.
Notes: <number>

## Slide 6
http://nodal.ercot.com <number>
Meeting Summary – March 5
On March 5, TPTF discussed the following:
  Market Rules Update
    Nodalizing of Zonal Protocol Sections 18, 20, 23, and 24:
      NPRR109 - Section 18, Load Profiling
      NPRR110 - Section 20, Alternative Dispute Resolution Procedure
      NPRR105 - Section 23, Texas Test Plan Team - Retail Market Testing
      NPRR106 - Section 24, Retail Point-to-Point Communications
    Schedule for nodalizing Section 11, Data Acquisition and Data Aggregation Processes for Voltage Studies
  EDS DAM/RUC/SASM MP Handbook
    On March 5, TPTF approved the EDS 4 Release 9 DAM/RUC/SASM Market Participant Handbook v1.03 as modified by TPTF March 5, 2008. The motion carried by unanimous roll-call vote. The Consumer Market Segment was not represented for the vote.
  Load Resource Flag for AS Trade Submissions
  COMS Update
    Draft NPRR Removal of Partial Assignment of CRR Shortfall to Real-Time
Notes: <number>

## Slide 7
http://nodal.ercot.com <number>
Meeting Summary – March 5 (continued)
On March 5, TPTF discussed the following:
  NPRR097, Changes to Section 8 to Incorporate Role of TRE, the IMM, and the Concept of Market Compliance
    On March 5, TPTF endorsed forwarding TPTF recommended changes to PRS for NPRR097. The motion carried by roll-call vote, with 100% in favor and three abstentions (Coral Power, Exelon, and BP Energy). The Independent Generator and Consumer Market Segments were not represented for the vote.
  MMS Update – Incorporating PUC Subst. R. 25.505(f)
    On March 5, TPTF approved the TPTF changes to the Requirements documents: MMS Overall Processes; MMS DAM and SASM; and MMS SCED and Real-Time Processes as submitted on March 5, 2008. TPTF requests ERCOT to provide an impact analysis on the project schedule and cost to make these changes and report back to TPTF. The motion carried by roll-call vote, with 100% in favor and two abstentions (Coral Power and Exelon). The Independent Generator and Consumer Market Segments were not represented for the vote.
Notes: <number>

## Slide 8
http://nodal.ercot.com <number>
Meeting Summary – March 5 (continued)
On March 5, TPTF discussed the following:
  Discussion of Combined-Cycle White Papers
    Combined-Cycle Unit Modeling in the Nodal Design
      On March 5, TPTF approved the white paper IDA003: Combined-Cycle Unit Modeling in the Nodal Design v2.1 as submitted. The motion carried by roll-call vote, with 75% in favor and two abstentions (Exelon and BP Energy). The Consumer Market Segment was not represented for the vote.
    Details on the Settlement of Combined-Cycle Plants
      On March 5, TPTF approved the proposed changes only in Section 12 of the COMS White Paper Details on the Settlement of Combined Cycle Plants v1.3. The motion carried by roll-call vote, with 79.2% in favor and nine abstentions (CPS San Antonio, Stream Energy, StarTex Power, Strategic Energy, Accent Energy, Cirro Group, Green Mountain Energy, Integrys Energy, and BP Energy). The Consumer Market Segment was not represented for the vote.
Notes: <number>

## Slide 9
http://nodal.ercot.com <number>
Meeting Summary – March 20
On March 20, TPTF discussed the following:
  Outage Scheduler Update
    Options for Outage Scheduler dual-entry issues
    Updates to the EDS Outage Scheduler MP Handbook
      On March 20, TPTF approved the EDS Outage Scheduler Market Participant Handbook v0.05 as modified by TPTF on March 20, 2008. The motion carried by roll-call vote, with 70% in favor and 14 abstentions (LCRA, Austin Energy, City of Garland, CPS San Antonio, City of Dallas, Town of Flower Mound, Stream Energy, StarTex Power, Strategic Energy, Accent Energy, Cirro Group, Green Mountain Energy, Integrys Energy, and Coral Power). All Market Segments were represented for the vote.
  NPRR111, Timelines for Response by ERCOT to Transmission Service Provider Requests
  Common Information Model (CIM) Update
  Nodal Timeline Update
  MMS Update
    MMS FAT
    MMS Deferral Items
  Nodal Program Update
Notes: <number>

## Slide 10
http://nodal.ercot.com <number>
Meeting Summary – March 20 (continued)
On March 20, TPTF discussed the following:
  MMS Update (continued)
    NPRR113, Load Resource Type Indicator for AS Trades and Self-Arranged AS
    Discussion Paper “Ancillary Service Supply Responsibility Issue – MMS”
    NPRR102 MMS Data Requirements for Publication of Resource and Load Information v0.1
Notes: <number>

## Slide 11
http://nodal.ercot.com <number>
Meeting Summary – March 21
On March 21, TPTF discussed the following:
  CRR Shortfall Update
    CRR Shortfall Scenarios
    Options for equalizing revenue imbalances resulting from CRR shortfall scenarios
  NPRR113, Load Resource Type Indicator for AS Trades and Self-Arranged AS
    On March 21, TPTF endorsed forwarding TPTF comments to PRS for NPRR113, Load Resource Type Indicator for Ancillary Service (AS) Trades and Self-Arranged AS, as discussed by TPTF on March 21, 2008. The motion carried by roll-call vote, with 100% in favor and one abstention (Exelon). The Consumer Market Segment was not represented for the vote.
  Combined Cycle Unit (CCU) Update
    Approach to calculating clawback factors for CCUs
    Revisions to clawback factors in COMs whitepaper “Details on the Settlement of Combined-Cycle Plants”
Notes: <number>

## Slide 12
http://nodal.ercot.com <number>
Meeting Summary – March 21 (continued)
On March 21, TPTF discussed the following:
  NPRR 104, Corrections and Clarifications for Real-Time Settlements and Ancillary Service Net Obligations
  Draft NPRR, Simplify Ancillary Services Settlement Formulas
  DAM Subgroup Update
  COMS Update
    COMS Disputes Management System CSD v0.02
      On March 21, TPTF approved the COMS Disputes Management System CSD v0.03 as submitted. The motion carried by roll-call vote, with 100% in favor and three abstentions (City of Eastland, City of Allen, and Reliant). The Independent Generator Segment was not represented for the vote.
    Status of the COMS Project
  Readiness Update
    Revisions to Metric E5, Nodal Statement on Auditing Standards (SAS) 70 Readiness
      On March 21, TPTF endorsed ERCOT moving forward with the revisions to Metric E5, Nodal Statement on Auditing Standards (SAS) 70 Readiness, as modified by TPTF on March 21, 2008. The motion carried by roll-call vote, with 100% in favor and no abstentions. The Independent Generator Segment was not represented for the vote.
    IBM Report on ERCOT and Market Participant Readiness
Notes: <number>

## Slide 13
http://nodal.ercot.com <number>
Meeting Summary – March 21 (continued)
On March 21, TPTF discussed the following:
  Readiness Update (continued)
    Project Artifact Schedule
    Nodal Readiness Scorecard
  EIP Update
    EIP External Interfaces Specification
Notes: <number>

## Slide 14
http://nodal.ercot.com <number>
Next Meetings
Next meetings
  Monday March 31 through Wednesday April 2
  Monday April 21 and Tuesday April 22
  Monday May 5 through Wednesday May 7
  Thursday May 22 and Friday May 23
Notes: <number>

## Slide 15
http://nodal.ercot.com <number>
Next Meetings (continued)
On March 31 through April 2, likely topics include:
  Nodal Timeline Update
  NMMS Update
    Translating the zonal network model to nodal
  Readiness Update
    ERCOT Business Processes
    Scorecard Update
  MMS Update
    Disposition of comments for NPRR102, MMS Data Requirements for Publication of Resource and Load Information v0.1
  Verifiable Cost Subgroup Update
    Review comments for the draft NPRR
    Review comments for the Verifiable Cost Manual
  Market Rules Update
    Review market comments for recently “nodalized” protocol sections:
      NPRR109 - Section 18, Load Profiling
      NPRR110 - Section 20, Alternative Dispute Resolution Procedure
      NPRR105 - Section 23, Texas Test Plan Team – Retail Market Testing
      NPRR106 - Section 24, Retail Point-to-Point Communications
Notes: <number>

## Slide 16
http://nodal.ercot.com <number>
Next Meetings (continued)
On March 31 through April 2, likely topics include:
  Quality Center Update
  EDS Update
    EDS Status Update
      EDS – SLA Availability Metrics Summary
    Discuss NPRR for Resource Limit Calculator to revise LDL equation per SPR 1643
    Review disposition of comments for the EDS 3 LFC Testing Market Participant Handbook v1.02
  Nodal Program Update
    Infrastructure capacity and disaster recovery
    Health checks
  User Interface Subgroup Update
  Quality Assurance
  MIS Update
    Notices
  CDR Update
    Discuss status of staging tables
    Request clarification to update frequency for AS Capacity Monitor data
    Identify items that have duplicative posting requirements
Notes: <number>

## Slide 17
http://nodal.ercot.com <number>
Next Meetings (continued)
On March 31 through April 2, likely topics include:
  Future Subgroup to address Operations and Market Issues such as:
    Ability to block offer off-line Non-Spin from Generation Resources
    Potential for reduced AS Offers into a SASM given the AS Offer re-submittal rules for un-struck DAM AS Offers linked to a 3-part offer
    SR25.505 SWCAP issue
    Wind-Powered Generation Resource (WGR) Issues
  Training Update
  CRR Update
    EDS 3 Release 7 Status and vendor discussion
    Discuss process for PCRR and MCFRI allocation
  DAM Overview
    Discuss the processes and tools of the Day-Ahead Market
Notes: <number>

## Slide 18
http://nodal.ercot.com <number>
Approval of Readiness Metrics
On March 3, TPTF endorsed moving forward with the revision to Metric CO1, Settle Market for Seven Days and Provide Appropriate Extracts, as submitted to TPTF on March 3, 2008. The motion carried by roll-call vote, with 100% in favor and one abstention (J. Aron and Co.). The Consumer Market Segment was not represented for the vote.
On March 21, TPTF endorsed ERCOT moving forward with the revisions to Metric E5, Nodal Statement on Auditing Standards (SAS) 70 Readiness, as modified by TPTF on March 21, 2008. The motion carried by roll-call vote, with 100% in favor and no abstentions. The Independent Generator Segment was not represented for the vote.
Request TAC approval for ERCOT to move forward with revisions to metric CO1, Settle Market for Seven Days and Provide Appropriate Extracts, as submitted to TPTF on March 3, 2008 and revisions to Metric E5, Nodal Statement on Auditing Standards (SAS) 70 Readiness, as modified by TPTF on March 21, 2008.
Notes: <number>

## Slide 19
http://nodal.ercot.com <number>
Approval of Milestones
On March 4, TPTF approved the EMS-MMS MOTE Requirements (B2) v0.12 as submitted. The motion carried by unanimous roll-call vote. The Independent Generator and Consumer Market Segments were not represented for the vote.
On March 21, TPTF approved the COMS Disputes Management System CSD v0.03 as submitted. The motion carried by roll-call vote, with 100% in favor and three abstentions (City of Eastland, City of Allen, and Reliant). The Independent Generator Segment was not represented for the vote.
The Transition Plan says: “Any declaration of the accomplishment of a major milestone (business requirements, conceptual design, and successful completion of Market Participant testing) or a decision to proceed is contingent on the approval of both ERCOT and TAC.”
Request TAC acknowledge TPTF completion of the following Milestones –
  EMS-MMS MOTE Requirements (B2) v0.12 complete
  COMS Disputes Management System CSD v0.03 complete
Notes: <number>

## Slide 20
http://nodal.ercot.com <number>
Questions
?
Notes: <number>