## Slide 1: Texas Nodal Market Implementation Program Update
Jerry Sullivan

## Slide 2: AGENDA
Program Status
Quality
Deferred Items
Schedule
  CIM Health Check
  Single Point Entry
  Go-Live Plan
Cost

## Slide 3: Program Status: Nodal Delivery
Nodal Delivery status remains amber; health checks starting
Cost
Schedule
Scope / Quality
Pending PUCT approval of Budget
Fee request filed w/ PUC on 6 Mar 08
Aligned with protocols
* TPTF is addressing issue where MPs not in complete agreement, e.g., self-committed resources in DAM.
Checkpoints in place to ensure ongoing viability of 12/1/2008
CIM Health Check today
EDS 3 and 4 still red (ACE testing and Alarm Processing, respectively)
Achieving quality standards to date; upcoming months will be telling
Applying increased efforts to identify and resolve defects in pre-FAT and FAT
Green *
Amber
Red
Amber
Nodal Delivery
Legend
Red
Amber
Green
Estimate at Complete = <$319.5m
Estimate at Complete = < $319.5m + 10%
Estimate at Complete = >$319.5m + 10%
Go-live = 12/1/08
Go-live = <30 days+
Go-live = >30 days+
Program is aligned with current protocols
Program is aligned to previous protocol version
Program is not aligned to protocols
Current product quality is not sufficient for Nodal launch
Most Nodal products currently achieve quality standards
All Nodal products currently achieve quality standards

## Slide 4: Program Status: ERCOT Readiness
ERCOT Readiness status is amber
ERCOT Readiness Survey to move to monthly updates
Transition plans recently developed (Feb. 29) and scheduled for updates in April and June
Business Process model was completed and provides a top-down view and low-level operational detail
Procedures being developed for each department based on Business Process model; Procedure scorecard in development and available at end of April
Steady progress on training
Staffing plans developed; recruiting ongoing; timeframes established
Staffing metric definition is a codification of long-standing practice, not a new metric

## Slide 5: Program Status: ERCOT / Market Readiness
Engagement [amber] – Still remains an area of concern
  Market Participant survey (third round) closed March 31.
    Results available mid-April.
Registration and Qualification [green]
Connectivity and Telemetry [green] – Connectivity metrics complete for most MPs. Outliers are new to the program and need to go through EDS process
Training [green] – Training metrics will be updated by survey results.
Trials Participation [green] – Actively measuring EDS3 and EDS4 trial participation metrics
Looking ahead
  Readiness Metric for Resource Entity review of Resources to Resource Nodes and Resources to EPS Meters (MP10) is due by April 15, 2008.
  Numerous metric milestones are upcoming in next two months
  Hall of Fame Scorecard and Wall of Shame metrics will be prime motivators
  See www.nodal.ercot.com for schedule of upcoming metrics
Market Participant Readiness status remains amber

## Slide 6: Quality - Summary
Recent Successes
  CRR1 has exited FAT
  MMS3 has exited FAT
  EMS3B and EMS4.1 have exited FAT
Areas of Concern
  Lengthy defect resolution time
  Late detection of detects exacerbates defect resolution time
Mitigation Measures
  Passive data center site with live data feed will allow for earlier defect detection
  Additional measures (e.g., key vendor resource retention) in progress
Nodal Quality effort experienced recent successes but concerns remain

## Slide 7: Quality Details: Nodal FAT Active Defects by Severity by Project
Overall, active defects are being tracked by project and by classification. Problems areas include:
  Network Model Management System (NMMS) has 14 Severity 1 defects
  Outage Scheduler (OS) has 6 Severity 2 defects
  Congestion Revenue Rights (CRR) has 1 Severity 1 and 5 Severity 2 defects
Note - Does not include closed and deferred defects; data as of 3.27.08
The relative low number of Severity 1 and 2 defects in FAT is encouraging

## Slide 8: Quality Assurance: EDS Active Defects Per Release by Severity
Notes: 1) Data only includes defects identified in EDS testing (i.e., defects that migrated into EDS from FAT are excluded)
2) Data does not include closed or deferred defects
3) Release 8 (Credit, Settlement and Billing) not yet in EDS; no EDS-identified defects in Release 4 (NMMS)
Release No.
2
1
5
3
6
9
7
EDS active critical (Severity 1 and 2) defects are concentrated in Releases 3, 5, and 9*
* State Estimator (SE) tuning, Security Constrained Economic Dispatch (SCED) and Locational Marginal Price (LMP) posting, and Day Ahead Market (DAM), et.al., respectively
Current testing in EDS represents approximately 25 - 30% of code to be tested in EDS
The number of defects associated with remaining EDS testing is expected to increase significantly due to the increasing complexity associated with systems’ integration
Timely fixes to the currently unknown number of defects in the code remaining to be tested in EDS represents a major project challenge.

## Slide 9: Deferred Items
Deferred items fall into one of three different categories
  Items to be implemented before go–live, but after 168 hour test
  Items to be developed before go–live, and ready for subsequent production release
  Items to be deferred to business as usual prioritization, i.e., Project Priority List (PPL) process
Currently deferred items will be funded through one or a combination of the following sources/actions:
  Existing Nodal budgetary allowance
    for projects implemented/developed before go-live
  Nodal Contingency allowance (as necessary)
    for projects implemented/developed before go-live
  Funding allowance in ERCOT’s 2009 budget
    for projects implemented post-Go-Live
    funding sources include specific project allocation and/or general allowance (total of both: ~$18M); includes capital and O&M allocations
  Reprioritization of projects in 2009
    deferred projects may (or may not) be funded based on project prioritization
Newly deferred items will be funded through one of the above identified mechanisms
Deferred items are separated into multiple categories with potentially different funding sources.

## Slide 10: Deferred Items: Categorization and Description
Multiple EDW reports arising from draft NPRRs
Market Operations Test Environment (MOTE)
Items to be implemented before go–live, but after 168 hour test
Items to be developed by Nodal before go–live, ready for subsequent production release
Items to be deferred to business as usual prioritization (Project Prioritization List (PPL) process)
MMS multiple network models (no capability to currently support separate network models)
Settlement & Billing Information only calculations
Dynamically scheduled resources incremental and decremental energy offer curves
Add API to CRR
Web-enabled registration
NMMS API upgrade
Market Participant Identity Management (MPIM) integration with Siebel
Internal facing alarm handling/presentation - control room/EMS
Internal facing UIs – Control room/EMS
Migration of non-Nodal TML functionality to MIS
Migration of content form nodal.ercot.com website to ERCOT.com website
Operator Training Simulator
Verifiable cost automation
Co-optimizing energy and AS for self-committed resources in the DAM
Enhancements for Disputes API
IMM & ERCOT Market Operations support study tools
MMS A/S Deliverability Evaluation Function (DEF) enhancements
MMS Weekly RUC enhancements
MMS Save Case format enhancement
MMC CCT data enhancement
MMS credit check performance enhancement
Outage scheduler enhancements

## Slide 11: Schedule: CIM Health Check
The CIM health check was recently completed
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
EDS 1
EDS 2
EDS 3
EDS 4
Today
MP Trials & NM Verification
SCED & LMP Posting for 6 months
ICCP / P2P
SE Tuning
E1 R2
E2 R3
E2 R4
E3 R5
E3 R6
LFC Testing
E3 R7
CRR Testing
E4 R9
CMM, DAM & RT Settlements, Verifiable Costs & Disputes
DAM, SASM & RUC execution, DAM Stability Test, EECP, DST, Compliance
E4 R8
Performance
Health Checks – measure of schedule viability
Dictated by PRR 727: Market Readiness Certification
168 Hr Test
EDS 4
Go Live Sequence
CIM
Integration
Defect
Go-Live (Go/No-Go)
Sept
Oct
Nov
TAC Meeting: 10/2
ERCOT BoD: 10/21
First Market Notice: 10/31
Second Market Notice: 11/21
168 Hr Test Start
32 Days to complete Test
3
2
1
Business Processes

## Slide 12: Schedule: CIM Health Check
CIM Health check is currently on-going and will be reported to TPTF at end of April.
Focus of health check will be on the NMMS, EMS, and MMS systems
Further evaluation will be upon process to date, and data issues
Largest known risk is the EMS importer delivery date, and ERCOT has escalated to AREVA mgmt.

## Slide 13: Schedule: Single Point Entry
The first piece of the Go Live sequence, Implementation Single Entry Model, is planned for June 2, 2008
Market Readiness Criteria and additional requirements that ties off to Single Model Entry Go Live:
  Network Model tested successfully and delivered (Market Readiness Criteria)
  MP Market Trials completed (currently on-going)
  Zonal Model conversion to Nodal and validation by ERCOT
  ERCOT business process and system readiness complete
ERCOT will be working with TPTF, ERCOT staff, TAC, and BoD to obtain certification to comply with Section 21.12.3 of the ERCOT Protocols, for Single Model Entry Go Live.
If necessary, due to the tight timelines, ERCOT may request an email vote from TAC for certification.

## Slide 14: Go-Live Plan: Will encompass key activities/actions post the successful completion of the 168-Hr test
Key Elements of the plan include:
  ERCOT and Market Participant engagement expectations
  Communications and ongoing health checks during the go-live period
  Phased Staging of production submission during cut-over
  Planned regression test of Nodal LFC
  Software environment controls (migration freeze)
  Contingency planning and guidelines for switch control back to zonal
Next Steps | Target Completion Date
Complete ERCOT review | April 7th
Present to TPTF for Vote | May 5th
Present to TAC for Vote | June 5th
Present to BoD | June 17th

## Slide 15: Schedule: Metric status for each of the Early Delivery Systems
(xx) – Number of metrics associated with a particular Release
EDS1 – Complete
EDS2 – Red resulting from ongoing issues with State Estimator
EDS3 – Red resulting from ACE testing. Will return to Yellow if TPTF approves revised testing approach.
EDS4 – Mostly unmeasured at this point, but inheriting Red status from recently moved Alarms Processing metric. Commercial Ops metrics being measured are Green
Overall Readiness – Yellow due to open issues on telemetry, modeling, and CIM
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
EDS 1
EDS 2
EDS 3
EDS 4
Today
MP Trials & NM Verification
SCED & LMP Posting for 6 months
ICCP / P2P
SE Tuning
E1 R2
E2 R3
E2 R4
E3 R5
E3 R6
LFC Testing
E3 R7
CRR Testing
E4 R9
CMM, DAM & RT Settlements, Verifiable Costs & Disputes
DAM, SASM & RUC execution, DAM Stability Test, EECP, DST, Compliance
E4 R8
168 Hr Test
Go Live Sequence
(1 EDS, 2 MP)
(3 EDS)
(5 EDS, 1 MP)
(2 EDS, 1 MP)
(3 MP)
(2 EDS, 2 MP)
(12 EDS, 2 MP)
(5 EDS, 3 MP)
Overall Readiness (15 metrics):
http://.scorecard.ercot.com
Releases
No change* in EDS status since last meeting
* As of 3.27.08

## Slide 16: Cost Element Summary
EAC Revised Budget and Forecast remain constant
Spending in January* was lower and reversed overrun through Dec.
Add’l $1.2 M in contingency earmarked (Testing and MPIM vendor extension)
*February actuals not available as of 3.27.08