## BULKINSERT
|  | Script ID | BULK INSERT |  | Power Point
|  | Script Name | BULK INSERT FOR USAGE AND BILLING
|  | Script Storyline | CR will create the Bulk Insert template for usage and billing sub-type. CR will verify that the new columns are present in the template as well as the new validations.
|  | Success Criteria | Bulk Insert csv file is successfully uploaded and the MarkeTrak issues are created in the GUI.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | MT RQMTS | 16 |  | TRACK | MarkeTrak |  | for the three scenarios: missing usage, disputed usage and 867.03F.
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | CR | CR | Create: Populate Bulk Insert template for usage and billing sub-type |  | CR populates requried fields for usage and billing sub-type for the following three scenarios: missing usage, disputed usage and 86703F | See Bulk Insert Method Appendix A
| Day 1 |  | 1 | CR | CR | CR saves as .csv comma separated file. |  | CR verifies .csv file contains the correct number of columns and the headings have been removed.
| Day 1 |  | 1 | CR | CR | Select: Bulk Insert from submit tree | GUI | CR selects Issue Type D2D and Issue Sub-type Usage/Billing- these are required. Description and comments are optional | Refer to User Guide Sections 8 for an example of submitting a Bulk Insert please continue to the process by using this example.
| Day 1 |  | 1 | CR | CR | Access TML to review MIR report for exceptions | TML | Open MIR report to verify issues have been created and resubmit any exceptions.
| Day 1 |  | 1 | CR | TDSP | CR verify that the issue was created with the correct information in the GUI | GUI