## Script Matrix
Script ID | Release | Script Name | Requirement
MTC01 | 1 | Connectivity Testing - API
MTIG1 | 2 | Inadvertent Gain - CR1 (Gaining CR) Submits | 25,27
MTIG2 | 2 | Inadvertent Gain - CR1 (Losing CR) Submits | 25,27
MTIG3 | 2 | ERCOT selects Invalid IAG - Inadvertent Gain - CR1 (Gaining CR) Submits | 25,27
MTIG4 | 2 | Gaining CR Disagrees - Inadvertent Gain - CR1 (Losing CR) Submits | 25,27
MTIG4 | 2 | Gaining CR Confirms that an Authorized Enrollment Was Received - Inadvertent Gain - CR1 (Losing CR) Submits MarkeTrak Issue | 25,27
MTIG6 | 2 | Duplicate Issue Scenario - Inadvertent Gain - CR1 (Losing CR) Submits | 25,27
MTBU1 | 2 | Billing and Usage -API | 16,10,8,4,5
MTBU2 | 2 | 997s/Project/Other | 11
MTMT1 | 2 | Missing Transaction - API | 13,35,36,10
MTCA1 | 2 | Cancel w/Approval - ERCOT Cancel | 28
MTCA2 | 2 | Cancel w/Approval - TDSP Cancel | 28,34
MTDV1 | 2 | DEV-IDR CR Submit | 30, 4, 5
MTDV2 | 2 | DEV - LSE - CR Submit | 31,32,
MTDV3 | 2 | DEV - LSE - TDSP Submit | 31,32,
MTPT1 | 2 | Premise Type | 37, 26
MTSN1 | 2 | Safety Net | 38
MTSO1 | 3 | Service Order | 39
MTMR1 | 3 | Move Out with Meter Removal | 40
MTRP1 | 3 | Reporting | 17
MTMP1 | 3 | Wrong MP Inovlved Transition - API | 33

## MTC01
|  | Script ID | MTC01 |  | Power Point
|  | Script Name | API Connectivity
|  | Script Storyline | CR or TDSP complete API pull for Query List . (Query detail update and insert will be tested in other MT scripts)
|  | Success Criteria | CR or TDSP will verify that data was received from the Query List API call and that it is a correctly formated XML query list response.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | N/A | N/A | N/A | N/A | N/A
|  | Operating Rule | N/A |  | TRACK | MarkeTrak API
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 0 | 1 | ERCOT | CR or TDSP | Email WSDL/XSDs, URL, and digital certificates: ERCOT | Email | ERCOT Emails WSDL/XSDs, URL, digital certificate and. to CR and TDSP connectivity contacts. | Schedule Connectivity date/time ERCOT to email Matrix & Connectivity Schedule by 5/7
|  |  | 1 | CR or TDSP |  | Load new WSDL/XSDs, URL, and digital certificate, : CR or TDSP |  |  | Must be loaded by 5/16
|  |  | 1 | CR or TDSP | ERCOT | Initiate Connectivity |  | API contact will initiate "Query List" | May 20 - 27
|  |  | 1 | CR or TDSP | ERCOT | Email status: CR or TDSP | Email | CR or TDSP will email ERCOT the status of the data received by Success/Failure Query List | Complete Connectivity by 5/27

## MTIG1
| Script ID | MTIG1 |  | Power Point
| Script Name | Inadvertent Gain - CR1 (Gaining CR) Submits
| Script Storyline | CR1 (Gaining CR) creates an Inadvertent Gain MarkeTrak request. CR1 (Gaining CR) requests CR2 (Losing CR) to investigate the possibility of an Inadvertent Gain. All MP's agree an Inadvertent Gain occurred and CR2 (Losing CR) regains ESI ID as of the date of loss.
| Success Criteria | The MarkeTrak issue is agreed upon by all Market Participants involved (CR2 (Losing CR), CR1 (Gaining CR) and TDSP). CR2 (Losing CR) successfully submits the backdated MVI to regain the ESI ID and correctly inputs required information into the MarkeTrak system. All parties continue processing until the issue is complete.
| Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  | Residential |  |  | CR1 (Gaining CR)
| Operating Rule | 25,27 |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
| Number of TDSPs | 1
|  | ERCOT | TDSP | CR1
| PreTest Setup | None | None | None
Checkpoint Date | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | 1 | CR1 (Gaining CR) | CR1 (Gaining CR) | Create : CR1 (Gaining CR) | Submit via GUI | CR selects “Inadvertent Gain Issue Type/Sub Type = Inadvertent Gains-Gaining” from the MarkeTrak Submit Tree within MarkeTrak via GUI. CR enters Required Information | Note New Verbiage: - Change all language to read “Inadvertent Gain” rather than “Inadvertent Switch” to be consistent - Changing any IAS references to read IAG
|  | 1 | CR1 (Gaining CR) | CR1 (Gaining CR) | Create : CR1 (Gaining CR) | OK | CR selects "OK" to create issue
|  | 1 | CR1 (Gaining CR) | ERCOT | State: "New ERCOT" | OK | Premise Type is automatically populated | Note: - ERCOT as the Responsible Party - Premise Type is automatically populated
|  | 1 | ERCOT | ERCOT | State: "New ERCOT" | Begin Working | ERCOT selects "Begin Working" transition. ERCOT assigns CR1 (Gaining CR), CR2 (Losing CR) & TDSP. Provides Original Transaction Date. Indicates whether CR1 (Gaining CR) is Current Rep of Record | Note New Field(s): - Add Original Inadvertent Transaction Date to transition of “Select IAG Parties” - Add field to indicate whether the CR1 (Gaining CR) is still the REP of Record to transition of “Select IAG Parties"
|  | 1 | ERCOT | CR2 (Losing CR) | State: "In Progress ERCOT" | OK | ERCOT selects "OK" to move issue to CR2 (Losing CR) | Note: - ERCOT as the Responsible Party
|  | 1 | CR2 (Losing CR) | CR2 (Losing CR) | State: "New (Losing CR)" | Begin Working | CR2 (Losing CR) selects "Begin Working" transition. CR2 (Losing CR) investigates Inadvertent Gain to determine if CR2 (Losing CR) should regain ESI ID as of their date of loss. | Note: - CR2 (Losing CR) as the Responsible Party
|  | 1 | CR2 (Losing CR) | CR2 (Losing CR) | State: "In Progress (Losing CR)" | Send to TDSP | CR2 (Losing CR) selects "Send to TDSP" | Note New Button: - Send to TDSP (Comments Required) TDSP Note New Button: - "Begin Working"
|  | 1 | CR2 (Losing CR) | TDSP | State: "In Progress (Losing CR)" | OK | CR2 (Losing CR) enters proposed regain date. CR adds comments. CR selects "OK" | Note New Field(s): - Add “Proposed Regain Date” to the transition
|  | 1 | TDSP | TDSP | State: "New (TDSP)" | Begin Working | TDSP selects "Begin Working" | TDSP Note New Button: - "Begin Working" Note: - TDSP as the Responsible Party
|  | 1 | TDSP | CR2 (Losing CR) | State: "In Progress (TDSP)" | Ready to Receive | TDSP investigates the issue details. TDSP selects "Ready to Receive" | TDSP Note New Button: - "Ready to Receive"
|  | 1 | CR2 (Losing CR) | CR2 (Losing CR) | State: "New (Losing CR Submit)" | Begin Working | CR2 (Losing CR) selects "Begin Working".
|  | 1 | CR2 (Losing CR) | CR2 (Losing CR) | State: "In Progress (Submit Regaining)" | Provide Regaining BGN | CR2 (Losing CR) selects "Provide Regaining BGN". Provides BGN02 & Transaction Date for the submitted transaction | Note New Field(s): - Add field to “Provide Regaining BGN 02” transition to provide the BGN 02 of the submitted transaction - Add field to “Provide Regaining BGN 02” Transition to provide the transition date. (see BGN 02 # from transaction).
|  | 1 | CR2 (Losing CR) | Siebel | State: "Submit Regaining Transaction" | OK | CR2 (Losing CR) selects "OK".
The following rows will not be tested in market test but will be tested in ERCOT UAT. ERCOT will simulate Siebel activitiesas detailed below
|  | 1 | Siebel | Siebel | State: "Regaining Transaction Submitted" | Regaining Transaction Siebel Status | Siebel Will Automatically: - Check “Regaining Transaction Siebel Status” every 30 minutes using the BGN 02 from the new initiating transaction | Note New Field(s): - “Regaining Transaction Siebel Status” - BLANK?
|  | 1 | Siebel | Siebel | State: "Regaining Transaction Submitted" | Regaining Transaction Siebel Status | Siebel Will Automatically: - Update the issue with the current “Regaining Transaction Siebel Status” | Note New Field(s): - “Regaining Transaction Siebel Status” - In Review?
|  | 1 | Siebel | Siebel | State: "Regaining Transaction Siebel Status" | Regaining Transaction Siebel Status | Siebel Will Automatically: - Update the issue with the current “Regaining Transaction Siebel Status” | Note New Field(s): - “Regaining Transaction Siebel Status” - Scheduled?
|  | 1 | Siebel | CR1 (Gaining CR) | State: "Complete" | Regaining Transaction Siebel Status | Siebel Will Automatically: - Assign the state of “Complete” with the Submitting MP as the Responsible Party once the “Regaining Transaction Siebel Status” is ”Complete”. | Note New Field(s): - “Regaining Transaction Siebel Status” - Complete? Note: - Submitting CR1 (Gaining CR) as the Responsible Party

## MTIG2
| Script ID | MTIG2 |  | Power Point
| Script Name | Inadvertent Gain - CR1 (Losing CR) Submits
| Script Storyline | CR1 (Losing CR) creates an Inadvertent Gain MarkeTrak request. CR1 (Losing CR) requests CR2 (Gaining CR) to investigate the possibility of an Inadvertent Gain. All MP's agree an Inadvertent Gain occurred and CR1 (Losing CR) regains ESI ID as of the date of loss.
| Success Criteria | The MarkeTrak issue is agreed upon by all Market Participants involved (CR1 (Losing CR), CR2(Gaining CR) and TDSP). CR1 (Losing CR) successfully submits the backdated MVI to regain the ESI ID and correctly inputs required information into the MarkeTrak system. All parties continue processing until the issue is complete
| Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  | Residential |  |  | CR2 (Gaining CR)
| Operating Rule | 25,27 |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
| Number of TDSPs | 1
|  | ERCOT | TDSP | CR1
| PreTest Setup | None | None | None
Checkpoint Date | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | 1 | CR1 (Losing CR) | CR1 (Losing CR) | Create : CR1 (Losing CR) | Submit via GUI | CR1 (Losing CR) selects “Inadvertent Gain Issue Type/Sub Type = Inadvertent Gains-Losing” from the MarkeTrak Submit Tree within MarkeTrak via GUI. CR enters Required Information | Note New Verbiage: - Change all language to read “Inadvertent Gain” rather than “Inadvertent Switch” to be consistent - Changing any IAS references to read IAG
|  | 1 | CR1 (Losing CR) | CR1 (Losing CR) | Create : CR1 (Losing CR) | OK | CR1 (Losing CR) selects "OK" to create issue
|  | 1 | CR1 (Losing CR) | ERCOT | State: "New ERCOT" | OK | Premise Type is automatically populated | Note: - ERCOT as the Responsible Party - Premise Type is automatically populated
|  | 1 | ERCOT | ERCOT | State: "New ERCOT" | Begin Working | ERCOT selects "Begin Working". Assigns CR1 (Losing CR), CR2 (Gaining CR) & TDSP. Provides Original Transaction Date. Indicates whether CR2 (Gaining CR) is Current Rep of Record | Note New Field(s): - Add Original Inadvertent Transaction Date to transition of “Select IAG Parties” - Add field to indicate whether the CR2 (Gaining CR) is still the REP of Record to transition of “Select IAG Parties”
|  | 1 | ERCOT | CR2 (Gaining CR) | State: "In Progress ERCOT" | OK | ERCOT selects "OK" to move issue to CR2 (Gaining CR). | Note: - ERCOT as the Responsible Party
|  | 1 | CR2 (Gaining CR) | CR2 (Gaining CR) | State: "New (Gaining CR)" | Begin Working | CR2 (Gaining CR) selects "Begin Working". Investigates Inadvertent Gain to determine if CR1 (Losing CR) should regain ESI ID as of their date of loss. | Note: - CR2 (Gaining CR) as the Responsible Party
|  | 1 | CR2 (Gaining CR) | CR2 (Gaining CR) | State: "In Progress (Gaining CR)" | Send to Losing CR | CR2 (Gaining CR) selects "Send to Losing CR". CR2 (Gaining CR) enters Comments. | Note New Button: - "Send to Losing CR" (Comments Required)
|  | 1 | CR2 (Gaining CR) | CR2 (Gaining CR) | State: "In Progress (Gaining CR)" | OK | CR2 (Gaining CR) selects "OK" to move issue to CR1 (Losing CR).
|  | 1 | CR2 (Gaining CR) | CR1 (Losing CR) | State: "New (Losing CR)" | Begin Working | CR1 (Losing CR) selects "Begin Working". Investigates MarketConditions to determine date of loss | Note: - CR1 (Losing CR) as the Responsible Party
|  | 1 | CR1 (Losing CR) | CR1 (Losing CR) | State: "In Progress (Losing CR)" | Send to TDSP | CR1 (Losing CR) selects "Send to TDSP". | Note New Button: - Send to TDSP (Comments Required)
|  | 1 | CR1 (Losing CR) | TDSP | State: "In Progress (Losing CR)" | OK | CR1 (Losing CR) enters proposed regain date. Adds comments. Selects "OK" to move issue to TDSP | Note New Field(s): - Add “Proposed Regain Date” to the transition
|  | 1 | TDSP | TDSP | State: "New (TDSP)" | Begin Working | TDSP selects "Begin Working" | TDSP Note New Button: - "Begin Working" Note: - TDSP as the Responsible Party
|  | 1 | TDSP | CR2 (Gaining CR) | State: "In Progress (TDSP)" | Ready to Receive | TDSP investigates the issue details. TDSP selects "Ready to Receive" | TDSP Note New Button: - "Ready to Receive"
|  | 1 | CR1 (Losing CR) | CR1 (Losing CR) | State: "New (Losing CR Submit)" | Begin Working | CR1 (Losing CR) selects "Begin Working".
|  | 1 | CR1 (Losing CR) | CR1 (Losing CR) | State: "In Progress (Submit Regaining)" | Provide Regaining BGN | CR1 (Losing CR) selects "Provide Regaining BGN". Provides BGN02 & Transaction Date for the submitted transaction | Note New Field(s): - Add field to “Provide Regaining BGN 02” transition to provide the BGN 02 of the submitted transaction - Add field to “Provide Regaining BGN 02” Transition to provide the transition date
The following rows will not be tested in market test but will be tested in ERCOT UAT. ERCOT will simulate Siebel activitiesas detailed below
|  | 1 | CR1 (Losing CR) | Siebel | State: "Submit Regaining Transaction" | OK | CR1 (Losing CR): - Selects "OK"
|  | 1 | Siebel | Siebel | State: "Regaining Transaction Submitted" | Regaining Transaction Siebel Status | Siebel Will Automatically: - Check “Regaining Transaction Siebel Status” every 30 minutes using the BGN 02 from the new initiating transaction | Note New Field(s): - “Regaining Transaction Siebel Status” - BLANK?
|  | 1 | Siebel | Siebel | State: "Regaining Transaction Submitted" | Regaining Transaction Siebel Status | Siebel Will Automatically: - Update the issue with the current “Regaining Transaction Siebel Status” | Note New Field(s): - “Regaining Transaction Siebel Status” - In Review?
|  | 1 | Siebel | Siebel | State: "Regaining Transaction Siebel Status" | Regaining Transaction Siebel Status | Siebel Will Automatically: - Update the issue with the current “Regaining Transaction Siebel Status” | Note New Field(s): - “Regaining Transaction Siebel Status” - Scheduled?
|  | 1 | Siebel | CR1 (Losing CR) | State: "Complete" | Regaining Transaction Siebel Status | Siebel Will Automatically: - Assign the state of “Complete” with the Submitting MP as the Responsible Party once the “Regaining Transaction Siebel Status” is ”Complete”. | Note New Field(s): - “Regaining Transaction Siebel Status” - Complete? Note: - Submitting CR1 (Losing CR) as the Responsible Party

## MTIG3
| Script ID | MTIG4 |  | Power Point
| Script Name | Gaining CR Disagrees - Inadvertent Gain - CR1 (Losing CR) Submits
| Script Storyline | CR1 (Losing CR) creates an Inadvertent Gain MarkeTrak request. CR1 (Losing CR) requests CR2 (Gaining CR) to investigate the possibility of an Inadvertent Gain. CR2 (Gaining CR) Disagrees.
Success Criteria
| Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  | Residential |  |  | CR2 (Gaining CR)
| Operating Rule | 25,27 |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
| Number of TDSPs | 1
|  | ERCOT | TDSP | CR1
| PreTest Setup | None | None | None
Checkpoint Date | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | 1 | CR1 (Losing CR) | CR1 (Losing CR) | Create : CR1 (Losing CR) | Submit via GUI | CR1 (Losing CR) selects “Inadvertent Gain Issue Type/Sub Type = Inadvertent Gains-Losing” from the MarkeTrak Submit Tree within MarkeTrak via GUI. CR1 (Losing CR) enters required information | Note New Verbiage: - Change all language to read “Inadvertent Gain” rather than “Inadvertent Switch” to be consistent - Changing any IAS references to read IAG
|  | 1 | CR1 (Losing CR) | CR1 (Losing CR) | Create : CR1 (Losing CR) | OK | CR1 (Losing CR) selects "OK" to create issue
|  | 1 | CR1 (Losing CR) | ERCOT | State: "New ERCOT" | OK | Premise Type is automatically populated | Note: - ERCOT as the Responsible Party - Premise Type is automatically populated
|  | 1 | ERCOT | ERCOT | State: "New ERCOT" | Begin Working | ERCOT selects "Begin Working". ERCOT assigns CR1 (Losing CR), CR2 (Gaining CR) & TDSP, provides Original Transaction Date, and Indicates whether CR2 (Gaining CR) is Current Rep of Record | Note New Field(s): - Add Original Inadvertent Transaction Date to transition of “Select IAG Parties” - Add field to indicate whether the CR2 (Gaining CR) is still the REP of Record to transition of “Select IAG Parties”
|  | 1 | ERCOT | CR2 (Gaining CR) | State: "In Progress ERCOT" | OK | ERCOT selects "OK" to move issue to CR2 (Gaining CR) | Note: - ERCOT as the Responsible Party
|  | 1 | CR2 (Gaining CR) | CR2 (Gaining CR) | State: "New (Gaining CR)" | Begin Working | CR2 (Gaining CR) selects "Begin Working". Investigates Inadvertent Gain to determine if CR1 (Losing CR) should regain ESI ID as of their date of loss | Note: - CR2 (Gaining CR) as the Responsible Party
|  | 1 | CR2 (Gaining CR) | CR2 (Gaining CR) | State: "In Progress (Gaining CR)" | Send to Losing CR | CR2 (Gaining CR) selects "Send to Losing CR". CR2 (Gaining CR) enters "Comments". | Note New Button: - "Send to Losing CR" (Comments Required)
|  | 1 | CR2 (Gaining CR) | CR2 (Gaining CR) | State: "In Progress (Gaining CR)" | OK | CR2 (Gaining CR) selects "OK" to move issue to CR1 (Losing CR).
|  | 1 | CR2 (Gaining CR) | CR1 (Losing CR) | State: "New (Losing CR)" | Begin Working | CR1 (Losing CR) selects "Begin Working". Investigates comments from Gaining CR and determine resolution. | Note: - CR1 (Losing CR) as the Responsible Party
|  | 1 | CR1 (Losing CR) | CR1 (Losing CR) | State: "In Progress (Losing CR)" | “Send to Gaining CR” or “Send to TDSP” or “Unexecutable” | CR1 (Losing CR) selects “Send to Gaining CR” or “Send to TDSP” or “Unexecutable” | Note New Button: - “Send to Gaining CR” or “Send to TDSP” or “Unexecutable” - Comments Required

## MTIG4
| Script ID | MTIG4 |  | Power Point
| Script Name | Gaining CR Confirms that an Authorized Enrollment Was Received - Inadvertent Gain - CR1 (Losing CR) Submits MarkeTrak Issue
| Script Storyline | CR1 (Losing CR) creates an Inadvertent Gain MarkeTrak request. CR1 (Losing CR) requests CR2 (Gaining CR) to investigate the possibility of an Inadvertent Gain. CR2 (Gaining CR) Gaining CR Confirms that an Authorized Enrollment Was Received.
Success Criteria
| Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  | Residential |  |  | CR2 (Gaining CR)
| Operating Rule | 25,27 |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
| Number of TDSPs | 1
|  | ERCOT | TDSP | CR1
| PreTest Setup | None | None | None
Checkpoint Date | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | 1 | CR1 (Losing CR) | CR1 (Losing CR) | Create : CR1 (Losing CR) | Submit via GUI | CR1 (Losing CR) selects “Inadvertent Gain Issue Type/Sub Type = Inadvertent Gains-Losing” from the MarkeTrak Submit Tree within MarkeTrak via GUI. CR1 (Losing CR) enters required information. | Note New Verbiage: - Change all language to read “Inadvertent Gain” rather than “Inadvertent Switch” to be consistent - Changing any IAS references to read IAG
|  | 1 | CR1 (Losing CR) | CR1 (Losing CR) | Create : CR1 (Losing CR) | OK | CR1 (Losing CR) selects "OK" to create issue
|  | 1 | CR1 (Losing CR) | ERCOT | State: "New ERCOT" | OK | Premise Type is automatically populated | Note: - ERCOT as the Responsible Party - Premise Type is automatically populated
|  | 1 | ERCOT | ERCOT | State: "New ERCOT" | Begin Working | ERCOT selects "Begin Working". ERCOT assigns CR1 (Losing CR), CR2 (Gaining CR) & TDSP, provides Original Transaction Date, and indicates whether CR2 (Gaining CR) is Current Rep of Record. | Note New Field(s): - Add Original Inadvertent Transaction Date to transition of “Select IAG Parties” - Add field to indicate whether the CR2 (Gaining CR) is still the REP of Record to transition of “Select IAG Parties”
|  | 1 | ERCOT | CR2 (Gaining CR) | State: "In Progress ERCOT" | OK | ERCOT selects "OK" to move issue to CR2 (Gaining CR). | Note: - ERCOT as the Responsible Party
|  | 1 | CR2 (Gaining CR) | CR2 (Gaining CR) | State: "New (Gaining CR)" | Begin Working | CR2 (Gaining CR) selects "Begin Working". Investigates Inadvertent Gain to determine if CR1 (Losing CR) should regain ESI ID as of their date of loss | Note: - CR2 (Gaining CR) as the Responsible Party
|  | 1 | CR2 (Gaining CR) | CR2 (Gaining CR) | State: "In Progress (Gaining CR)" | Unexecutable | CR2 (Gaining CR) determines Valid Enrollment Request from Customer thus Inadvertent Gain is invalid. CR2 (Gaining CR) selects "Unexecutable".
|  | 1 | CR2 (Gaining CR) | CR2 (Gaining CR) | State: "In Progress (Gaining CR)" | Authorized Enrollment Confirmed | CR2 (Gaining CR) selects "Authorized Enrollment Confirmed" from the drop down box. CR2 (Gaining CR) enters "Comments". | Note Drop Down Box: - "Authorized Enrollment Confirmed" (Comments Required)
|  | 1 | CR2 (Gaining CR) | CR2 (Gaining CR) | State: "In Progress (Gaining CR)" | OK | CR2 (Gaining CR) selects "OK" to move issue to "Complete"
|  | 1 | CR2 (Gaining CR) | CR1 (Losing CR) | State: "Complete" | OK |  | Note: - Issue Complete with CR1 (Losing CR) - Submitting CR as the Responsible Party

## MTIG5
| Script ID | MTIG5 |  | Power Point
| Script Name | Losing CR Disagrees with Issue - Inadvertent Gain - CR1 (Gaining CR) Submits
| Script Storyline | CR1 (Gaining CR) creates an Inadvertent Gain MarkeTrak request. CR1 (Gaining CR) requests CR2 (Losing CR) to investigate the possibility of an Inadvertent Gain. CR2 (Losing CR) disagrees.
| Success Criteria | CR2 (Losing CR) disagrees.
| Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  | Residential |  |  | CR1 (Gaining CR)
| Operating Rule | 25,27 |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
| Number of TDSPs | 1
|  | ERCOT | TDSP | CR1
| PreTest Setup | None | None | None
Checkpoint Date | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | 1 | CR1 (Gaining CR) | CR1 (Gaining CR) | Create : CR1 (Gaining CR) | Submit via GUI | CR1 (Gaining CR) selects “Inadvertent Gain Issue Type/Sub Type = Inadvertent Gains-Gaining” from the MarkeTrak Submit Tree within MarkeTrak via GUI. CR1 (Gaining CR) enters required information. | Note New Verbiage: - Change all language to read “Inadvertent Gain” rather than “Inadvertent Switch” to be consistent - Changing any IAS references to read IAG
|  | 1 | CR1 (Gaining CR) | CR1 (Gaining CR) | Create : CR1 (Gaining CR) | OK | CR1 (Gaining CR) selects "OK" to create issue.
|  | 1 | CR1 (Gaining CR) | ERCOT | State: "New ERCOT" | OK | Premise Type is automatically populated | Note: - ERCOT as the Responsible Party - Premise Type is automatically populated
|  | 1 | ERCOT | ERCOT | State: "New ERCOT" | Begin Working | ERCOT selects "Begin Working". ERCOT assigns CR1 (Gaining CR), CR2 (Losing CR) & TDSP, provides Original Transaction Date, and indicates whether CR1 (Gaining CR) is Current Rep of Record. | Note New Field(s): - Add Original Inadvertent Transaction Date to transition of “Select IAG Parties” - Add field to indicate whether the CR1 (Gaining CR) is still the REP of Record to transition of “Select IAG Parties"
|  | 1 | ERCOT | CR2 (Losing CR) | State: "In Progress ERCOT" | OK | ERCOT selects "OK" to move issue to CR2 (Losing CR). | Note: - ERCOT as the Responsible Party
|  | 1 | CR2 (Losing CR) | CR2 (Losing CR) | State: "New (Losing CR)" | Begin Working | CR2 (Losing CR) selects "Begin Working". Investigates Inadvertent Gain to determine if CR2 (Losing CR) should regain ESI ID as of their date of loss. | Note: - CR2 (Losing CR) as the Responsible Party
|  | 1 | CR2 (Losing CR) | CR2 (Losing CR) | State: "In Progress (Losing CR)" | Send to Gaining CR | CR2 (Losing CR) determines Valid Enrollment Request from Customer thus Inadvertent Gain is invalid. Selects “Send to Gaining CR” | Note New Button: - Send to Gaining CR (Comments Required)
|  | 1 | CR2 (Losing CR) | CR2 (Losing CR) | State: "In Progress (Losing CR)" | OK | CR2 (Losing CR) selects "OK" to move issue to CR1 (Gaining CR).
|  | 1 | CR2 (Losing CR) | CR1 (Gaining CR) | State: "New (Gaining CR)" | Begin Working | CR1 (Gaining CR) selects "Begin Working". Investigates Inadvertent Gain to determine if CR2 (Losing CR) should regain ESI ID as of their date of loss. | Note: - CR1 (Gaining CR) as the Responsible Party
|  | 1 | CR1 (Gaining CR) | CR1 (Gaining CR) | State: "In Progress (Gaining CR)" | Send to Losing CR | CR1 (Gaining CR) selects "Send to Losing CR" CR1 (Gaining CR) enters "Comments". | Note New Button: - "Send to Losing CR" (Comments Required)
|  | 1 | CR1 (Gaining CR) | CR2 (Losing CR) | State: "In Progress (Gaining CR)" | OK | CR1 (Gaining CR) selects "OK" to move issue to CR2 (Losing CR).
|  | 1 | CR2 (Losing CR) | CR2 (Losing CR) | State: "New (Losing CR)" | Begin Working | CR2 (Losing CR) selects "Begin Working". CR2 (Losing CR) investigates comments from Gaining CR and determaine resolution. | Note: - CR2 (Losing CR) as the Responsible Party
|  | 1 | CR2 (Losing CR) | CR2 (Losing CR) | State: "In Progress (Losing CR)" | “Send to Unexecutable” | CR2 (Losing CR) selects “Unexecutable”. | Note New Button: - “Unexecutable” - Comments Required

## MTIG6
| Script ID | MTIG9 |  | Power Point
| Script Name | TDSP Request updated Proposed Regain Date - Inadvertent Gain - CR1 (Gaining CR) Submits
| Script Storyline | CR1 (Gaining CR) creates an Inadvertent Gain MarkeTrak request. TDSP Request updated Proposed Regain Date (Gaining CR is submitter). CR1 (Gaining CR) requests CR2 (Losing CR) to investigate the possibility of an Inadvertent Gain. TDSP request updated proposed regain date. All MP's agree an Inadvertent Gain occurred and CR2 (Losing CR) regains ESI ID as of the date of loss.
| Success Criteria | TDSP Request updated Proposed Regain Date. The MarkeTrak issue is ultimately agreed upon by all Market Participants involved (CR1 (Gaining CR), CR2(Losing CR) and TDSP) and CR1 (Gaining CR) successfully submits the backdated MVI to regain the ESI ID and correctly inputs required information into the MarkeTrak system. All parties continue processing until the issue is complete
| Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  | Residential |  |  | CR2 (Gaining CR)
| Operating Rule | 25,27 |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
| Number of TDSPs | 1
|  | ERCOT | TDSP | CR1
| PreTest Setup | None | None | None
Checkpoint Date | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | 1 | CR1 (Gaining CR) | CR1 (Gaining CR) | Create : CR1 (Gaining CR) | Submit via GUI | CR1 (Gaining CR) selects “Inadvertent Gain Issue Type/Sub Type = Inadvertent Gains-Gaining” from the MarkeTrak Submit Tree within MarkeTrak via GUI. CR enters required information. | Note New Verbiage: - Change all language to read “Inadvertent Gain” rather than “Inadvertent Switch” to be consistent - Changing any IAS references to read IAG
|  | 1 | CR1 (Gaining CR) | CR1 (Gaining CR) | Create : CR1 (Gaining CR) | OK | CR1 (Gaining CR) selects "OK" to create issue.
|  | 1 | CR1 (Gaining CR) | ERCOT | State: "New ERCOT" | OK | Premise Type is automatically populated | Note: - ERCOT as the Responsible Party - Premise Type is automatically populated
|  | 1 | ERCOT | ERCOT | State: "New ERCOT" | Begin Working | ERCOT selects "Begin Working". ERCOT assigns CR1 (Gaining CR), CR2 (Losing CR) & TDSP, provides Original Transaction Date, and indicates whether CR1 (Gaining CR) is Current Rep of Record. | Note New Field(s): - Add Original Inadvertent Transaction Date to transition of “Select IAG Parties” - Add field to indicate whether the CR1 (Gaining CR) is still the REP of Record to transition of “Select IAG Parties"
|  | 1 | ERCOT | CR2 (Losing CR) | State: "In Progress ERCOT" | OK | ERCOT selects "OK" to move issue to CR2 (Losing CR). | Note: - ERCOT as the Responsible Party
|  | 1 | CR2 (Losing CR) | CR2 (Losing CR) | State: "New (Losing CR)" | Begin Working | CR2 (Losing CR) selects "Begin Working". Investigates Inadvertent Gain to determine if CR2 (Losing CR) should regain ESI ID as of their date of loss | Note: - CR2 (Losing CR) as the Responsible Party
|  | 1 | CR2 (Losing CR) | CR2 (Losing CR) | State: "In Progress (Losing CR)" | Send to TDSP | CR2 (Losing CR) selects "Send to TDSP". | Note New Button: - Send to TDSP (Comments Required)
|  | 1 | CR2 (Losing CR) | TDSP | State: "In Progress (Losing CR)" | OK | CR2 (Losing CR) enters proposed regain date, adds comments, and selects "OK" | Note New Field(s): - Add “Proposed Regain Date” to the transition
|  | 1 | TDSP | TDSP | State: "New (TDSP)" | Begin Working | TDSP selects "Begin Working". | TDSP Note New Button: - "Begin Working" Note: - TDSP as the Responsible Party
|  | 1 | TDSP | TDSP | State: "In Progress (TDSP)" | Request Updated Proposed Regain Date | TDSP investigates the issue details. TDSP selects “Request Updated Proposed Regain Date”. | TDSP Note New Button: - “Request Updated Proposed Regain Date”
|  | 1 | TDSP | CR2 (Losing CR) | State: "In Progress (TDSP)" | OK | TDSP selects "OK" to move issue to CR2 (Losing CR), TDSP enters "Comments". | Note: - “Proposed Regain Date” is Cleared
|  | 1 | CR2 (Losing CR) | CR2 (Losing CR) | State: "New (Losing CR Submit)" | Begin Working | CR2 (Losing CR) selects "Begin Working". Investigates Inadvertent Gain to determine if CR2 (Losing CR) should regain ESI ID as of their date of loss. | Note: - CR2 (Losing CR) as the Responsible Party
|  | 1 | CR2 (Losing CR) | CR2 (Losing CR) | State: "In Progress (Losing CR)" | Send to TDSP | CR2 (Losing CR) selects "Send to TDSP". | Note New Button: - Send to TDSP (Comments Required)
|  | 1 | CR2 (Losing CR) | TDSP | State: "In Progress (Losing CR)" | OK | CR2 (Losing CR) enters proposed regain date, adds comments, and selects "OK". | Note New Field(s): - Add “Proposed Regain Date” to the transition
|  | 1 | TDSP | TDSP | State: "New (TDSP)" | Begin Working | TDSP selects "Begin Working". | TDSP Note New Button: - "Begin Working" Note: - TDSP as the Responsible Party
|  | 1 | TDSP | CR2 (Losing CR) | State: "In Progress (TDSP)" | Ready to Receive | TDSP investigates the issue details. TDSP selects "Ready to Receive" | TDSP Note New Button: - "Ready to Receive"
|  | 1 | CR2 (Losing CR) | CR2 (Losing CR) | State: "New (Losing CR Submit)" | Begin Working | CR2 (Losing CR) selects "Begin Working". | Note: - CR2 (Losing CR) as the Responsible Party
|  | 1 | CR2 (Losing CR) | CR2 (Losing CR) | State: "In Progress (Losing CR Submit)" | Provide Regaining BGN | CR2 (Losing CR) selects "Provide Regaining BGN 02".
|  | 1 | CR2 (Losing CR) | CR2 (Losing CR) | State: "In Progress (Losing CR Submit)" | Provide Regaining BGN | CR2 (Losing CR) provides BGN 02 & Transaction Date for the submitted transaction. | Note New Field(s): - Add field to “Provide Regaining BGN 02” transition to provide the BGN 02 of the submitted transaction - Add field to “Provide Regaining BGN 02” Transition to provide the transition date.
|  | 1 | CR2 (Losing CR) | Siebel | State: "Submit Regaining Transaction" | OK | CR2 (Losing CR) selects "OK".
The following rows will not be tested in market test but will be tested in ERCOT UAT. ERCOT will simulate Siebel activitiesas detailed below
|  | 1 | Siebel | Siebel | State: "Regaining Transaction Submitted" | Regaining Transaction Siebel Status | Siebel Will Automatically: - Check “Regaining Transaction Siebel Status” every 30 minutes using the BGN 02 from the new initiating transaction | Note New Field(s): - “Regaining Transaction Siebel Status” - BLANK?
|  | 1 | Siebel | Siebel | State: "Regaining Transaction Submitted" | Regaining Transaction Siebel Status | Siebel Will Automatically: - Update the issue with the current “Regaining Transaction Siebel Status” | Note New Field(s): - “Regaining Transaction Siebel Status” - In Review?
|  | 1 | Siebel | Siebel | State: "Regaining Transaction Siebel Status" | Regaining Transaction Siebel Status | Siebel Will Automatically: - Update the issue with the current “Regaining Transaction Siebel Status” | Note New Field(s): - “Regaining Transaction Siebel Status” - Scheduled?
|  | 1 | Siebel | CR1 (Gaining CR) | State: "Complete" | Regaining Transaction Siebel Status | Siebel Will Automatically: - Assign the state of “Complete” with the Submitting MP as the Responsible Party once the “Regaining Transaction Siebel Status” is ”Complete”. | Note New Field(s): - “Regaining Transaction Siebel Status” - Complete? Note: - Submitting CR1 (Gaining CR) as the Responsible Party

## MTBU1
|  | Script ID | MTBU1 |  | Power Point
|  | Script Name | Billing and Usage
|  | Script Storyline | CR submits MT issue for Billing and Usage (Missing Transaction). TDSP researchs MT issue and discovers that transaction is missing. TDSP will resolve issue and send Missing Transaction
|  | Success Criteria | One issue is downloaded and successfully processed and the results correctly uploaded to the MarkeTrak system. The TDSP continues processing until all issues are closed.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | MT RQMTS | 8, 10, and 16 |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | CR | TDSP | Create : CR | Submit via GUI | CR submits 1 issue into MarkeTrak via GUI. Issue Type/Sub Type = Billing and Usage from the drop down box. CR fills in Required fields. CR selects "Submit" | CR selects TDSP territory. MarkeTrak assures proper field information and checks for duplicate issue. "Transaction Drop Down Box" will include :867_03 Monthly 00, 867_03 Monthly 01, 867_03 Monthly 05, 867_03 Final, 810_02, 810_03. Comments in the "Comment Field" are optional. Verify New fields are present and required or optional
|  |  | 1 | TDSP | TDSP | State: New TDSP | Begin Working | TDSP selects "Begin Working" transition. MarkeTrak system updates state to - In Progress (Assignee)
|  |  | 1 | TDSP | CR | State: In Progress (Assignee) TDSP | Complete | TDSP investigates Billing and Usage issue and determaines that TDSP usage was not sent. TDSP resolves issue and sends missing transaction. TDSP selects the "Complete" transition. This will require you to enter the Tran Id. Then select OK. MarkeTrak system updates to state of Pending Complete. | New process - by selecting the "Complete" Transition a pop up screen will appear for the Tran id to be entered
|  |  | 1 | CR | CR | State: Pending Complete | Complete | CR selects the "Complete" transition. MarkeTrak system updates to state of Closed.

## MTBU2
|  | Script ID | MTBU2 |  | Power Point
|  | Script Name | 997, Projects, and Others
|  | Script Storyline | TDSP will select "Projects" from the submit tree, and validate that the "ISA Field" is present and optional (Cancel out back to submit tree). TDSP will select "Other" from the submit tree, and validate that the "ISA Field" is present and optional (Cancel out back to submit tree). TDSP will select "997" from the submit tree, and submit a "997" MT. CR researches the MT and discovers that the 997 was not sent. CR sends the 997 and resolves the issue.
|  | Success Criteria | One issue is downloaded and successfully processed and the results correctly uploaded to the MarkeTrak system. The TDSP continues processing until all issues are closed.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | MT RQMTS | 11 |  | TRACK | MarkeTrak API
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | TDSP | CR | Create: TDSP | Submit via GUI | TDSP selects "Projects" from the submit tree. TDSP validates that "ISA Field" is present. TDSP cancels the MT, and backs out to submit tree.
|  |  | 1 | TDSP | CR | Create : TDSP | Submit via GUI | TDSP selects "Other" from the submit tree. TDSP validates that "ISA Field" is present. TDSP cancels the MT, and backs out to submit tree.
|  |  | 1 | TDSP | CR | Create: TDSP | Submit via GUI | TDSP selects "997" from the submit tree. TDSP fills in required fields. TDSP clicks "OK" | Verify new field "ISA"
|  |  | 1 | CR | CR | State: New CR | Begin Working | CR selects the "Begin Working" transition. MarkeTrak system updates state to In Progress: CR.
|  |  | 1 | CR | CR | State: In Progress (Assignee) CR | Complete | CR researches the "997" MT, discovers that 997 was not sent. CR sends 997. CR then clicks on "Complete"
|  |  | 1 | TDSP | TDSP | State: Pending Complete | Return to Assignee | TDSP did not receive the 997. Therefore the TDSP returns to the Assignee with required "Comments". TDSP then selects "Return to Assignee".
|  |  | 1 | CR | CR | State: New CR | Begin Working | CR selects the "Begin Working" transition. MarkeTrak system updates state to In Progress: CR.
|  |  | 1 | CR | CR | State: In Progress (Assignee) CR | Complete | CR researches the "997" MT, discovers that 997 was not sent. CR sends 997. CR then clicks on "Complete"
|  |  | 1 | TDSP | TDSP | State: Pending Complete | Complete | TDSP receives 997, and then the TDSP selects "Complete". Issue transitioned to state of Closed.

## MTMT1
|  | Script ID | MTMT1 |  | Power Point
|  | Script Name | Missing Transaction
|  | Script Storyline | CR submits "Missing Transaction" MarkeTrak issue. TDSP researches the MT issue and discovers that the transaction was not sent. TDSP resolves the MT issue and sends missing transaction to CR.
|  | Success Criteria | One issue is downloaded and successfully processed and the results correctly uploaded to the MarkeTrak system. The TDSP continues processing until all issue is closed.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | MT RQMTS | 13, 35, 36, 10 |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | CR | TDSP | Create: CR | Submit via GUI | CR selects "Missing Transaction" from the submit tree. CR fills in required fields. CR clicks "OK" | Verify add service period start date is visible and "Optional"
|  |  | 1 | TDSP | TDSP | State: New TDSP | Begin Working | TDSP selects "Begin Working" transition. MarkeTrak system updates state to In Progress: TDSP
|  |  | 1 | TDSP | CR | State: In Progress (Assignee) TDSP | Comments | TDSP select the 'Add Comments" button. TDSP inputs the following 'working on getting read performed' In the comment field. TDSP clicks OK.
|  |  | 1 | CR | TDSP | State: In Progress (Assignee) TDSP | E-Mail Responsible MP | CR requests update on MarkeTrak issue. Customer requested urgency. | Email will be saved and attached to the issue.
|  |  | 1 | TDSP | CR | State: In Progress (Assignee) TDSP | Complete | TDSP sends the missing transaction. TDSP completes the MT issue. TDSP may add "Comments". TDSP selects "Complete".
|  |  | 1 | CR | CR | State: Pending Complete CR | Complete | CR selects "Complete". MarkeTrak system updates state to Closed.

## MTCA1
|  | Script ID | MTCA1 |  | Power Point
|  | Script Name | Cancel with Approval
|  | Script Storyline | CR creates a Cancel with Approval issue and uploads to ERCOT MarkeTrak. ERCOT receives and performs applicable validation, assigns the priority indicator to "yes" and makes the issue accessible to the TDSP. The TDSP will retrieve the isssue and approve ERCOT cancel.
|  | Success Criteria | One priority issue is logged and successfully processed and the results correctly uploaded to the MarkeTrak system. All new MarkeTrak functionality is successfully tested.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | Operating Rule | 28 |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | CR | ERCOT | Create: CR | Submit via GUI | CR submits 1 issue into MarkeTrak via GUI. Issue Type = Cancel with Approval | CR initiates cancel with approval MarkeTrak issue through their GUI CR confirm the new field "Priority Designation" is shown and populates scheduled meter read date
|  |  | 1 | CR | ERCOT | State: New ERCOT | Begin Working | ERCOT will retrieve new Cancel with Approval issue and select the "Begin Working"transition.
The following row will not be tested in market test but will be tested in ERCOT UAT.
|  |  | 1 | CR | MarkeTrak | <Create> |  | MarkeTrak will retrieve new Cancel with Approval issue and perform applicable validations and assign an issue number. Assigns priority based on SMRD Priority = Y | Create transition complete and issue moves to state New
|  |  | 1 | ERCOT | TDSP | State: New TDSP | Begin Working | TDSP retrieves new Cancel with Approval issue with Priority indicator and selects the "Begin Working" transition. The MarkeTrak system trasitions to a state of In Progress TDSP | This will change the state from "New" to "In Progress"
|  |  | 1 | TDSP | TDSP | State: In Progress TDSP | ERCOT Cancel | TDSP selects "ERCOT Cancel" and updates MarkeTrak GUI with comments. TDSP approves ERCOT to send cancel 814_08. | Make sure button reads "ERCOT Cancel"
|  |  | 1 | TDSP | ERCOT | State: New (ERCOT) ERCOT | Begin Working | TDSP selects "Begin Working". MarkeTrak will update to "In Progress (ERCOT)"
|  |  | 1 | ERCOT | ERCOT | State: In Progress (ERCOT) ERCOT | Item Cancelled | ERCOT selects "Item Cancelled" after sending 814_08. | Siebel Status/Sub Status will automatically update with transition
|  |  | 1 | ERCOT | CR | State: Complete CR | Complete | ERCOT selects "Complete"

## MTCA2
|  | Script ID | MTCA2 |  | Power Point
|  | Script Name | Cancel with Approval - TDSP Cancel
|  | Script Storyline | CR creates a Cancel with Approval issue and uploads to ERCOT MarkeTrak. ERCOT receives and performs applicable validation, assigns the priority indicator to "yes" and makes the issue accessible to the TDSP. The TDSP will retrieve the isssue and submit cancel.
|  | Success Criteria | One issue is downloaded and successfully processed and the results correctly uploaded to the MarkeTrak system. All new MarkeTrak functionality is successfully tested.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | Operating Rule | 28,34 |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | CR | ERCOT | Create: CR | Submit via GUI | CR submits 1 issue into MarkeTrak via GUI. Issue Type = Cancel with Approval | CR initiates cancel with approval MarkeTrak issue through their GUI
|  |  | 1 | CR | ERCOT | State: New ERCOT | Begin Working | ERCOT will retrieve new Cancel with Approval issue and select the "Begin Working"transition.
The following row will not be tested in market test but will be tested in ERCOT UAT.
|  |  | 1 | CR | MarkeTrak | <Create> |  | MarkeTrak will retrieve new Cancel with Approval issue and perform applicable validations and assign an issue number. Assigns priority based on SMRD Priority = Y | Create transition complete and issue moves to state New
|  |  | 1 | TDSP | TDSP | State: New TDSP | Begin Working | TDSP selects "Begin Working". TDSP retrieves new Cancel with Approval issue with Priority indicator. | This will change the state from "New" to "In Progress"
|  |  | 1 | TDSP | TDSP | State: In Progress TDSP | TDSP Cancel | TDSP selects "TDSP Cancel" and verifies the new button is available | Simulate : TDSP sending 814_28
|  |  | 1 | TDSP | CR | Cancelled (PC) | Pending Complete | Once ERCOT receives the 814_28 with BGN07~09, the issue state will transition to Pending Complete | Note: Will remain at ERCOT until "siebel status/sub-status" Cancelled. Then it returns to submitting MP as complete

## MTDV1
|  | Script ID | MTDV1 |  | Power Point
|  | Script Name | DEV-IDR CR Submit
|  | Script Storyline | CR submits DEV-IDR MarkeTrak where usage exists in MP's system but not in ERCOT's system. CR will transition to TDSP. TDSP will research the MT and agree to the MT. TDSP continues processing until the issue is closed
|  | Success Criteria | One issue is downloaded and successfully processed and the results correctly uploaded to the MarkeTrak system. MP is able to verify that the usage exists in ERCOT system. The TDSP continues processing until the issue is closed.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | MT RQMTS | 30 |  | TRACK | MarkeTrak API
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | CR | TDSP | Create: CR | Submit via GUI | CR selects "IDR in MP System not ERCOT" from the submit tree. CR fills in all required fields. CR clicks "OK" | CR checks that "New Total" is a required field.
|  |  | 1 | TDSP | TDSP | State: New TDSP | Begin Working | TDSP selects "Begin Working". MarkeTrak system updates state to - In Progress (Assignee)
|  |  | 1 | TDSP | CR | State: In Progress (Assignee) TDSP | Complete | TDSP researches the "New Total" and compares to their system. Upon review TDSP agrees with CR. TDSP will resend transaction to update 727 usage. TDSP selects "Complete"
|  |  | 1 | CR | CR | State Pending Complete CR | Complete | CR verifies 727 extract. CR then selects the "Complete" transition. MarkeTrak system will update to state of "closed"

## MTDV2
|  | Script ID | MTDV2 |  | Power Point
|  | Script Name | DEV-LSE CR Submit
|  | Script Storyline | CR submits MarkeTrak with modification of start time and stop time. ERCOT will review MT and perform their validations. If the MT passes validation, it is transitioned to the TDSP to begin working. TDSP will review MT, compare to their system, and modify the start and stop time. The CR will agree with modifications. Next, ERCOT will update the 727 service history. CR verifies changes were made and closes the issue.
|  | Success Criteria | One issue is downloaded and successfully processed and the results correctly uploaded to the MarkeTrak system. MP is able to verify that the service history exists in ERCOT system via 727 extract. The TDSP continues processing until the issue is closed.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | MT RQMTS | 31, 32 |  | TRACK | MarkeTrak API
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | CR | ERCOT | Create: CR | GUI | CR selects "LSE Date Change Start and Stop" from the submit tree. CR fills in all required fields. CR clicks "OK"
|  |  | 1 | ERCOT | ERCOT | State: New ERCOT | Begin Working | ERCOT selects "Begin Working". ERCOT validates the MT against their internal data. ERCOT agrees and transitions the issue to the TDSP.
|  |  | 1 | ERCOT | TDSP | State: In Progress (ERCOT) ERCOT | Passed Analysis | ERCOT completes required fields. ERCOT selects "Passed Analysis" transition.
|  |  | 1 | TDSP | TDSP | State: New (Pending Approval) TDSP | Begin Working | TDSP selects "Begin Working". MarkeTrak system updates state to - In Progress (Pending Approval)
|  |  | 1 | TDSP | CR | State: In Progress (Pending Approval) TDSP | Modify and reassign | TDSP selects "Modify/Reassign". TDSP inputs modified "Start and Stop Time". TDSP clicks "OK" | The issues comments will now contain a log of the changes made using the "Modify/Reassign" transition on the "New StartTime" and "New StopTime" fields.
|  |  | 1 | CR | CR | State: New (Pending Approval) CR | Begin Working | CR selects "Begin Working". CR agrees with the modifications.
|  |  | 1 | CR | ERCOT | State: In Progress (Pending Approval) CR | Update Approved | CR selects "Updated Approved". CR must select 'OK' to complete transition.
|  |  | 1 | ERCOT | ERCOT | State: New (ERCOT Resolve) ERCOT | Begin Working | ERCOT selects "Begin Working".
|  |  | 1 | ERCOT | ERCOT | State: In Progress (ERCOT Resolve) ERCOT | Additional Info Required | ERCOT selects "Additional Info Required". Comments Required: ERCOT asks the TDSP for service history with DUNS for Effected Period (SHwDfEP).
|  |  | 1 | TDSP | TDSP | State: New (Pending Approval) TDSP | Begin Working | TDSP selects "Begin Working".
|  |  | 1 | TDSP | ERCOT | State: In Progress (Pending Approval) TDSP | Update Approved | TDSP selects "Updated Approved". TDSP inputs service history with DUNS for Effected Period (SHwDfEP)
|  |  | 1 | ERCOT | ERCOT | State: New (ERCOT Resolve) ERCOT | Begin Working | ERCOT selects "Begin Working". ERCOT updates 727 extract
|  |  | 1 | ERCOT | CR | State: In Progress (ERCOT Resolve) ERCOT | Complete | ERCOT selects "Complete".
|  |  | 1 | CR | CR | State: Pending Complete CR | Complete | CR reviews 727 extract. CR selects "Complete"

## MTDV3
|  | Script ID | MTDV3 |  | Power Point
|  | Script Name | DEV-LSE TDSP Submit
|  | Script Storyline | TDSP submits MarkeTrak with modification of StartTime and StopTime and inputs "Service History with DUNS for Effected Period". ERCOT will review MT and perform their validations. If the MT passes validation, it is transitioned to the CR to begin working. CR will review MT and compares to their system and agrees to the issue.
|  | Success Criteria | One issue is downloaded and successfully processed and the results correctly uploaded to the MarkeTrak system. The TDSP continues processing until the issue is closed.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | MT RQMTS | 31, 32 |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | TDSP | ERCOT | Create: TDSP | GUI | TDSP selects "LSE Date Change Start and Stop" from the submit tree. TDSP fills in all required fields. TDSP clicks "OK" | Entering the Service History with DUNS for Effected Period (SHwDfEP) at the submission of this issue will test if the (SHwDfEP) information is proprietary only to the TDSP and ERCOT.
|  |  | 1 | ERCOT | ERCOT | New ERCOT | Begin Working | ERCOT selects "Begin Working".
|  |  | 1 | ERCOT | CR | In Progress (ERCOT) ERCOT | Passed Analysis | ERCOT validates the MT against their internal data. ERCOT agrees selects "Passed Analysis", and transitions the issue to the CR.
|  |  | 1 | CR | CR | New (Pending Approval) CR | Begin Working | CR selects "Begin Working". MarkeTrak system updates state to - In Progress (Assignee)
|  |  | 1 | CR | ERCOT | In Progress (Pending Approval): CR | Update Approved | CR selects "Update Approved"
|  |  | 1 | ERCOT | ERCOT | New (ERCOT Resolve) ERCOT | Begin Working | ERCOT selects "Begin Working".
|  |  | 1 | ERCOT | TDSP | In Progress (ERCOT Resolve) ERCOT | Complete | ERCOT selects "Complete"
|  |  | 1 | TDSP | TDSP | Pending Complete TDSP | Complete | TDSP reviews 727 extract. TDSP selects "Complete".

## MTPT1
|  | Script ID | MTPT1 |  | Power Point
|  | Script Name | Premise Type
|  | Script Storyline | CR creates a premise type issue. CR requesting TDSP investigate premise type. CR believes premise type incorrect
|  | Success Criteria | One issue is downloaded and successfully processed and the results correctly uploaded to the MarkeTrak system. The TDSP continues processing until the issue is closed.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | Operating Rule |  |  | TRACK | MarkeTrak API
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | CR | TDSP | Create: CR | Submit via GUI | CR submits 1 issue into MarkeTrak via GUI. Issue Type/Sub Type = PremiseType (CR Selects Premise type from drop down box) | CR selects TDSP territory. MarkeTrak assures proper field information and checks for duplicate issue.
|  |  | 1 | TDSP | TDSP | State: New TDSP | Begin Working | TDSP selects "Begin Working". Marketrak system updates state to - In Progress (Assignee)
|  |  | 1 | TDSP | CR | State: In Progress (Assignee) TDSP | 814_20 Sent/Complete | TDSP selects "814 Sent/Complete". TDSP investigates Premise Type. MarkeTrak system updates state to Pending Complete
|  |  | 1 | CR | CR | State: Pending Complete CR | Complete | CR selects "Complete". MarkeTrak system updates state to Complete

## MTSN1
|  | Script ID | MTSN1 |  | Power Point
|  | Script Name | MarkeTrak Phase II - Safety Net
|  | Script Storyline | TDSP submits a safety net issue. CR receives issue from ERCOT and submits comments stating they have sent EDI. TDSP receives comments from CR and closes the issue.
|  | Success Criteria | Safety Net issue is created and successfully processed and the results correctly uploaded to the MarkeTrak system. All new MarkeTrak functionality is successfully tested.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | Operating Rule |  |  | TRACK | MarkeTrak API
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | TDSP | CR | Create: TDSP | MT Safety Net | TDSP submits issue into MarkeTrak via: API (Update), GUI or Bulk InsertIssue Type = Safety Net
|  |  | 1 | CR | CR | State: New CR | Begin Working | CR retrieves new Safety Net issue. CR selects "Begin Working" and adds comments stating they will submit EDI.
|  |  | 1 | CR | TDSP | In Progress (Assignee) CR | Complete | CR submits EDI. CR selects "Complete".
|  |  | 1 | TDSP | TDSP | Pending Complete TDSP | Complete | TDSP reviews that EDI is received. TDSP selects "Complete".

## MTSO1
|  | Script ID | MTSO1 |  | Power Point
|  | Script Name | Service Order
|  | Script Storyline | CR creates a Service Order issue. CR requests TDSP to investigate status of Service Order transaction.
|  | Success Criteria | One issue is downloaded and successfully processed and the results correctly uploaded to the MarkeTrak system. The TDSP continues processing until the issue is closed.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | Operating Rule |  |  | TRACK | MarkeTrak API
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | CR | TDSP | Create: CR | Submit via GUI | CR submits 1 issue into MarkeTrak via GUI. Issue Type/Sub Type = Service Order (CR Selects Service Order from drop down box) | CR selects TDSP territory. MarkeTrak assures proper field information and checks for duplicate issue.
|  |  | 1 | TDSP | TDSP | State: New TDSP | Begin Working | TDSP selects "Begin Working". Marketrak system updates state to - In Progress (Assignee)
|  |  | 1 | TDSP | CR | State: In Progress (Assignee) TDSP | Return to Submitter | TDSP investigates Service Order determained that TDSP needs more information. TDSP selects " Return to Submitter". Comments are required. MarkeTrak system updates state to New: CR.
|  |  | 1 | CR | CR | State: New (All) CR | Begin Working | CR selects "Begin Working". MarkeTrak system updates state to In Progress: CR
|  |  | 1 | CR | TDSP | State: In Progress CR | Return to Assignee | CR provides additional information. CR selects "Return to Assignee". Comments are required. MarkeTrak system updates state to New: TDSP.
|  |  | 1 | TDSP | TDSP | State: New TDSP | Begin Working | TDSP selects "Begin Working". Marketrak system updates state to - In Progress (Assignee)
|  |  | 1 | TDSP | CR | State: In Progress (Assignee) TDSP | Complete | TDSP investigates Service Order. TDSP selects the "Complete" transition. MarkeTrak system updates state to Pending Complete: CR.
|  |  | 1 | CR | CR | State: Pending Complete CR | Complete | CR selects the "Complete" transition. MarkeTrak system updates to state Closed

## MTMR1
|  | Script ID | MTMR1 |  | Power Point
|  | Script Name | Move Out with Meter Removal
|  | Script Storyline | TDSP submits MT issue for Move Out with Meter Removal. CR researches the MT issue determines that the meter was actually removed from the premise. CR will submit the Move Out (Coded B44). Some TDSPs require backdated MVOs.
|  | Success Criteria | One issue is downloaded and successfully processed and the results correctly uploaded to the MarkeTrak system. The TDSP continues processing until all issue is closed.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | MT RQMTS | 40 |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | TDSP | CR | Create: TDSP | Submit via GUI | TDSP selects "Move Out with Meter Removal" from the submit tree. TDSP fills in all required information. TDSP clicks "OK"
|  |  | 1 | CR | CR | State: New CR | Begin Working | CR selects "Begin Working". MarkeTrak system updates state to In Progress: CR
|  |  | 1 | CR | CR | State:In Progress (Assignee) CR | Add Comments | CR researches the "Move Out with Meter Removal" and discovers the meter was removed. Upon verification that the meter was removed the CR will submit the Move Out with the B44 code. CR will select the add "Comments" button. CR will enter comments and click OK. | must select 'OK' to complete transition
|  |  | 1 | CR | CR | State: In Progress (Assignee) CR | Complete | CR verify that they have received 867_03 final. CR selects "Complete".
|  |  | 1 | TDSP | TDSP | State: Pending Complete | Complete | TDSP selects the "Complete" transition. completes the MT issue. TDSP may add "Comments". MarkeTrak system updates to state "Closed"

## MTRP1
|  | Script ID | MTRP1 |  | Power Point
|  | Script Name | Reports
|  | Script Storyline | Recommendation: Run report request against production data. Market Participant submits a report request to ERCOT via MarkeTrak. ERCOT runs the requested report and delivers to Market Participant via TML report hyperlink.
|  | Success Criteria | 31 Day report, 3,000 + rows of data, report format, report run in background and delivered to TML report site successfully.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  | Operating Rule | 17 |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 0 | 1 | Market Participant | ERCOT | Create: MP |  | MP selects "Reports" from MT home page. Make data selections from parameter drop down menu.
|  |  | 1 | ERCOT | Market Participant | New: ERCOT |  | ERCOT will run the report and deliver to TML Report site via hyperlink and closes issue.
|  |  | 1 | Market Participant |  |  |  | MP retrieves report via TML

## MTMP1
|  | Script ID | MTMP1 |  | Power Point
|  | Script Name | Wrong MP Involved in Transtion
|  | Script Storyline | CR submits MarkeTrak with the incorrect DUNs Number. CR contacts ERCOT, notifying them that the wrong DUNs was inputted. ERCOT intervention to transition the MarkeTrak using "Wrong MP Involved in Transition". This will remove proprietary information from visibility. Issue will be automatically closed.
|  | Success Criteria | One issue is downloaded and successfully processed and the results correctly uploaded to the MarkeTrak system. The TDSP continues processing until all issue is closed.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | MT RQMTS | 33 |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | CR | TDSP | Create: CR | Submit via GUI | CR submits 1 issue into MarkeTrak via GUI. Issue Type/Sub Type = Billing and Usage from the drop down box. CR fills in assignee INCORRECTLY (TDSP X). CR fills in all other required fields. | CR selects TDSP territory. MarkeTrak assures proper field information and checks for duplicate issue. "Transaction Drop Down Box" will include :867_03 Monthly 00, 867_03 Monthly 01, 867_03 Monthly 05, 867_03 Final, 810_02, 810_03. Comments in the "Comment Field" are optional.
|  |  | 1 | TDSP | TDSP | State: New TDSP | Begin Working | TDSP selects "Begin Working". MarkeTrak system updates state to - In Progress (Assignee)
|  |  | 1 | CR | ERCOT | State: In Progress (Assignee) TDSP |  | CR notifies ERCOT that the wrong MP was assigned this issue. Request ERCOT intervention on this issue. | No transition. Notify by email or phone
|  |  | 1 | TDSP | ERCOT | State: In Progress (Assignee) TDSP | Wrong MP Involved | ERCOT User selects Wrong MP Involved- Comments required
|  |  | 1 | ERCOT | CR | Intervention Complete |  |  | All proprietary information will be changed to "X"s or "O"s