|  |  |  |  | System Planning Division |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report to Reliability and Operations Subcommittee for March 2008 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
| Item |  |  |  |  |  |  |  |  |
| 1. | ERCOT is currently tracking 219 active generation interconnection requests totaling over 100,000 MW. This includes over 44,000 MW of wind generation. Some projects were cancelled this past month due to inactivity and some projects were split into multiple phases (identified by an alphabetic suffix). |  |  |  |  |  |  |  |
| 2. | New Interconnect Agreements signed: Laredo Peaking Power Plant (08INR0064) for 200 MW in Webb County |  |  |  |  |  |  |  |
| 3. | 210 MW of new generation went in-service (80 MW upgrade of an existing coal unit and 130 MW wind) |  |  |  |  |  |  |  |
| 4. | Regional Planning is currently reviewing proposed transmission improvements with a total cost of $206.3 M. |  |  |  |  |  |  |  |
| 5. | CREZ Transmission Optimization Study is complete and filed with the PUCT under D-33672 |  |  |  |  |  |  |  |
| 6. | The Wind Ancillary Services Study performed by General Electric is complete and filed with the PUCT, also under D-33672. |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1.	New Generation Beginning Commercial Operations	1

1.2.	New Signed Interconnection Agreements	1

1.3.	Summary of Active Generation Interconnection Requests	1

2.	Potential Future Generation Interconnections	2

3.	Regional Planning Group Project Reviews	3

4.	Other Notable Activities	4

# Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://oldercot.ercot.com/tmaps.

## New Generation Beginning Commercial Operations

### Coal:

### J.T. Deely Upgrade for 80 MW in Bexar County

Wind:

- Silver Star Wind for 60 MW in Erath County

- Goat Wind for 70 MW in Sterling County

Note:  These units are included in the online wind capacity amount of 5,173 MW

## New Signed Interconnection Agreements

08INR0064, Laredo Peaking Power Plant, 200 MW, Webb County

## Summary of Active Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY BEING PROCESSED |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Currently tracking 219 active generation interconnection or change requests As of March 31, 2008 |  |  |  |  |  |
|  |  | North | South | West | Total |
| Security Screening Study |  | 5 | 3 | 13 | 21 |
| SSS Completed |  | 8 | 9 | 15 | 32 |
| Full Interconnect Study |  | 26 | 29 | 71 | 126 |
| FIS Completed |  | 0 | 1 | 1 | 2 |
| Interconnect Agreement Completed |  | 8 | 8 | 24 | 40 |
| Capacity for Grid, MW |  | 29,522 | 29,098 | 41,780 | 100,400 |
| Wind Capacity, MW |  | 2,315 | 4,117 | 38,315 | 44,747 |

| Potential Future Generation Interconnections Fuel | Public (MW) | Non-Public (MW) | Total (MW) |
| --- | --- | --- | --- |
| Combined Cycle - Gas | 3,958 | 26,445 | 30,403 |
| Combustion Turbine - Gas | 646 | 448 | 1,094 |
| Nuclear | 9,186 | 6,400 | 15,586 |
| Coal | 4,131 | 4,144 | 8,275 |
| Wind | 10,138 | 34,479 | 44,617 |
| Other |  | 425 | 425 |
| Totals | 28,059 | 72,341 | 100,400 |

The table below summarizes the publicly known potential future generation projects for the ERCOT region.  (IA=Interconnect Agreement, PL=Public Letter)

| Future Generation Interconnections (Public Projects) as of March 31, 2008 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INR | Site Name | Status | County | Region | Fuel | In-service Date | MW Into Grid | Change from Last Report |
| 07INR0030 | Louis (Buffalo Gap 3) | IA | Nolan | West | Wind | Apr-08 | 138 |  |
| 06INR0036 | Quail Run Energy Center 2 | IA | Ector | West | Gas-CC | May-08 | 275 |  |
| 08INR0064 | Laredo Peaking Power Plant | IA | Webb | South | Gas-CT | May-08 | 193 | New IA |
| 06INR0035 | Colorado Bend Energy Center 2 | IA | Wharton | South | Gas-CC | Jun-08 | 275 |  |
| 07INR0027 | South Houston Green Pwr Exp Prj 1 | IA | Galveston | South | Gas-CC | Jun-08 | 244 |  |
| 07INR0022 | Panther Creek Wind Farm | IA | Howard | West | Wind | Jun-08 | 150 |  |
| 08INR0028 | McAdoo Energy Center | IA | Dickens | North | Wind | Jul-08 | 300 |  |
| 04INR0011b | Mesquite Wind Phase 4 | IA | Shackelford | West | Wind | Aug-08 | 136 |  |
| 04INR0011c | Cottonwood Wind | IA | Shackelford | West | Wind | Aug-08 | 100 |  |
| 04INR0017 | Ocotillo Wind Farm 1 | IA | Howard | West | Wind | Aug-08 | 59 |  |
| 03INR0030b | Wild Horse Wind Farm 2 | IA | Cottle | West | Wind | Aug-08 | 39 |  |
| 08INR0055 | Capricorn Ridge III | IA | Coke | West | Wind | Aug-08 | 249 |  |
| 08INR0038 | M Bar Wind | PL | Andrews | West | Wind | Sep-08 | 194 |  |
| 07INR0025 | Airtricity Lamesa Wind Plant | IA | Dawson | West | Wind | Oct-08 | 183 |  |
| 06INR0012 | Sherbino Mesa Wind Farm | IA | Pecos | West | Wind | Oct-08 | 300 |  |
| 07INR0034 | Wolf Ridge Windfarm | IA | Cooke | North | Wind | Oct-08 | 113 | MW Adj |
| 07INR0037 | Bull Creek Wind Plant | IA | Borden | West | Wind | Oct-08 | 180 |  |
| 07INR0045b | Airtricity Inadale | IA | Scurry | West | Wind | Nov-08 | 212 |  |
| 07INR0045a | Airtricity Pyron Wind Farm | IA | Scurry | West | Wind | Nov-08 | 303 |  |
| 08INR0018 | Gunsight Mountain | IA | Howard | West | Wind | Dec-08 | 120 |  |
| 08INR0025 | Pistol Hill Energy Center | PL | Ector | West | Wind | Dec-08 | 300 |  |
| 07INR0029 | South Trent Wind Farm | IA | Taylor | West | Wind | Dec-08 | 101 |  |
| 07INR0005 | Notrees-1 | IA | Ector | West | Wind | Dec-08 | 151 |  |
| 07INR0011 | Turkey Track Energy Center | IA | Nolan | West | Wind | Dec-08 | 170 | MW Adj |
| 05INR0015a | Gulf Wind 1 | IA | Kenedy | South | Wind | Dec-08 | 283 |  |
| 06INR0022a | Penascal Wind Farm 1 | IA | Kenedy | South | Wind | Dec-08 | 202 |  |
| 08INR0037 | Airtricity Panther Creek 2 | IA | Howard | West | Wind | Dec-08 | 220 |  |
| 08INR0053 | Elbow Creek Wind Project | IA | Howard | West | Wind | Dec-08 | 117 |  |
| 08INR0059 | Gray Wind Project | PL | Borden | West | Wind | Dec-08 | 141 |  |
| 04INR0011e | Hackberry Wind Farm | IA | Shackelford | West | Wind | Dec-08 | 165 |  |
| 09INR0026a | Sterling Energy Center | PL | Sterling | West | Wind | Dec-08 | 200 |  |
| 07INR0036 | Coyote Run Windfarm | IA | Borden | West | Wind | Mar-09 | 225 | MW Adj |
| 08INR0046 | Bosque Expansion | IA | Bosque | North | Gas-CC | Mar-09 | 255 |  |
| 08INR0065 | Buffalo Gap 4 and 5 | PL | Nolan | West | Wind | Mar-09 | 465 |  |
| 09INR0028 | V H Braunig 6 | PL | Bexar | South | Gas-CT | May-09 | 185 |  |
| 08INR0040 | Lenorah Project | PL | Martin | West | Wind | May-09 | 350 |  |
| 09INR0060 | WindTex Stephens WndFrm | PL | Borden | West | Wind | May-09 | 141 |  |
| 09INR0027 | Winchester Peaking Plant | IA | Fayette | South | Gas-CT | Jun-09 | 178 |  |
| 09INR0036 | McAdoo Energy Center II | PL | Dickens | West | Wind | Jun-09 | 500 |  |
| 08INR0035 | Cedar Bayou 4 | IA | Chambers | South | Gas-CC | Jun-09 | 539 |  |
| 09INR0026 | Sterling Energy Center | PL | Sterling | West | Wind | Jun-09 | 300 |  |
| 09INR0045 | Sand Hill Peakers | PL | Travis | South | Gas-CT | Jun-09 | 90 |  |
| 08INR0003 | Sandow 5 | IA | Milam | North | Coal | Jul-09 | 581 |  |
| 05INR0015b | Gulf Wind 2 | PL | Kenedy | South | Wind | Sep-09 | 400 |  |
| 09INR0015 | Comanche Peak 1&2 Upgrade | PL | Somervell | North | Nuclear | Oct-09 | 86 |  |
| 03INR0030a | Wild Horse Wind Farm 1 | IA | Cottle | West | Wind | Nov-09 | 60 |  |
| 09INR0006a | Oak Grove SES 1 | IA | Robertson | North | Coal | Nov-09 | 855 |  |
| 09INR0034 | Gatesville Wind Farm | PL | Coryell | North | Wind | Dec-09 | 200 |  |
| 09INR0037 | Scurry County Wind III | PL | Scurry | West | Wind | Mar-10 | 350 |  |
| 09INR0006b | Oak Grove SES 2 | IA | Robertson | North | Coal | May-10 | 855 |  |
| 06INR0006 | Cobisa-Greenville | PL | Hunt | North | Gas-CC | May-10 | 1750 |  |
| 09INR0002 | J K Spruce 2 | IA | Bexar | South | Coal | Jun-10 | 750 |  |
| 05INR0015c | Gulf Wind 3 | PL | Kenedy | South | Wind | Sep-10 | 400 |  |
| 09INR0001 | Sandy Creek 1 | IA | McLennan | North | Coal | Sep-10 | 925 |  |
| 06INR0026 | Wild Horse Mountain | IA | Howard | West | Wind | Dec-10 | 120 |  |
| 12INR0003 | Throckmorton Wind Farm | PL | Throckmorton | West | Wind | Dec-10 | 400 |  |
| 10INR0010 | Jack County 2 | PL | Jack | North | Gas-CC | Jun-11 | 620 | MW Adj |
| 07INR0004 | Pampa Energy Center | PL | Gray | West | Coal | May-12 | 165 |  |
| 09INR0024 | B&B Panhandle Wind | PL | Carson | West | Wind | Jun-12 | 1001 |  |
| 12INR0004 | Fort Concho Wind Farm | PL | Tom Green | West | Wind | Jul-12 | 400 |  |
| 15INR0002 | Comanche Peak 3 and 4 | PL | Somervel | North | Nuclear | Jan-15 | 3200 |  |
| 15INR0008 | STP 3 and 4 | PL | Matagorda | South | Nuclear | Jan-15 | 2700 |  |
| 11INR0011 | Victoria City Nuclear | PL | Victoria | South | Nuclear | Jan-15 | 3200 |  |
|  |  |  |  |  |  | TOTAL | 28,059 |  |

# Regional Planning Group Project Reviews

- Oncor submitted a two phase project to relieve congestion related to new wind units in the Lamesa area.  The first phase of the project will upgrade both ends, but not the middle of the Lamesa to Bluff Creek 138 kV line, rebuild the Bluff Creek to China Grove 138 kV line, rebuild the Lamesa to Ackerly Vealmoor 69 kV line to 138/69 kV double circuit, rebuild the Lamesa 138 kV switching station, and build a new 138 kV Ackerly Vealmoor station.  The cost of the first phase of these upgrades is $40.3 M.  The second phase of the project would be done if a third wind unit signs an interconnect agreement.  This phase would add second circuits to all rebuilt lines and include station upgrades at China Grove and Big Spring.  The additional cost of the second phase upgrades is $40.5 M for a total of $80.8 M.  Both phases of this project are being reviewed to ensure that the improvements fit into the likely CREZ transmission solution for the area.

- Oncor submitted a project to upgrade the Payne to Collin 138 kV to a rating of 326 MVA using double circuit structures with one circuit in place for a cost of $19 M.  This project is currently in ERCOT Independent Review.

- Oncor submitted a project to construct the Krum Tap Switching Station and rebuild the Krum – Decatur 69 kV line and the Krum Tap 138 kV line as a 138 kV double-circuit line with one circuit in place using a conductor with a minimum rating of 214 MVA. The estimated cost of this project is $17.8 M and is currently in ERCOT Independent Review.

- LCRA submitted a project to add a 3rd 345/138 kV autotransformer at the Zorn substation.  This project should be complete by summer peak 2013 and cost is estimated at $15 M.  This project is currently in ERCOT Independent Review.

- Oncor submitted a project to upgrade the Midland East – Stanton East – Big Spring West – Big Spring Switch 138 kV line.  The proposed upgrade will replace the existing 4/0 ACSR 84 MVA circuit with a single circuit line with a long-term emergency rating of 394 MVA.  The estimated completion date is peak 2010 with a cost of approximately $ 24 M.  This project is currently in ERCOT Independent Review.

- AEPSC submitted a project to increase the reliability of service in the Presidio area.  This project will install a second 138/69 kV autotransformer at Marfa in 2008, install 2-2.4 MW NaS battery units at Presidio in 2009, and replace the existing 69 kV line with a 138kV-capable but 69kV-operated line from Alamito Creek to Chinati to Presidio in 2012.  Total cost of the project is estimated to be $67 M.

- CNP Energy submitted a 2007 Five-Year Plan project to install a new 345/138 kV substation called Rothwood to eliminate potential unserved energy under contingency scenario(s).  The projected completion date is summer 2010 with an estimated cost of $23 M.

# Other Notable Activities

- All postings referred to below can be found at http://oldercot.ercot.com/tmaps unless otherwise indicated.

- The Wind Ancillary Services  Study, performed by General Electric International under contract to ERCOT is complete and the Final Report has been filed with the PUCT under D-33672 http://interchange.puc.state.tx.us/WebApp/Interchange/application/dbapps/filings/pgSearch.asp

- System Planning has completed the CREZ Transmission Optimization Study, which has been filed with the PUCT under D-33672

- Updated SSWG 2008 Data Set A and Data Set B cases were posted

- SPWG 2008 Current Year Short Circuit case has been posted

- Q1 TPIT spreadsheet was completed and filed March 1st.  Individual worksheets were sent March 28th and are due to ERCOT May 1st.

- The Texas Renewable Energy Credit Trading program (PUCT Substantive Rule 25.173) completed the mandated business for 2007 at midnight on March 31st. Ninety-one Competitive Retailers “retired” a total of 3,421,626 RECs in order to satisfy the mandate for 2007. Retailers also retired an additional 814,234 RECs voluntarily in support of the Texas Clean Air Initiative.

- The Labeling of Electricity program underwent a significant upgrade in automation this year. The emissions information required by the PUCT Substantive Rules 25.475 and 25.476 was posted to the Texas Renewables web site (www.texasrenewables.com/reports.asp ) on April 1st as required. The EFL workbook that REPs use to create their emissions information labels will be posted to the same site on April 4th.

- An upgrade to the Operations and System Planning Department site is nearing completion.  A market notice with more information will be sent later this month.