## Slide 1: Texas Nodal Program ERCOT Readiness Update
TPTF
Revised: April 2, 2008
March 31, 2008

## Slide 2
Agenda
<number>
Executive Readiness Survey
Transition Plans
Business Process Model and Procedures
Training
Staffing

## Slide 3
ERCOT Executive Readiness Survey
<number>
The ERCOT Executive Readiness Survey was initiated approximately 4 months after the Market Participant Survey.
Conducted more frequently (i.e. every 2 months) than the quarterly Market Participant survey. It is now moving to monthly.
Next iteration will be published on April 1st.

## Slide 4
Transition Plans
<number>
Transition Plans were developed for each Nodal project and all affected departments. Approximately 80 department and project plans were developed.
Transition Plans cover:
  Overview – project/department objectives, customer (user) information, transition plan objectives, reference materials and outstanding issues
  Scope of Transition – resources, facilities, hardware, software, documentation, budget, training, roles and responsibilities
  Transition Planning – release process, data migration, performance measures and reporting, governance and management approach, problem resolution, documentation strategies, training, sustainability metrics, transition schedule, and gaps
Initial drafts were created in February, 2008
Updates are scheduled for April and June
Transition Plans are reviewed by impacted departments
Issues, Gaps, TBDs are escalated and tracked

## Slide 5
Business Process Model
<number>
An enterprise-wide Business Process Model was completed to have a complete picture of ERCOT business operations. The model provides a top-down view depicting high level design to low level operational detail. This enabled:
  Market Trials: Operating procedures to be developed and tested to ensure that ERCOT employees can operate new Nodal systems
  Continuity Planning: Each department can identify and plan for how to perform each of their business processes in the event of an emergency or disaster
  Process Improvement: Analysis of each of its operating activities to identify opportunities to improve the efficiency (cost and cycle time) and effectiveness (quality) of its processes
  Market Response: ERCOT can respond to future business goals relating to protocol changes, governmental regulations and technology advancements

## Slide 6
Our approach was to document the processes of each department and merge them to create a consolidated, end-to-end view…
<number>
. . . representing ERCOT by the processes it follows rather than by department; this enables an activity-based view of the organization.
Operate ERCOT
Planning
Operating
Settlements
Level 1
Level 2
Level 3
Level 4
Level 1
Level 2
Level 3
Level 4
Level 1
Level 2
Level 3
Level 4
Merge
Merge
Business Process Model

## Slide 7
Business Process Model
<number>
A one-page view of ERCOT in relation to its high-level functions…

## Slide 8
Business Process Model
<number>
Operational Procedures
Level 1
14 processes
Level 2
83 processes
Level 3
407 processes
Level 4
621 processes
The ERT has identified approximately 1400 procedures. It is expected that it will results in about 750 actual procedures.
A top-down approach was used to decompose the Level 1 picture so that each linked to desk procedures…

## Slide 9
Business Process Model
<number>
Block diagrams map the process to show how the operation works . . .
Illustrative Example

## Slide 10
Business Process Model
<number>
This shows the registration process ‘drills down’ to the credit check procedures

## Slide 11
Business Process Model
<number>
The level 2 process describes how new market participants are registered with ERCOT

## Slide 12
Business Process Model
<number>
Level 3 describes how ERCOT processes the application by the market participant and registers them in the appropriate system…

## Slide 13
Business Process Model
<number>
These templates are illustrative
Level 4 describes how a credit check is conducted as part of the registration process, and how it links to use cases and procedures

## Slide 14
Procedures
<number>
Procedures were determined for each department based on the Business Process Model. Along with other input, departments validated and determined the procedures needed. Many of the identified procedures from the Process Model can be combined into a single procedure.
As a result of the Business Process Model, there were 1433 procedures identified. They are identified by department (next slide).
Development of procedures has already begun and good progress has been made to date.
Systems Operations is YELLOW and within 30 days of schedule with plans to catch up within the next month.
All IT departments are GREEN except for three departments that are within 30 days of their plan.
Market Operations, Systems Planning, and Corporate functions are GREEN.
Department Level Procedures Scorecard is in development and will be available by the end of April

## Slide 15
Procedures
<number>
111 - Treasury & Credit Administration | 64
112 - Contract Admin & Procurement | 35
113 – ICMP | 11
114 - Accounting & Budget | 49
120 - General Counsel | 14
130 – HR | 25
170 - Market Rules | 5
180 - Internal Audit | 22
302 IT - Business and Customer Services | 6
310 IT - Systems Engineering & Administration | 12
315 IT - Storage Resource Management | 8
325 – Facilities | 18
330 IT – Network | 12
345 IT- EMMS Development | 21
347 IT - Enterprise Integration | 15
350 352 353- PMO | 10
351 396 405 605- DPO/PMO | 26
354 IT - Enterprise Information Services | 17
355 IT - Enterprise Architecture | 10
356 IT - Commercial Services | 16
357 358 IT - Corporate Applications and Web & Data Services | 14
360 IT - Database Administration | 17
370 - Corporate Security - Info Systems | 10
371 - Corporate Security - Physical | 8
380 IT - Console Operations | 10
385 IT – Release Management | 22
390 IT - Commercial Operations | 3
395 IT - EMMS Production Support | 5
410 - Market Operations Support | 48
410 - Market Operations Support - Demand response | 26
415 - Operating Standards | 7
421 - Outage Coordination | 33
422 - Network Modeling | 35
423 - Operations Planning & Analysis | 111
424 - Advanced Network Applications | 87
426 - Operations Engineering | 59
427 - System Operations Training | 15
428 - System Operations Control Center | 178
450 – CRR | 55
460 - Regulatory Support & Reporting | 4
471 472 473 - System Planning Group | 12
530 - Settlements Metering | 144
540 - Energy Analysis & Aggregation | 31
550 - Settlements & Billing | 39
570 - Retail Customer Choice | 6
585 – CODIA | 1
630 650 - Retail Client Services & Retail Market Analysis | 22
640 - Market Operations Testing | 10
660 - Wholesale Client Services | 30

## Slide 16
Training
<number>
Department Level and Individual Training plans have been created.
Individual Training plans are being revisited and updated as managers have been able to target more specific training needs.
Progress has been steady on training.
Systems Operations, Market Operations, Systems Planning, and Corporate functions are GREEN.
75% of IT departments are GREEN. The remaining 25% are YELLOW and within 30 days of their training plan.
Department Level Training Scorecard has been developed.
Scorecard identifies the training required by individual within the department and the target completion date for each course.

## Slide 17
Training
<number>
Scorecard identifies courses required by each person in the department
ERCOT
Training
Scorecard
Example
Overall Department Status

## Slide 18
Staffing
<number>
Actively recruiting for 39 Nodal positions.
Identified key positions for department ramp-up and for the 168 hour test. Remaining positions are targeted for later in the year.
Transition plans helped to clarify timing and staffing for departments. There was a sharp increase in open positions at the start of the year.
Some positions for 2009 have been opened early to ensure adequate time for recruiting, training, availability for EDS activities and the 168 hour test.
5 additional intern positions have been identified and are targeted to start in Spring/Summer to support activities.
The majority of openings have been addressed within the targeted timeframe.

## Slide 19
Proposed Positions
Staffing – Nodal Staffing Status
<number>
Identified Nodal - Specific Positions in each Division
Added 5 New Intern Positions
Actively Recruiting 39 Positions
Several Positions have Offers Pending
Division | 2006 Auth | 2008 Auth | 2008 Current | 2008 Open | 2008 % Filled | 2009 Reqtd | 2009 Open | 2009 % Filled
Information Technology | 119 | 156 | 139 | 17 | 89% | 166 | 27 | 84%
Market Operations | 72 | 89 | 83 | 6 | 93% | 91 | 8 | 91%
System Operations | 108 | 132 | 122 | 10 | 92% | 136 | 14 | 90%
System Planning | 8 | 14 | 13 | 1 | 93% | 15 | 2 | 87%
Totals | 307 | 391 | 357 | 34 | 91% | 404 | 51 | 88%
Plus 5 Intern Positions

## Slide 20
Staffing – Metric E-8
<number>
Propose to modify metric E-8
Based on the alternative criteria (referenced on later slide):
  Information Technology AMBER (will go red next week)
  Market Operations AMBER
  System Operations AMBER (will go red next week)
  System Planning AMBER (will go red next week)
Based on the suggestion that we should be at 90% of staffing model by June 1st, 2008:
  May 1st, 2008: 85% of staffing model
  June 1st, 2008: 90% of staffing model
  July 1st, 2008: 95% of staffing model
Currently all divisions are at 85% or better
  By June 1st (90%): IT needs to hire 2 additional people
  By July 1st (95%): IT – 10; Market Ops – 2; Sys Ops – 4; Sys Planning - 1
Our recommendation is to encompass both standards

## Slide 21
Staffing – 2009 Change Drivers
<number>
New Market Functions
  Implementation of Day-Ahead Energy Market, Congestion Revenue Rights
New Systems (ex. NMMS, CRR)
  Increased complexity of network model, increased hardware, EMMS complexity and an increase in testing,
Increased business process complexity (Market Settlements, Network Modeling)
  Increased complexity of nodal market settlements and wholesale client services
  Increased planning services

## Slide 22
Staffing – Metric Definition and Monitoring
<number>
Assumptions:
  Only Nodal affected or affecting positions
  Critical Nodal Positions are those that would impact Nodal Go-Live (critical path to go-live)
  Key Nodal Positions are those resources needed to execute Nodal in production (including 168 hour test)
Criteria for Red Status:
  0 to 20% of Key Nodal Positions for a department – vacant for a period greater than 120 days
  20% to 39% of Key Nodal Positions for a department – vacant for a period greater than 90 days
  40% or greater of Key Nodal Positions for a department – vacant for a period greater than 60 days
  2 (approximately 20%) or more of the Critical Nodal Positions – vacant for a period of 30 days or more
Criteria for Amber Status:
  0 to 20% of Key Nodal Positions for a department – vacant for a period of 91 to 120 days
  20% to 39% of Key Nodal Positions for a department – vacant for a period of 61 to 90 days
  40% or greater of Key Nodal Positions for a department – vacant for a period of 31+ days
  1 (approximately 10%) of the Critical Nodal Positions – vacant for 0 to 30 days