## 2008
No. | PWG 2008 Goals | Target Date | % Complete
18 | Distributive Generation load profiling implementation (PRR draft) | 2008-05-26 | 90% | CHG
1 | Implementation of LRS sample selection round two. | 2008-07-01 | 72% | CHG
4 | Review 2007 UFE Analysis (final complete, true-up pending) | 2008-07-30 | 50% | CHG
2 | 2008 Annual Validation. | 2008-11-07 | 5% | CHG
3 | Evaluate the methodology for profile scaling factors (per UFETF Nov. 16) | 2008-12-01 | 0%
6 | Update Long Term Strategy of Load Profiles including refreshed timeline | 2008-12-07 | 0%
7 | IDR Analysis – 2 issues outstanding from original analysis. | 2008-12-07 | 0%
8 | Review if having more weather stations adds accuracy | 2008-12-07 | 0%
9 | Review if the weighting of weather stations is appropriate | 2008-12-07 | 0%
11 | Review LPG language on list based profiles and universality | 2008-12-07 | 0%
16 | LPGRR language Chapter 15 for consistency with PUCT Load Research Rule | 2008-12-23 | 0%
13 | Investigate ways to improve Business Profile ID assignments | 2008-12-24 | 0%
10 | Review IDR installation procedure language to ensure compliance (Pending AMR Rule) | 2008-12-25 | 0%
14 | Review analysis of DLC demonstration programs (Pilot) | 2008-12-25 | 0%
5 | Examine ways to accommodate extreme events in Settlement process. | 2008-12-26 | 0%
17 | Advanced Metering Implementation LPG changes if needed | 2008-12-27 | 0% |  | CHG
12 | Demand Response Implementation | 2008-12-29 | 0% | CHG | New
15 | Review Protocol and LPG language for appropriateness for large Opt-in Entity | 2008-12-31 | 0% | CHG
*** | Not expected to be completed in 2008 due to market status
*** | Working or on the next Agenda

## 2007
No. | PWG 2007 Goals | Target Date | % Complete
1 | Implement new Version 2 ERCOT Profiles. | 2007-05-07 | 100%
2 | LRS sample selection round two. | 2007-04-01 | 100%
3 | New Oil & Gas Profile - BUSOGFLT | 2007-09-07 | 100%
4 | 2007 Annual Validation. | 2007-11-07 | 80% to 100% | CHG
5 | Evaluate the methodology for profile scaling factors (per UFETF Nov. 16) | 2007-12-07 | 0% | CHG
6 | Review 2004, 2005 & 2006 UFE Analysis. | 2007-12-07 | 67 to 100% | CHG
7 | Examine ways to accommodate extreme events in Settlement process. | 2007-12-07 | 5% | CHG
8 | Establish Long Term Strategy of Load Profiles including refresh timeline | 2007-09-07 | 5% to 100% | CHG
9 | IDR Analysis – 2 issues outstanding from original analysis. | 2007-12-07 | 0% | CHG
10 | Review if having more weather stations adds accuracy | 2007-12-01 | 0%
11 | Review if the weighting of weather stations is appropriate | 2007-12-01 | 0%
12 | Review IDR installation procedure language to ensure compliance (Pending AMR Rule) | 2007-12-07 | 0% | CHG
13 | Does having 2 decimals on load profiles significantly affect settlement | 2007-06-07 | 100%
14 | Review LPG language on list based profiles and universality | 2007-12-07 | 0%
15 | PUCT Docket responses to demand response or AMR rule, etc. (DLC Implementation) | 2007-12-07 | 65 to 70% | CHG
16 | Set up area on PWG web page for key documents | 2007-05-07 | 100%
17 | Annual Review of load profiles as specified in market language | NA | NA
18 | Analysis to identify new profiles as specified in market language (Primary Voltage) | 2007-12-07 | 20% to 100% | CHG
19 | Update the TOU procedures on the Load Profiling web site | 2007-12-07 | 25% to 100% | CHG
20 | Investigate ways to improve Business Profile ID assignments | 2007-12-07 | 0%
21 | Review analysis of DLC demonstration programs (Pilot) | 2007-12-07 | 0% |  | CHG
22 | Review Protocol and LPG language for appropriateness for large Opt-in Entity | 2007-12-07 | 5% | CHG | CHG
23 | LPGRR language Chapter 15 for consistency with PUCT Load Research Rule | 2007-12-07 | 15% | CHG | CHG
24 | Advanced Metering Implementation for IDR Requirement and TOU | 2007-12-07 | 0% to 50% | CHG | New
Color Legend:
Completion in 2007 shall not occur - moved to 2008 |  |  |  | CHG