## Slide 1: April 2008 RO Projects Financial Overview & Release Recommendations Retail Market Subcommittee May 14, 2008 Hope Parrish Market Operations Division Projects Organization

## Slide 2: RO Project Financial Update
Overview
Review RO Project Financial Overview as of 04/30/2008
ERCOT Seeking RMS endorsement for partial release of RO Variance to the SRT for appropriate reallocation in 2008.

## Slide 3: 2008 RO PPL
Planned and Unplanned 2007
Carry-over Projects
(Green Shaded Area)
Projects ABOVE the
current Capability Line
(Orange Shaded Area)
Projects BELOW the
current Capability Line
(Yellow Shaded Area)

## Slide 4: 2007 Carry-Over Projects
PR60008_01: Go-Live Update: 06/14/2008 (originally 05/10/2008)
PR70007_01: Moved into “Execution”
PR70005_01: Moved to “Closed”

## Slide 5: Projects ABOVE the Capability Line
PR80028_01: Moved to “Planning”
PR7006_02: Moved to “Planning”
Notes: 50061_01 Moved to ON Hold: Freed up approx. $120k, however not recommended for release by CART

## Slide 6: Projects BELOW the Capability Line
No status change on these projects
Notes: ERCOT will continue to evaluate the projects under the line to determine if we can move anything up. Currently the items just below the line are funded with the 2008 PPL

## Slide 7: Financial Overview as of 05/01/2008 (cont’d)
RO PPL Budget Activity | Amount | Notes/comments
Approved RO Capability Line Budget Funding | $6.1M | Current approved RO funding allocation Designates where the capability line falls
Current Forecast Spend of projects above the Capability Line | ~$2.3M | Based on current expectations and run rates for active and not started projects above the capability line
Budget Variance | ~$3.8M | Budget Variance is difference between RO Capability Line Budget Funding and Current Forecast Spend of projects above the Capability Line $1M due to consolidation of PR60008 Ts&Cs and Performance Measures $2.2M due to projects deferred $600K due to project underspend REQUEST: ERCOT Seeking endorsement from RMS to release $2.27M to SRT to reallocate as appropriate. Will still leave a $1.5M variance to monitor in 2008.

## Slide 8: Budget Variance Allocation
Below is the updated view of under spend categories. These categories will be monitored throughout the year to assess potential reallocations.
MO/RO Budget Variance
2008; $ thousand
$2.270M
$1.06M
$730K
RO Total = $2.270
No Concerns
Should be monitored
Should not Release
CART and RMS will all review the MO-RO portfolio and acknowledge the release of $2.270M from the overall MORO portfolio budget variance of approx. $4.0M. (3.6 RO).
RO Total = $785K
RO Total = $713
RO recommended Release is
Approx. $2.270M

## Slide 9: Questions / Contact
Hope Parrish
Project Manager, MO DPO
Market Operations Divisional Projects Organization
ERCOT
(512) 248-6522
hparrish@ercot.com