## Slide 1
Retail Market Subcommittee
May 14th, 2008
ERCOT Project Update
PR60008 Ts & Cs and Performance Measures
Notes: <number>

## Slide 2: PR60008 Project Status
Project Status – Execution Phase
Project Phases
Initiation – Completed
Planning – Completed
Execution _Started 01/11/2008
  Go-Live – 06/14/2008 *(UPDATED)*
    Fall back contingency date due to issues encountered in iTEST
Recent Accomplishments
Migrated Code to iTEST
Completed all Test Scripting and Data Preparation
Resolved application issues in iTEST found during smoke test (details on next slide)
Next Steps
Complete Testing: 06/06/2008
Go Live: 06/14/2008
Stabilization End: 07/11/2008

## Slide 3: PR60008 Project Status Continued
12/06/2008 Release PROD (tent.)
Stabilization
Risks / Issues / Updates:
Issue 1: Slow TIBCO performance found in iTEST– Resolved
  Root Cause Environment Issue –
  Resolution: Storage I/O
Issue 2: TIBCO message memory errors found in iTEST– Resolved
  Root Cause: Application Issue isolated to iTEST
  Resolution: Configuration setting in iTEST Only
Result: Schedule Delay - PR60008 Ts and Cs and Performance Measures moved to contingency date of 06/14/2008 due to time needed to complete testing – LOW RISK between PR60008 and PR70007 MarkeTrak Enhancements
  Risk Mitigation:
  Separate resources for DEV, Business, and Operations. Mitigating resource impacts with testing

## Slide 4
Questions?
PR60008 Project Status Continued