## Slide 1
Update to RMS
May 14, 2008
Notes: <number>

## Slide 2
Accomplishments:
  Test Scripts have been completed and posted to Retail Testing Website
  Revisions to User Guide are underway to incorporate changes for Release and 1 and 2 implementations
  Preparations are underway for testing
Notes: <number>

## Slide 3
Test Scripts completed and posted to website
WDSL/ XSD for Release 1 sent out on April 29th – Market Notification
Registration for MarkeTrak testing closed May 1st – 8 CR’s and 5 TDSP’s have signed up for testing
Training material for Release 1 has been posted to www.ercot.com and distributed to via Market Notice
Notes: <number>

## Slide 4
By May 12th, Test Digital Certificates will be issued
May 14th, CR’s and TDSP’s send esiid test bed for Sandbox
May 16th – ERCOT will conduct MarkeTrak training which will incorporate Release 1 changes
May 20 – Connectivity Test and Sandbox opens
May 22 – Complete revision discussions of the User’s Guide – deadline for updates to be submitted
Notes: <number>

## Slide 5
Project Status - Execution Phase
Project Phases
Initiation - Completed
Planning - Completed
Execution _Started 03/21/2008
Go-Live Release 1 - 06/14/2008
Go-Live Release 2 - 08/16/2008
Go-Live Release 3 - 12/06/2008
Closing - 02/2009

## Slide 6
Internal Requirements, Conceptual Design, Detail Designs, Security Assessment all complete
Release 1 Development @ 90% Complete(100% pending completion of UAT)
Release 2A Development @ 30% Complete
Next Steps
Release 1 Test Script Completion = 05/01/2008
Release 1 UAT = 05/19/2008 - 06/06/2008
Sandbox Open = 05/20/2008

## Slide 7
Next meeting: May 22nd
Location - Austin ( hotel near ERCOT)
User Guide discussion
  Must have all updates by close of meeting

## Slide 8
Notes: <number>