|  |  |  |  | System Planning Division |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report to Reliability and Operations Subcommittee for April 2008 (revised May 13, 2008*) |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
| Item |  |  |  |  |  |  |  |  |
| 1. | ERCOT is currently tracking 234 active generation interconnection requests totaling over 104,000 MW. This includes almost 49,000 MW of wind generation. |  |  |  |  |  |  |  |
| 2. | New Interconnect Agreements signed: - Victoria Power Station for 332 MW (Combined Cycle Gas Plant) in Victoria County with in-service date of July 2008. This is the first interconnect to convert an existing retired unit into combined cycle operation by adding a gas turbine and heat recovery steam generation equipment (HRSG). |  |  |  |  |  |  |  |
| 3. | One new generation facility began commercial operation. - Louis Wind (Buffalo Gap 3) in Nolan County – 138 MW - Total installed wind in ERCOT is 5,311 MW |  |  |  |  |  |  |  |
| 4. | The 2008 CSC Utilization Report was presented to WMS in April. Details at: http://www.ercot.com/calendar/2008/04/20080416-WMS.html |  |  |  |  |  |  |  |
| 5. | Regional Planning is currently reviewing proposed transmission improvements with a total cost of $227.6 M. |  |  |  |  |  |  |  |

* Project in-service date change

Table of Contents

1.	Generation Interconnection	1

1.1.	New Generation Beginning Commercial Operations	1

1.2.	New Signed Interconnection Agreements (also found in 1.4 Table) 	1

1.3.	Summary of Active Generation Interconnection Requests	1

1.4.	Potential Future Generation Interconnections	2

2.	Regional Planning Group Project Reviews	4

3.	Other Notable Activities	4

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://oldercot.ercot.com/tmaps.

## New Generation Beginning Commercial Operations

Wind:

- Louis (Buffalo Gap 3)  for 138 MW in Nolan County

Note:  These units are included in the online wind capacity amount of 5,311 MW

## New Signed Interconnection Agreements (also found in 1.4 Table)

Victoria Power Station (08INR0050) for 332 MW in Victoria County with in-service date of July 2008.

## Summary of Active Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY BEING PROCESSED |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Currently tracking 233 active generation interconnection or change requests As of February 29, 2008 |  |  |  |  |  |
|  |  | North | South | West | Total |
| Security Screening Study |  | 5 | 8 | 14 | 27 |
| SSS Completed |  | 5 | 11 | 20 | 36 |
| Full Interconnect Study |  | 30 | 27 | 72 | 129 |
| FIS Completed |  | 0 | 2 | 1 | 3 |
| Interconnect Agreement Completed |  | 7 | 9 | 23 | 39 |
| Capacity for Grid, MW |  | 29,083 | 32,075 | 43,030 | 104,188 |
| Wind Capacity, MW |  | 2,555 | 6,765 | 39,435 | 48,755 |

| Fuel | Public (MW) | Non-public (MW) | Total (MW) |
| --- | --- | --- | --- |
| Combined Cycle - Gas | 4,295 | 25,743 | 30,038 |
| Combustion Turbine - Gas | 646 | 463 | 1,109 |
| Nuclear | 9,186 | 6,400 | 15,586 |
| Coal | 4,131 | 4,424 | 8,555 |
| Wind | 10,000 | 38,755 | 48,755 |
| Other |  | 145 | 145 |
| Totals | 28,258 | 75,930 | 104,188 |

## Potential Future Generation Interconnections

The table below summarizes the publicly known potential future generation projects for the ERCOT region.  (IA=Interconnect Agreement, PL=Public Letter)

| Future Generation Interconnections (Public Projects) as of April 30, 2008 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INR | Site Name | Status | County | Region | Fuel | In-Service Date | MW Into Grid | Change from Last Report |
| 06INR0036 | Quail Run Energy Center 2 | IA | Ector | West | Gas-CC | May-08 | 275 |  |
| 06INR0035 | Colorado Bend Energy Center 2 | IA | Wharton | South | Gas-CC | Jun-08 | 275 |  |
| 07INR0027 | South Houston Green Pwr Exp Prj1 | IA | Galveston | South | Gas-CC | Jun-08 | 244 |  |
| 07INR0022 | Airtricity Panther Creek Wind Farm | IA | Howard | West | Wind | Jun-08 | 150 |  |
| 08INR0050 | Victoria Power Station | IA | Victoria | South | Gas-CC | Jul-08 | 332 | New IA |
| 08INR0028 | McAdoo Energy Center | IA | Dickens | North | Wind | Jul-08 | 300 |  |
| 08INR0064 | Laredo Peaking Power Plant | IA | Webb | South | Gas-CT | Aug-08 | 193 |  |
| 03INR0030b | Wild Horse Wind Farm 2 | IA | Cottle | West | Wind | Aug-08 | 39 |  |
| 04INR0017 | Ocotillo Wind Farm 1 | IA | Howard | West | Wind | Aug-08 | 59 |  |
| 04INR0011c | Cottonwood Wind | IA | Shackelford | West | Wind | Aug-08 | 100 |  |
| 04INR0011b | Mesquite Wind Phase 4 | IA | Shackelford | West | Wind | Aug-08 | 136 |  |
| 08INR0055 | Capricorn Ridge III | IA | Coke | West | Wind | Aug-08 | 249 |  |
| 06INR0012a | Sherbino Mesa Wind Farm 1 | IA | Pecos | West | Wind | Sep-08 | 150 | Phased |
| 08INR0038 | M Bar Wind | PL | Andrews | West | Wind | Sep-08 | 194 |  |
| 07INR0034 | Wolf Ridge Windfarm | IA | Cooke | North | Wind | Oct-08 | 113 |  |
| 07INR0025 | Airtricity Lamesa Wind Plant | IA | Dawson | West | Wind | Oct-08 | 183 |  |
| 07INR0037 | Bull Creek Wind Plant | IA | Borden | West | Wind | Oct-08 | 180 |  |
| 07INR0045b | Airtricity Inadale | IA | Scurry | West | Wind | Nov-08 | 212 |  |
| 07INR0045a | Airtricity Pyron Wind Farm | IA | Scurry | West | Wind | Nov-08 | 303 |  |
| 05INR0015a | Gulf Wind 1 | IA | Kenedy | South | Wind | Dec-08 | 283 |  |
| 06INR0022a | Penascal Wind Farm 1 | IA | Kenedy | South | Wind | Dec-08 | 202 |  |
| 07INR0005 | Notrees-1 | IA | Ector | West | Wind | Dec-08 | 150.75 |  |
| 04INR0011e | Hackberry Wind Farm | IA | Shackelford | West | Wind | Dec-08 | 165 |  |
| 07INR0011 | Turkey Track Energy Center | IA | Nolan | West | Wind | Dec-08 | 170 |  |
| 07INR0029 | South Trent Wind Farm | IA | Taylor | West | Wind | Dec-08 | 101.2 |  |
| 08INR0018 | Gunsight Mountain | IA | Howard | West | Wind | Dec-08 | 120 |  |
| 08INR0025 | Pistol Hill Energy Center | PL | Ector | West | Wind | Dec-08 | 300 |  |
| 08INR0037 | Airtricity Panther Creek 2 | IA | Howard | West | Wind | Dec-08 | 220 |  |
| 08INR0053 | Elbow Creek Wind Project | IA | Howard | West | Wind | Dec-08 | 117.3 |  |
| 08INR0059 | Gray Wind Project | PL | Borden | West | Wind | Dec-08 | 141 |  |
| 09INR0026a | Sterling Energy Center | PL | Sterling | West | Wind | Dec-08 | 200 |  |
| 08INR0046 | Bosque Expansion | IA | Bosque | North | Gas-CC | Mar-09 | 255 |  |
| 07INR0036 | Coyote Run Windfarm | IA | Borden | West | Wind | Mar-09 | 225 |  |
| 08INR0065 | Buffalo Gap 4 and 5 | PL | Nolan | West | Wind | Mar-09 | 465 |  |
| 09INR0028 | V H Braunig 6 | PL | Bexar | South | Gas-CT | May-09 | 185 |  |
| 08INR0040 | Lenorah Project | PL | Martin | West | Wind | May-09 | 350 |  |
| 09INR0060 | Wind TexStephens WndFrm | PL | Borden | West | Wind | May-09 | 141 |  |
| 08INR0035 | Cedar Bayou 4 | IA | Chambers | South | Gas-CC | Jun-09 | 544 |  |
| 09INR0027 | Winchester Peaking Plant | IA | Fayette | South | Gas-CT | Jun-09 | 178 |  |
| 09INR0045 | Sand Hill Peakers | PL | Travis | South | Gas-CT | Jun-09 | 90 |  |
| 09INR0026 | Sterling Energy Center | PL | Sterling | West | Wind | Jun-09 | 300 |  |
| 09INR0036 | McAdoo Energy Center II | PL | Dickens | West | Wind | Jun-09 | 500 |  |
| 08INR0003 | Sandow 5 | IA | Milam | North | Coal | Jul-09 | 581 |  |
| 05INR0015b | Gulf Wind 2 | PL | Kenedy | South | Wind | Sep-09 | 400 |  |
| 09INR0015 | Comanche Peak 1&2 Upgrade | PL | Somervell | North | Nuclear | Oct-09 | 86 |  |
| 09INR0006a | Oak Grove SES 1 | IA | Robertson | North | Coal | Nov-09 | 855 |  |
| 03INR0030a | Wild Horse Wind Farm 1 | IA | Cottle | West | Wind | Nov-09 | 60 |  |
| 09INR0034 | Gatesville Wind Farm | PL | Coryell | North | Wind | Dec-09 | 200 |  |
| 09INR0037 | Scurry County Wind III | PL | Scurry | West | Wind | Mar-10 | 350 |  |
| 06INR0006 | Cobisa-Greenville | PL | Hunt | North | Gas-CC | May-10 | 1750 |  |
| 09INR0006b | Oak Grove SES 2 | IA | Robertson | North | Coal | May-10 | 855 |  |
| 09INR0002 | J K Spruce 2 | IA | Bexar | South | Coal | Jun-10 | 750 |  |
| 09INR0001 | Sandy Creek 1 | IA | McLennan | North | Coal | Sep-10 | 925 |  |
| 05INR0015c | Gulf Wind 3 | PL | Kenedy | South | Wind | Sep-10 | 400 |  |
| 06INR0012b | Sherbino Mesa Wind Farm 2 | IA | Pecos | West | Wind | Oct-10 | 150 | Phased |
| 06INR0026 | Wild Horse Mountain | IA | Howard | West | Wind | Dec-10 | 120 |  |
| 12INR0003 | Throckmorton Wind Farm | PL | Throckmorton | West | Wind | Dec-10 | 400 |  |
| 10INR0010 | Jack County 2 | PL | Jack | North | Gas-CC | Jun-11 | 620 |  |
| 07INR0004 | Pampa Energy Center | PL | Gray | West | Coal | May-12 | 165 |  |
| 09INR0024 | B&B Panhandle Wind | PL | Carson | West | Wind | Jun-12 | 1001 |  |
| 12INR0004 | Fort Concho Wind Farm | PL | Tom Green | West | Wind | Jul-12 | 400 |  |
| 15INR0002 | Comanche Peak 3 and 4 | PL | Somervel | North | Nuclear | Jan-15 | 3200 |  |
| 15INR0008 | STP 3 and 4 | PL | Matagorda | South | Nuclear | Jan-15 | 2700 |  |
| 11INR0011 | Victoria City Nuclear | PL | Victoria | South | Nuclear | Jan-15 | 3200 |  |
|  |  |  |  |  |  | TOTAL | 28,258 |  |

# Regional Planning Group Project Reviews

# Oncor submitted a two phase project to relieve congestion related to new wind units in the Lamesa area.  The first phase of the project will upgrade both ends, but not the middle of the Lamesa to Bluff Creek 138 kV line, rebuild the Bluff Creek to China Grove 138 kV line, rebuild the Lamesa to Ackerly Vealmoor 69 kV line to 138/69 kV double circuit, rebuild the Lamesa 138 kV switching station, and build a new 138 kV Ackerly Vealmoor station.  The cost of the first phase of these upgrades is $40.3 M.  The second phase of the project would be done if a third wind unit signs an interconnect agreement.  This phase would add second circuits to all rebuilt lines and include station upgrades at China Grove and Big Spring.  The additional cost of the second phase upgrades is $40.5 M for a total of $80.8 M.  Both phases of this project are being reviewed to ensure that the improvements fit into the likely CREZ transmission solution for the area.

# Oncor submitted a project to construct the Krum Tap Switching Station and rebuild the Krum – Decatur 69 kV line and the Krum Tap 138 kV line as a 138 kV double-circuit line with one circuit in place using a conductor with a minimum rating of 214 MVA. The estimated cost of this project is $17.8 M and is currently in ERCOT Independent Review.

# LCRA submitted a project to add a 3rd 345/138 kV autotransformer at the Zorn substation.  This project should be complete by summer peak 2013 and cost is estimated at $15 M.  This project is currently in ERCOT Independent Review.

# Oncor submitted a project to upgrade the Midland East – Stanton East – Big Spring West – Big Spring Switch 138 kV line.  The proposed upgrade will replace the existing 4/0 ACSR 84 MVA circuit with a single circuit line with a long-term emergency rating of 394 MVA.  The estimated completion date is peak 2010 with a cost of approximately $ 24 M.  This project is being reviewed to ensure that the improvements are compatible with the likely CREZ transmission solution for the area.

# AEPSC submitted a project to increase the reliability of service in the Presidio area.  This project will install a second 138/69 kV autotransformer at Marfa in 2008, install 2-2.4 MW NaS battery units at Presidio in 2009, and replace the existing 69 kV line with a 138kV-capable but 69kV-operated line from Alamito Creek to Chinati to Presidio in 2012.  Total cost of the project is estimated to be $67 M.  This project is currently in ERCOT Independent Review.

# CNP Energy submitted a 2007 Five-Year Plan project to install a new 345/138 kV substation called Rothwood to eliminate potential unserved energy under contingency scenario(s).  The projected completion date is summer 2010 with an estimated cost of $23 M.  This project will be presented to TAC and the ERCOT Board of Directors in May 2008.

# Congestion Management

- Zonal congestion costs during the first quarter of 2008 are almost as much as for the entire year of 2007.

- Two thirds of the zonal congestion costs during the first quarter of 2008 were attributable to congestion between the West and North zones.

- Transmission outages affected the ability to transfer power between West and North zones.  Requests for some of these key outages were not submitted to ERCOT in time to be included in the determination of how many TCRs to sell.  This resulted in West to North TCRs being oversold, contributing to high BENA charges.

CSC Congestion Charges collected from QSEs

| $Million | N_H | S_H | N_S | S_N | W_N | N_W | TOTAL |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2008 total | 6.7 | -- | 11.6 | -6.9 | 40.4 | 8.8 | 60.5 |
| 2007 Q1 | -- | 1.0 | -- | 0.1 | -- | 1.1 | 2.0 |
| 2007 total | 39.8 | 12.5 | -- | -1.5 | 5.1 | 4.4 | 60.3 |

Settlement quality data available through March 2008.

Congestion vs. TCRs – Jan - Mar 2008

| Jan. | N_H | N_S | S_N | W_N | N_W | Month total |
| --- | --- | --- | --- | --- | --- | --- |
| Congestion Charges | 0 | 2.6 | -2.0 | 7.5 | 0.7 | 8.8 |
| TCR Payout | 0 | 1.7 | 0.6 | 15.7 | 1.8 | 19.9 |
| Est. Shortfall | 0 | 0.9 | 2.6 | 8.2 | 1.1 | 11.1 |

| Feb. | N_H | N_S | S_N | W_N | N_W | Month total |
| --- | --- | --- | --- | --- | --- | --- |
| Congestion Charges | 0 | 7.0 | -0.5 | 8.5 | 8.1 | 23.1 |
| TCR Payout | 0 | 4.9 | 0.2 | 27.6 | 28.9 | 61.7 |
| Est. Shortfall | 0 | 2.1 | 0.7 | 19.1 | 20.8 | 38.6 |

| Mar. | N_H | N_S | S_N | W_N | N_W | Month total |
| --- | --- | --- | --- | --- | --- | --- |
| Congestion Charges | 6.7 | 2.0 | -4.4 | 24.4 | ~0.01 | 28.7 |
| TCR Payout | 8.0 | 1.3 | 2.5 | 49.1 | 0.05 | 61.0 |
| Est. Shortfall | 1.3 | .7 | 6.9 | 24.7 | 0.04 | 32.3 |

Congestion & TCR Report:  for the details of the tables below (intervals, flows / limits, costs and quantities) see the TCR_Congestion20080414 presentation to the April WMS (Item 6 in the Key Documents) at the following link: http://www.ercot.com/calendar/2008/04/20080416-WMS.html

# Other Notable Activities

- All postings referred to below can be found at http://oldercot.ercot.com/tmaps unless otherwise indicated.