## Slide 1: Texas Nodal Market Implementation Program Update
Jerry Sullivan

## Slide 2: Agenda
Program Status
ERCOT and Market Participant Readiness
Schedule
  Single Entry Model (NMMS)
  Go-Live Plan
Market Participant Identity Management (MPIM)
Quality
Cost

## Slide 3: Program Status: Summary
Nodal Delivery status remains:
ERCOT Readiness status is:
MP Readiness status is:
Cost*
Schedule
Scope / Quality
Green
Amber
Green
Amber
Nodal Delivery
EDS1
EDS2
EDS3
EDS4
Green
Red
Red
Red
Amber
Amber
Green
Current performance trend is acceptable
Significant recent improvement
Schedule indicators under significant stress
Primary Rating Indicators
Secondary Indicators
* Anticipated approval at May 8 PUC open meeting
Issues (EDS):
EDS 2 - State Estimator
EDS 3 - ACE testing - will return to Amber if TAC approves revised testing approach (current meeting)
EDS 4 - Outage Scheduler and System Failover

## Slide 4: ERCOT Readiness
ERCOT Readiness status is Amber
ERCOT Executive Readiness Survey is updated monthly
Received updates to Transition Plans this past week - the next update is scheduled for June
Business Process model is being updated in conjunction with procedures development
Procedure plans have been created for each department and are being monitored and reported in Procedures scorecard
Steady progress on training
Staffing plans developed; recruiting ongoing; timeframes established
Staffing, Procedures and Training progress being updated on Nodal scorecard weekly
Procedures and Training completion target is by August 31, 2008

## Slide 5: Market Participant Readiness
Engagement and Training [green] – Vast improvement in last few weeks (see following slides)
Connectivity and Telemetry [green] – Connectivity metrics complete for most MPs - outliers are new to the program and need to go through EDS process
Trials Participation [green] – Actively measuring EDS3 and EDS4 trial participation metrics
Registration and Qualification [amber] due to MP10 (Resource to Node mapping)
  ERCOT received responses from 80 percent (143 of 179) of Resource Entities; scoring based on email from resource indicating acceptance of mapping; missing emails scored amber
  Per the metric, the QSEs responsible for the resource carry the score (12 of 37 QSEs turned amber as a result of this metric)
  In June the standard becomes more stringent: QSEs must ensure that Resources Entities certify the accuracy of the mapping in ERCOT systems
Looking ahead
  Numerous metric milestones are upcoming in next two months:
    MP17 – MP Qualification Activities begins measurement on 6/2
    MP20 - MP Ability to Submit Outage Information begins measurement once it approved by TAC (anticipated 5/8)
Market Participant Readiness status is Green

## Slide 6: Market Participant Readiness
Market Participants with Engagement Status RED*
* Data as of noon 4.30.08
Denton
GUES
LCRA
Magic Valley
STEC
Texas Municipal Power
Texas-New Mexico Power
TDSPs:
Affordable Power
Alliance
Ambridge
Andeler
APNA
Aquila
BOA
Barclays
Bear
Blu Power
Brilliant
Cargill
Chain Lakes
Citadel
Clearview
Conoco Philips
DTE
  Duke
  Electric Now LP
  Epcot
  Fortis
  Freedom
  Gexa
  Himalaya
  Integrys
  Juice
  Just Energy
  Kansas City P&L
  Keystone
  Lehman Brothers
  Liberty
  LPT
  Merrill Lynch
  Mirant
QSEs w/o Resources:
  Morgan Stanley
  National
  Pegasus
  Repower
  Sempra Energy Solutions
  Sitara
  Spark
  Tara
  Texpo
  Trieagle
  UBS
  Urban
  Vantage
  Vega
  W P&L
  WCW (dropped Out)
ERCOT Account Management made a concerted and effective effort in reaching out to over 70 MPs
Since 4/18, 49 scorecard updates received, turning scores GREEN for 41 MPs
For Engagement and Training:
  TDSPs and QSEs with Resources segments have turned GREEN
  QSEs without Resources improved from RED to AMBER
Outreach and Updates will continue until Round 4 survey published mid-May
Update and Outlook
Airtricity
AEP
EnergyCo
FPL
Fulcrum
Invenergy
J Aron
Sweetwater
Topaz
Xtend
QSEs w/ Resources:
(Strike through): represents respondents that turned green since 4/18

## Slide 7: Market Participant Readiness
Market Participants with Training Status RED*
Alliance
Andeler
APN
Bear
BLU
Cargill
Citadel
Electric Now LP
Epcot
Fortis
Freedom
Glacial
Himalaya
Integrys
Kansas City P&L
  Lehman Brothers
  Liberty
  LPT
  Mirant
  National
  Pegasus
  Sitara
  Tara
  Texpo
  UBS
  Urban
  Vantage
  W P&L
  WCW (dropped out)
Magic Valley
STEC
QSEs w/o Resources:
TDSPs:
  QSEs w/Resources: 16% (6 of 37)
  QSE w/o Resources: 31% (26 of 84)
  TDSPs: 6% (1 of 18)
  LSEs: 69% (70 of 102)
  * for all MP metrics
Summary: MPs that are RED*
* Data as of noon 4.30.08
(Strike through): represents respondents that turned green since 4/18

## Slide 8: Schedule: Single Entry Model (NMMS)
Situation
NMMS deployment to production environment is dependent on ability to ensure data consistency between zonal and network models
Ability to test for data consistency between zonal and nodal network models requires EMS to import data from NMMS, via the EMS CIM importer, so that a nodal network model can be generated
The EMS CIM importer will not be delivered on schedule (May 2)
  Pre-FAT testing was due to be completed on April 25, with FAT completion following by May 2
  Pre-FAT testing still ongoing as of today (April 30)
Impact
Delay in completion of EMS CIM importer will delay deployment of NMMS to production environment
Length of potential delay is under review
No impact as yet to Nodal Go-Live of December 1
  Deployment of NMMS to production is not on critical path but data validation (as opposed data consistency) check between zonal and nodal models is on critical path and will be required before 168-Hour Test
  Data validation check requires comparison of multiple network models - Base (i.e., zonal), NMMS, EMS and MMS
Current NMMS (Single Point Entry) Go-Live date (June 2) is delayed due to delay in receipt of the EMS CIM importer

## Slide 9: Go-Live Plan: will encompass key activities/actions post the successful completion of the 168-Hour Test
Key Elements of the plan include:
  Following completion of 168-Hour Test, ERCOT, QSEs, and TSPs will operate nodal systems 24x7 in parallel with their zonal systems
  Two LFC tests, one after the 168-Hour Test and one before Go-Live sequence, plus allowance for two discretionary tests
  MP & ERCOT 30-day key system environment freeze before Texas Nodal Market Implementation Date (TNMID)
  QSEs must operate zonal systems for 7 days post TNMID by submitting BES offers, AS offers, and Resource plans, and maintain operational ability on key zonal systems 30 days post TNMID
  QSEs’ testing after Go-Live sequence must apply to ERCOT for re-testing 30 days after TNMID
  Upon cut-over to nodal system operations, nodal backup systems are first contingency; given multiple problems with critical nodal systems, ERCOT will switch to constant frequency control for up to 12 hrs, then revert to zonal system operations
Next Steps | Target Completion Date
Complete ERCOT review | April 7th
Present to TPTF for Vote | May 22nd
Present to TAC for Vote | June 5th
Present to BoD | June 17th

## Slide 10: Market Participant Identity Management (MPIM)
ERCOT to have compliant system in place by early June; required by July 1
MP users with access to Critical Cyber Assets (CCA) systems must provide attestations as to training and personnel
Attestations will come from MP User Security Administrator (MP-USA) and will take two forms: the first attesting that the user has completed training requirements in accordance with the CIP-004-1, and the second attesting that the MP has fulfilled all CIP-004-1 requirements or revisions thereof
MPIM will send notifications to the user and MP-USA on a regular basis regarding need for annual training
ERCOT is subject to and bound by NERC standards, including CIP-004-1, Cyber Security – Personnel and Training

## Slide 11: Parallel Operations
21.12.5 Reinstatement of Zonal Protocol Provisions
Market Participants shall maintain their zonal generation control systems for a period of thirty (30) days after the Texas nodal market implementation date. In the event of a contingency in implementation of the nodal market design for generation control subsystems (Load Frequency Control and Security Constrained Economic Dispatch as defined in the Nodal Protocols) or settlement systems that causes the ERCOT CEO to deem it necessary to reinstate a Zonal Protocol section, ERCOT shall issue a Notice stating the date and time on which the Zonal Protocol section will be reinstated. The time lines set forth in Section 21.12.2, Notice to Market Participants of Activities Essential for Nodal Market Open, shall not apply to any such reinstatement. That Notice will also include a description of the reason why the reinstatement is necessary and a proposed timeline for resolution of the system failure
  MPs must operate zonal systems for 7 days post Texas Nodal Market Implementation Date (TNMID) by submitting BES offers, AS offers, and Resource plans, and maintain operations ability on key systems for 30 days post-TNMID
  Current settlements system is being upgraded and will be used going forward for long running zonal systems
  There would be a cost to MPs to extend maintenance of parallel systems
  30-day parallel operations’ period is considered adequate, but subject to review if new considerations dictate
Current ERCOT plans to operate certain zonal and nodal systems in parallel post- Go-Live are based on Protocol provision (see below)

## Slide 12: Quality Assurance
Overall volume of defects, the volume of Severity 1 and 2 defects, and the rate of increase in Severity 3 defects pose risks to the project
Mitigation Measures:
Defect analysis as a basis for test planning
Testing emphasis applied to high risk areas/projects
Shifting emphasis to more comprehensive testing earlier in the software life cycle (i.e., development and pre-FAT vs FAT)