## Slide 1: Texas Nodal Market Implementation Program Update
Jerry Sullivan

## Slide 2: Agenda
Program Status
Schedule Revision
  Situation and Plan Forward Update
AREVA (CIM) Status
TSP Data Validation Status

## Slide 3: Program Status
Nodal Delivery status is:
ERCOT Readiness status is:
MP Readiness status is:
Cost*
Schedule
Scope / Quality
Green
Amber
Green
Red
Nodal Delivery
Green
Red
Amber
Current performance trend is acceptable
Changed due to schedule impact
Primary Rating Indicators
Secondary Indicators
MP-11 (Resource Asset Registration), while improving, drove overall status to amber
EDS Issues
EDS 2: Data for State Estimator impacting performance and accuracy; Network Operations Model performance issues
EDS 3: Carry-over issues resulting from EDS 2 (SCED and LMPs) and LFC
EDS 4: Verification of Outage Evaluation System Functionality (Areva) and System Failover
* Slippage beyond Dec. 1 will have cost implications
EDS1
EDS2
EDS3
EDS4
Green
Red
Amber
Red

## Slide 4: Market Participant Readiness
MP-11: Missing authorized RARFs [Resource Entities]
Status
  Close to receiving all expected RARFs
    Currently 98% of MWs are reporting in.
  RARF data review is underway.
    Review primary data set for Nodal systems testing (SCED, LFC, RUC, DAM)
    Approximately 30% of MWs complete to date.
GENERATION
CAPRICORN RIDGE WIND LLC (RE)
POST WIND FARM LP
CAPRICORN RIDGE WIND II LLC (RE)
TEXAS BIG SPRING LP
BASS ENTERPRISES PRODUCTION CO
LAAR
EAGLE ENERGY PARTNERS I LP (RES)
FORMOSA PLASTICS CORPORATION AMERICA (RES)
PRIZE PETROLEUM LLC (RE)

## Slide 5: Schedule Revision: Situation
The repetitive slippage of the EMS Common Information Model (CIM) importer (combined with other software slippages and data population and validation concerns) necessitates a delay in the 168 hour test and a change to the Nodal “go live” date.
  The project needs CIM to work before we can move on as it is integral to the exchange of information among key applications
  We are analyzing the integration and testing required with the slippage of the EMS CIM importer and how the delay affects other applications (e.g., NMMS, MMS, OS, etc.).
  Options have been and will continue to be reviewed with TPTF.
The plan is to review the existing integrated schedule to:
  Determine delay impacts to the Critical Path
  Allow for increased testing and integration re. CIM effort and related applications
  Analyze budget impacts
The December 1 Nodal Go-Live date has been delayed

## Slide 6: Schedule Revision: Plan Forward
Objective
  Develop a credible and achievable Go-Live date that optimizes cost and schedule.
Process
  Revisit the existing integrated schedule and adjust, as necessary, dependencies, sequential tasks, and integration efforts
  The previous integrated schedule focused on expedited delivery of software to the early delivery systems (EDS). The new integrated schedule may:
    Adjust dates/timeframes of EDS market trials
    Allow for more time for integration and testing
    Allow more time for data validation
  Review the schedule and options with TPTF
  Continue to stress integration and testing
  Dedicate a team to drive development of the new schedule.
Timeline
  No deadline for setting a new schedule date, but efforts are focused on completing the review as soon as possible
  Major unknown is the final delivery date of the EMS CIM importer and implications on downstream applications, etc.
ERCOT is aggressively pursuing the development of a revised Nodal project schedule

## Slide 7: Schedule
The EMS CIM importer delivery experienced delays prior to May 2. The current June 13th delivery date for FAT completion, recently communicated to the BoD, will not be met by AREVA. (See next slide.)
Nearly all software from all vendors is on-site and being tested. So far, we expect to meet all protocols (with current scope) in the revised schedule
Integration and validation are key ongoing activities.
Risks to the revised schedule:
  Relaxing scope control; we can ill afford to open up software to significant changes.
We will be working with TPTF on options, plans, and dates
Not to scale
Today
Previous commitment of EMS CIM Delivery Date (May 2)
Latest EMS CIM Delivery commitment date (June 13)
Go-Live Period*
Final Integration Activities
Critical Schedule Events/Activities
168-Hour
Test
Go Live Date
Post Go Live Activities
?

## Slide 8: AREVA (CIM) Status
The CIM Importer is late for Pre-FAT completion…
  Results in late defect identification and fixes
  Results in late FAT completion
  Results in delayed deployment
…but AREVA is making progress in EMS application development
  EMS 5 (final EMS deployment) due to FAT next week
CIM Importer is delayed beyond its current June 13th scheduled delivery

## Slide 9: TSP Data Validation Status
ERCOT Single Entry Model (SEM) Process
  Model creation
  Data/model validation – ERCOT
  Data/model validation – TSPs
Key Issue
  TSP data/model validation timeline; TSPs indicate a need for significantly more time than the schedule currently permits
Status
  No current resolution
  Meetings are ongoing with the Network Data Support Working Group
  A follow up meeting of NDSWG is scheduled for Thursday, May 29. TSPs will meet in Austin (or via WebEx) to help understand and resolve the timeline issues.
ERCOT and TSPs are still working to resolve a key difference regarding the time required for data validation