Texas Nodal Market

168-Hour Test Procedure

v0.02

Revision History

| Date | Version | Description | Author |
| --- | --- | --- | --- |
| 03/28/2008 | 0.01 | Initial Draft | EDS Test Team |
| 06/02/2008 | 0.02 | Consideration of comments from ERCOT Staff | EDS Test Team |

Table of Contents

1.0	Introduction	4

2.0	Entry Criteria	5

3.0	Exit Criteria	5

4.0	168-Hour Test Environment Controls	6

4.1	Change Control Guidelines for ERCOT	6

4.2	Change Control Guidelines for MPs	6

5.0 	168-Hour Test Procedure	6

6.0	Personnel Staffing	7

6.1 	ERCOT Operations	7

6.2 	QSEs Representing Generation Resources	8

6.3 	QSE Representing Load Resources	8

6.4 	QSEs representing Load without Resources	9

6.5 	QSEs without Resources or Loads	9

6.6 	TSPs	9

7.0	Communications Plan	10

8.0	Role of TPTF during the 168-Hour Test	10

9.0	Establishment of Test Credit Limits for Market Participants	10

10.0	CRR Auctions	11

11.0	Appendix A:  Severity level definition	12

12.0	Appendix B:  Readiness Metrics to be completed before start of 168-Hour test	13

13.0	Appendix C:  Readiness Metrics to be completed by the end of 168-Hour test	14

# 1.0	Introduction

As the Early Delivery System (EDS) Team completes integration of the Nodal systems, ERCOT will conduct a readiness test of all Texas Nodal Systems. The test will demonstrate the how the Nodal Protocols and Nodal requirements documents have been implemented and will include a systems stability test.  The systems stability test requires the real time systems performing SCADA, Network Security Analysis, Transmission Constraint Management, SCED, HRUC and LFC as well as the Day Ahead functions including DAM, DA Security Analysis, DA RUC and including the Nodal support systems including Network Model Management, Outage Scheduler, Outage Evaluation tools all which must operate without significant error for at least 168 continuous hours.  On detection of any significant error of the operations systems (non-settlement), ERCOT and its vendors and contractors will correct the problem and re-start the 168-Hour Test.

ERCOT shall also provide QSEs with test settlement statements for each completed Operating Day of the 168-Hour Test.  The test settlement statements for each Operating Day will use calculated dispatches and LMPs from SCED and actual generation meter data from the EPS metering systems to provide simulated settlement statements for real-time and day ahead operations.  QSEs shall review the test settlement statements and mock invoices for errors and provide feedback to ERCOT for resolution.    ERCOT will work with Market Participants to resolve any settlements issues identified during the 168-Hour Test, 30 days prior to the Texas Nodal Market Implementation Date (TNMID).

This procedure describes a coordinated plan of actions among ERCOT and Market Participants to test the entire Texas Nodal System using test operations as close as possible to the expected operation of ERCOT’s systems after the TNMID. The test is scheduled to begin 30 days prior to the Nodal Market “Go-Live Period”, (nominally, September 1, 2008).

This 168-Hour Test Procedure establishes the conduct of operations by ERCOT, QSEs, and Transmission Service Providers (TSPs) to verify of all systems functionality, integration, and systems stability.  This procedure details the activities that must be performed to complete the 168-Hour Test as required by the Nodal Transition Plan.

Successful completion of the 168-Hour Test will demonstrate the robustness of the nodal software, processes and systems.  Once complete, final preparations will immediately begin to transition to full implementation of the nodal market design as documented in the Go-Live Procedures.

The purpose of the activities and robustness of operations outlined in this procedure will assure the ERCOT systems meet Nodal Protocol requirements, operations are conducted according to approved ERCOT procedures, and settlement systems produce accurate results in a form suitable to Market Participants.  Benefits of the full operations testing include:

- Exercising of all software and systems

- Exercising of all business processes for ERCOT staff and Market Participants

- Stability testing in a simulated real-time environment

- Ensuring that the Market Information System produces correct data to the posting systems

- Exercising of all Market Participant interfaces to ERCOT systems

- Exercising of the ERCOT systems to support the Independent Market Monitor (IMM) and Texas Reliability Entity (Texas RE) prior to the TNMID

ERCOT staff and all Market Participants must work closely together to assure the successful testing of the Texas Nodal Market while minimizing project risk; assuring the reliability of the ERCOT computer systems, and fully exercising all Market Participants interfaces to ERCOT.  All Market Participants should expect that this 168-Hour Test Procedure will require significant effort, unusual work hours and additional labor costs to support testing efforts.

During the 168-Hour Test, all outputs of the Nodal system are for testing purposes only and at no times should be acted on by MPs to manage reliability or the energy market.

# 2.0	Entry Criteria

The following criteria must be completed for ERCOT to start the 168-Hour Test.

- Market Participant User Security Administrator (MP USA) enters/validates roles for Market Participant employees into the nodal Market Participant Identity Management system (MPIM) to ensure access to nodal systems.

- ERCOT reports to TPTF that all Severity Level 1 and 2 defects have been resolved

- ERCOT presents for TPTF approval a plan to resolve all Severity Level 3 defects prior to TNMID

- ERCOT provides a list to TPTF of any functionality expected to be operational after the TNMID that is not to be included in the 168-Hour Test

- ERCOT certifies that all operating procedures to be used after the TNMID have been approved for implementation

- ERCOT certifies that the readiness metrics listed in Appendix B have successfully been completed

- ERCOT completes the testing as outlined in EDS1, EDS2, EDS3, and EDS4 test procedures and has affirmed that the readiness metrics tied to such have been successfully completed

- Market Participants’ systems meet the failover timing requirements without effecting ERCOT operations functionality as required in the protocols

- ERCOT, with the approval of the TPTF, declares the system ready for the start of 168-Hour Testing

# 3.0	Exit Criteria

The following criteria must be completed for ERCOT to exit the 168-Hour Test.

- 168 hours of continuous nodal systems testing has been completed without encountering any Severity Level 1 or 2 defects.

- ERCOT provides a test summary report to TPTF outlining the successful testing processes

- ERCOT certifies that readiness metric R3 has been successfully completed

- ERCOT provides a plan to TPTF to resolve any Market Participant comments on the settlement and invoice statements for the period covered by the successful 168-Hour Test

# 4.0	168-Hour Test Environment Controls

ERCOT, QSEs and TSPs, as applicable to each entity, shall maintain a fully functional nodal system operating Supervisory Control and Data Acquisition (SCADA), Generation Control, Network Security Analysis, Transmission Constraint Management (TCM), SCED, Hour-Ahead (HA) Security Analysis, Hourly Reliability Unit Commitment (HRUC), DAM, Day-Ahead (DA) Security Analysis, Day-Ahead Reliability Unit Commitment (DRUC), Outage Scheduler, Outage Evaluation, Network Model update support system including Network Operations Model Change Requests (NOMCRs), settlement systems for both the DAM and Real-Time and any other system expected to be operational after the TNMID.

All ERCOT systems shall be under strict change control procedures administered by the Director of Operations and Infrastructure and Nodal Executive Director. No software changes to ERCOT systems will be implemented during the 168-Hour Test without stopping testing and starting a new 168 hours of testing.

During the 168-Hour Test, all nodal systems will be managed as if the systems were fully in production 7x24, exercising the same procedures used for zonal production operations to implement software updates and data base changes. Changes to nodal systems that impact Market Participants will require re-starting the 168-Hour Test at a mutually agreeable time after when Market Participants have implemented the required changes.

# 4.1	Change Control Guidelines for ERCOT

ERCOT will enforce a strict code change control procedure managing all aspects of the Texas nodal systems including the following: server and desktop operating systems; security changes; application patches; network changes; storage changes; and user access changes. No new functionality that did not exist at the commencement of a 168-Hour Test will be allowed to be introduced to any system that is expected to be operational after the TNMID without re-starting the entire test period. Software modifications intended to fix defects in functionality found during the 168-Hour Test may be made only with the intent of re-starting the entire 168-Hour Test.  Every effort will be made to ensure that operating systems and security systems remain as is during the 168-Hour Test.

Failures of physical hardware that effect operations functionality will be cause to re-start the 168-Hour Test.

# 4.2	Change Control Guidelines for MPs

Market Participants must also enforce a strict code change control procedure managing all aspects of their Texas nodal systems during the 168-Hour Test.  All Market Participant nodal systems should be managed as if the systems were fully in production, exercising the same procedures used for production operations to implement software updates and database changes.  Market Participants should exercise good judgment when considering migration or upgrades to ensure that the integrated nodal system is not affected.

# 5.0 	168-Hour Test Procedure

The day prior to the 168-Hour Test, ERCOT will conduct a test the Day-Ahead Market for the purpose of procuring test quantities of Ancillary Service (AS) for all Operating Hours of the day of the start of the 168-Hour Test.  QSEs representing Resources that intend to participate in nodal shall provide test AS offers such offers being typical of that expected for current market conditions.

Each QSE shall update its Current Operating Plan, indicating expected Generation and Load Resource Status, limits and AS Resource Responsibility.  TSPs shall update the nodal Outage Scheduler with Transmission Element outages according to the requirements of the nodal Protocols.

ERCOT shall execute the Day Ahead Security Analysis and Reliability Unit Commitment for the next operating day.

ERCOT shall conduct a complete test of all nodal systems software and operating procedures, and simulate real time dispatch of the ERCOT Grid in order to to emulate sufficiently the actual operation of the nodal system according to the protocols.  During the test, if any Severity Level 1 or 2 defects are discovered, ERCOT shall repair the defect and re-start the 168 hour clock of the test. Test results from the prior DAM are acceptable to be used for the current Operating Day if the re-start of the test only involves the Real Time systems.  However, if Severity Level 1 or 2 defects are discovered in the DAM, then the defect must be repaired or resolved and a re-start of the real time systems test will be required beginning at midnight the next Operating Day after defect resolution.

ERCOT must provide sufficient testing to completely fill 168 hours with quality data so that true settlement statements can be provided for an entire seven consecutive days of test operations.

# 6.0	Personnel Staffing

ERCOT, QSEs, and TSPs will continuously perform full 7x24 operations of the nodal systems including DAM testing as outlined below.  By continuously operating as if the nodal system is in full control of the ERCOT System (except that nodal generation control outputs are blocked at the QSE), any defects will become apparent quickly and ERCOT will be able to direct resolution and re-start the test if necessary.   The following describes the staffing required by function:

# 6.1 	ERCOT Operations

ERCOT shall staff appropriately to execute the Adjustment Period and Real-Time Operations tasks 7x24. ERCOT operators will assure that the LFC calculations, transmission security violations, contingency lists, Load forecasts, dynamic limits, wind forecasting, Outage evaluation tools, Outage Scheduler, HRUC, MIS, and all other real-time processes are fully exercised for continuous trial operations. ERCOT operators will assure that any Transmission Constraint activated for control in SCED is realistic and representative of actual operating conditions on the ERCOT Grid.

ERCOT shall conduct the Day-Ahead Market operations each day (operational (7x8) simulating purchases of Ancillary Service and administration of the energy market operations of the DAM.  These processes include calculation and use of the ACL as well as CRR offers into the DAM.

ERCOT shall produce test Settlement Statements, Settlement Invoices and Shadow Settlement Extracts for all Market Participants registered to participate in the nodal market design according to the settlement timelines in the Protocols.  ERCOT will also accept test Disputes on the test settlement statements.  Data upload process for generation data will follow the currently-established timeline and will be uploaded into nodal settlements systems synchronously with updating the zonal settlements systems

# 6.2 	QSEs Representing Generation Resources

QSEs representing Generation Resources must be sufficiently staffed to ensure continuous operation of the nodal generation control systems, 7x24 to support ERCOT’s ongoing operations.  QSE operators shall provide all SCADA data required by protocols to support real-time operation of the nodal systems.  QSE operators shall keep the Current Operating Plans up-to-date to reflect projected Generation Resource Status, limits and AS Resource Responsibility.  Current Operating Plans shall be updated based on results from the nodal market systems for Ancillary Service but should project actual expected Resource availability.  QSEs with Generation Resources shall continuously update their Resource limits in Real-Time according to the nodal protocol requirements.  QSE operators will periodically view the generation control outputs and the Base Points received from ERCOT.  QSE operators will report to ERCOT any outstanding deficiencies or obvious reasonability errors.

QSEs must continuously maintain a valid Three-Part Supply Offer to sell energy, Output Schedules, or Incremental / Decremental Offer Curves for any available Generation Resource during the 168-Hour Test.  Three-Part Offers, Output Schedules, or Incremental / Decremental Offer Curves shall be similar to those that the QSE expects to use after the TNMID.  Similarly, if the QSE qualifies its Generation Resources to offer Ancillary Service into the DAM, the QSE shall make AS offers during the 168-Hour Test DAM that are reasonably representative of those expected after the TNMID. During the 168-Hour Test, QSEs representing Generation Resources must participate in the DAM AS testing seven (7) days per week.  Participation in the Day-Ahead Energy market is voluntary and QSEs may also submit energy-only offers and bids into the test operation of DAM; if made, such offers and bids must reasonably represent true market conditions.  Three-Part offers and Current Operating Plan must be maintained 7x24 to support testing of RUC. Any energy awards from the test DAM will be appropriately entered into the Current Operating Plan for each Resource, provided that the Resource is expected to operate on-line during the 168-Hour Test. QSEs are requested to not make DAM offers for energy or AS on Resources that are highly unlikely to actually be on-line during the 168-Hour Test. If an actual Forced Outages of Resources or changes to a Resource’s capability should occur during the test, the QSE should be report such in the COP and through Real Time Telemetry.

QSEs shall review the test Settlement Statements provided by ERCOT for accuracy and report any deficiencies to their Client Relations Representative at ERCOT or to the ERCOT Help Desk as soon as reasonably possible.

QSEs and the Resource Entities they represent shall follow the appropriate process and timelines to communicate model changes to ERCOT.  ERCOT may waive protocol requirements for NOMCRs if such is required to facilitate completion of the 168-Hour Test.

# 6.3 	QSE Representing Load Resources

QSEs representing Load Resources must maintain all SCADA data required by ERCOT to support real-time operation of the nodal systems including management of all SCADA telemetry according to the nodal protocols.  QSE operators will keep the Current Operating Plan up to date reflecting projected Load Resource Status, limits and AS Resource Responsibility.  Current Operating Plans shall be updated based on results from the nodal market test systems.

QSEs representing Load Resources must participate in the DAM AS testing seven (7) days per week.  During these periods, QSEs are requested to maintain valid offers for Ancillary Service in the DAM which should be reasonably representative of the amounts expected after Go-Live.  Current Operating Plans must be maintained 7x24 for each Resource to support testing of RUC and any awards from the test DAM must be appropriately entered into the Current Operating Plan for each Resource throughout the duration of the 168-Hour Test. If an actual Forced Outages of Resources or changes to a Resource’s capability should occur during the test, the QSE should be report such in the COP and through Real Time Telemetry.  QSEs shall provide test AS offers only on Load Resources expected to be available for each day of the 168-Hour Test.

QSEs shall review the test Settlement Statements provided by ERCOT for accuracy and report any deficiencies to their Client Relations Representative at ERCOT or to the ERCOT Help Desk as soon as reasonably possible.

QSEs and the Resource Entities they represent shall follow the appropriate process and timelines to communicate model changes to ERCOT.  ERCOT may waive protocol requirements for NOMCRs if such is required to facilitate completion of the 168-Hour Test.

# 6.4 	QSEs representing Load without Resources

During the 168-Hour Test, QSEs representing Load without Resources must participate in the DAM testing.  QSEs must participate in testing seven (7) days a week.  During this period QSEs with Loads, who expect to participate in the DAM beyond AS self-arrangement, should provide ERCOT with DAM bids for energy, test offers or bids for Point-to-Point (PTP) Obligations, Energy Trades, Capacity Trades, etc that represent true market conditions. Such offers and bids shall be representative of current market conditions and reflect reasonable purchases and sales.

QSEs shall review the test Settlement Statements provided by ERCOT for accuracy and report any deficiencies to their Client Relations Representative at ERCOT or to the ERCOT Help Desk as soon as reasonably possible.

# 6.5 	QSEs without Resources or Loads

During the 168-Hour Test, ERCOT requires QSEs without Resources or Loads, who expect to participate in the DAM after the TNMID to participate in the DAM testing.  QSEs should provide ERCOT with DAM bids for energy, test offers or bids for Point-to-Point (PTP) Obligations, Energy Trades, Capacity Trades, etc. representing true market conditions.

QSEs shall review the test Settlement Statements provided by ERCOT for accuracy and report any deficiencies to their Client Relations Representative at ERCOT or to the ERCOT Help Desk as soon as reasonably possible.

# 6.6 	TSPs

TSPs must maintain all SCADA data required by ERCOT to support the real-time operation of the nodal systems. TSPs shall provide updates to the Outage Scheduler of any Outage that is required by the Nodal Protocols.  TSPs shall manage the SCADA data telemetered to ERCOT with the same level of support required by the Nodal Protocols.

TSPs shall support ERCOT in managing the Network Operations Model and model updates to correct errors. TSPs shall use the NOMCR process to communicate model changes to ERCOT.  At ERCOT’s request, all TSPs shall review ERCOT’s model of the TSP’s system and provide ERCOT with assistance in verifying the modeling of any Private Networks that connect to the TSPs system.  ERCOT may waive protocol requirements for NOMCRs if such is required to facilitate completion of the 168-Hour Test.

# 7.0	Communications Plan

Once the 168-Hour Test starts, ERCOT will conduct daily conference calls to inform all Market Participants of newly-discovered problems and resolutions to previously-announced issues.  ERCOT shall post to the MIS Secure Area, within a reasonable time after receiving notice of an issue, a summary of all outstanding software and hardware issues reported to ERCOT’s issue tracking system, Quality Center.  A summary listing of all Severity 1, 2, 3, 4 and 5 defects shall be provided to Market Participants upon their request. ERCOT will summarize all trend indicators.  On the Friday conference calls, ERCOT will discuss 168-Hour Test progress and requirements for weekend operations.

ERCOT will make presentations to TPTF outlining the test results and summarize any problems with completing the 168-Hour Test.

# 8.0	Role of TPTF during the 168-Hour Test

During the 168-Hour Test, TPTF’s Quick Response Working Group will be available for consultation in determining the resolution of defects and for determining the severity of certain defects where the severity is in question.  This group will be available to assist ERCOT in making decisions regarding system functionality and appropriate classification of specific defects found during the 168-Hour Test. Following the 168-Hour Test, TPTF shall review and approve the final report of the test results and authorize implementation of the Go-Live Plan.

Any decisions made by the Quick Response Working Group will be vetted at the next scheduled TPTF meeting. Special meetings of the TPTF may be called to facilitate resolution of specific defects or problematic issues.

TPTF will continue performing Market Readiness reviews and will authorize the closure of completed measurement metrics and may forward additional new metrics as may be required.  The TPTF chairman will report to TAC on the progress of 168-Hour Testing.

# 9.0	Establishment of Test Credit Limits for Market Participants

Seven (7) days prior to the start of the first attempt of the 168-Hour Test, ERCOT shall provide a test assessment of each Market Participant's creditworthiness and determine the amount of unsecured credit for each Market Participant for the purposes of conducting the 168-Hour Test.  ERCOT will establish a test credit limits for test CRR auctions. ERCOT shall monitor test credit exposure and enforce test Financial Security requirements as required to simulate reasonable Market Participant operations during the 168-Hour Test.

During the course of the 168-Hour Test (actual timing to be determined) a CRR market will be created and opened.  This will allow Market Participants the opportunity to practice allocating a portion of their Available Credit Limit to CRR auction activities and see the residual impact on credit available for other market activities.

# 10.0	CRR Auctions

A test CRR Auction will be provided prior to the 168-Hour Test which will offer CRRs that will be effective for the duration of the tests required to successfully complete the testing requirements.  The test CRR auction will be conducted as part of CRR EDS activities during EDS 3 Release 7.5 (CRR mock monthly Auction).  ERCOT will provide notice to all Market Participants of the test auction schedule, for submission of test PCRR nominations, publication of PCRR/MCFRI test results, test bid submission windows, test auction execution, test posting of results, and test Market Participant.  Market Participants must review the ownership records prior to the 168 Hour Test to verify expected results.

# 11.0	Appendix A:  Severity level definition

| Severity Level | Definition | Description |
| --- | --- | --- |
| 1 | Data Loss/Critical Error | Defects that render unavailable the critical functions of the system under test. These include errors such as system errors, application failures, loss of data, incorrect calculations, inability to transfer data, failure to access database, and inability to display information to the user. |
| 2 | Loss of functionality without workaround | Defects that render unavailable partial functionality of the system under test with no workaround available. These include errors such as incorrect information displayed to the user, information not updating correctly, extracts failing, and missing export files. |
| 3 | Loss of functionality with workaround | Defects that render unavailable partial functionality of the system under test with a workaround available. These include errors such as incorrect message displayed, optional information missing or not displayed correctly, not receiving e-mail notifications, and incorrect defaults. |
| 4 | Partial loss of a feature set | Defects that affect a feature that is not executed on a frequent basis and there is not a significant impact on the system. These include errors such as help information, filtering, and consistent naming. |
| 5 | Cosmetic/Documentation Error | Defects that are cosmetic and need to be resolved, but are not a factor in the functionality or stability of the system. These include errors such as field alignment, report formatting, drop down list order, fonts, column order, and documentation that is inconsistent with the system(s) as tested. |

# 12.0	Appendix B:  Readiness Metrics to be completed before start of 168-Hour test

Commercial Operations Metrics

- CO1 – Settle market for 7 Days and provide appropriate extracts - CO2 Verify Dispute Process of 168 Hour Test - CO3 – Verify DAM Settlement Statements - CO4 – Zonal/Nodal Coordinated Settlement Operations - CO5 Verify RTM Settlement Statements - CO6 – Verify RTM Settlement Invoices - CO7 – Verify DAM Invoices - CO8 – Verify CRR Auction Invoices - CO9 – Verify Financial Transfer and Processing - C010 – Verify Credit Calculations

Congestion Revenue Rights Metrics

- CRR2 – Develop TCR to CRR Transition Plan - CRR3 – Trial operation of Monthly CRR Auction - CRR4 – Implement TCR to CRR Transition Plan - CRR5 – Trial Operation of Annual CRR Auction during Trials

ERCOT Internal Metrics

- E0 - ERCOT Engagement - E1 - ERCOT Staff Completes Training - E2 – Verify ERCOT Performance Monitoring Test Plan - E3 – Validate Telemetry/SE-EDW/MIS Access & Data Accuracy - E4 – Price Protection Mechanisms - E6 – Develop Nodal Operating Guides - E7 - Validate EDW Access & Accuracy of Postings Required by the IMM and PUCT Rules - E8 – ERCOT Staffed for Texas Nodal Operations - E10 – Validate EDW Commercial Systems Access & Accuracy - E11 – Validate EDW Compliance Data Access - E12 – MIS Compliance Test - E14 – Verify QSE Performance Monitoring Test Plan - E15 – Verify TSP Performance Monitoring Test Plan

Energy Management Operations Metrics

- EMO1 – Network Security Analysis & Transmission Constraint Management - EMO2 – Verify Voltage Support Functionality - EMO3 – Verify Outage Evaluation System Functionality - EMO5 – Verify ACE performance - EMO6 – QSE Response to Dispatch - EMO7 – Verify Load Forecast Accuracy - EMO8 – Conduct EECP Test - EMO9 – Validate Zonal and Nodal Common Constraints - EMO12 - Network Operations Model and SE Performance - EMO13 - Network Operations Model and SE Performance

IMM Metrics

- IMM1 - Market Monitor Systems Capability

Market Operations Metrics

- MO3 – Verify Supplemental Ancillary Service market (SASM) - MO4 – Verify SCED Execution Quality - MO5 – Generate LMPs for 6 months - MO7 – ERCOT Operating Personnel and Facilities Readiness

Network Model Management Metrics

- N1 – ERCOT Telemetry Alarm Processing - N2 – ERCOT Telemetry/ICCP System Failover - N3 – Validate SE performance and Accuracy - N4 – Network Modeling Single Entry

Overall Readiness Metrics

- R2 – Develop Texas Nodal Market Launch Plan

# 13.0	Appendix C:  Readiness Metrics to be completed by the end of 168-Hour test

Overall Readiness Metrics

- R3 - 168-Hour System Stability Test and Trial Real Time Settlement