## Slide 1: SEM Go-Live procedure
June 12, 2008
ROS
Linda Clarke

## Slide 2: Single Entry Model Go-Live procedure
The intent of the document is to ensure that ERCOT and Market Participants have a common understanding of the definition of Single Entry Model (SEM) Go-Live and to detail the Network Modeling activities to be performed by both ERCOT and Market Participants for each of the following Nodal milestones
Single Entry Model Go-Live
Transition to Nodal Protocol Section 3
168-Hour Test
Nodal Go-Live
What do we seek from ROS today?
NDSWG provided comments on the document and have highlighted issues which need resolution before the document can be approved
We are seeking ROS to validate ERCOT’s response to key issues raised

## Slide 3: The timeline outlined in the SEM Go-Live procedure
TPTF
Steps towards Single Entry Model
ERCOT completes EDS 2 Release 4 testing
ERCOT exports Zonal “seed” model to NMMS
ERCOT validates Model and performs Data Consistency check
NMMS application and ERCOT validated Network Operations Model deployed to Production environment
First Notice to Market Participants for enabling Nodal Protocol § 3
Second Notice to Market Participants for enabling Nodal Protocol § 3
ERCOT enables Nodal Protocol § 3

## Slide 4: ERCOT shall perform data consistency check prior to SEM Go-Live
Perform data inventory / validation
  Identify source and sink of each element within CIM
  Perform business rules validation
Perform Stage 1 data validation
  Export Zonal “seed” model to NMMS
  Add nodal information from RARFs and other sources (load zones, hubs, electrical buses etc.)
  Load model in CIM/XML format to Nodal EMS
  Perform power flow comparison between Zonal and Nodal EMS systems
  Validate SE and Contingency solutions are comparable to the Zonal EMS
Stage 2 data validation will be performed prior to Nodal Go-Live and will involve performing power flow comparison of model between Zonal EMS, Nodal EMS and Nodal MMS systems

## Slide 5: Key issues
# | Description | Proposed response
1 | TSP activities during the transition to Nodal Protocol Section 3 | During the transition period to Section 3, TSPs are required to verify Station mnemonic (ID) and name Switches operating code or number Transformers IDs and model Shunt devices capacitors and reactors Series devices capacitors and reactors Load model and ID Mapping of ICCP data to the model Connectivity of device internal to a station Association of node to connectivity groups PSS/E bus number association to the group Line names and impedances, ratings, dynamic ratings Conversion of operational model to PSS/E model …. Any more suggestions?
2 | Time required for transition to Nodal Protocol Section 3 | Based on comments received, ERCOT is proposing at least seventy five days for the transition. Once TSPs begin confirming that the above activities are being completed in their respective organizations, the actual date will be determined. In accordance with Protocol section 21.12, ERCOT will seek approval from TPTF, TAC and BOD and send first Market Notice 30 days prior to enabling Section 3, followed by a second Market Notice ten days prior to the date Can we add an upper limit to the transition timeline? 120 days, 150 days etc?

## Slide 6: Key issues contd..
# | Description | Proposed response
3 | Treatment of in flight Service Requests prior to SEM Go-Live Treatment of Approval to Energize requests | 
4 | NOMCR approval timeline during the transition period will have to be faster than Nodal Protocol Section 3.10.1 | 
5 | Additional tools training and modeling guides will have to be provided to the TSPs before SEM Go-Live | 

## Slide 7: Next Steps for the SEM Go-Live Procedure
Activity | 
Publish Whitepaper detailing CIM data validation methodology | 2 weeks?
Send out revised SEM Go-Live procedure to NDSWG and TPTF for comments | June end
Seek TPTF approval for SEM Go-Live Procedure | Mid-July
Seek TAC approval for SEM Go-Live Procedure | TAC meeting immediately following TPTF approval