|  |  |  |  | System Planning Division |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report to Reliability and Operations Subcommittee for May 2008 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
| Item |  |  |  |  |  |  |  |  |
| 1. | - ERCOT is currently tracking 240 active generation interconnection requests totaling over 106,000 MW. This includes almost 51,000 MW of wind generation - New Interconnect Agreements signed: - Jackson Mountain Wind (06INR0029) in Nolan County for 90 MW - 743 MW of new generation began commercial operation |  |  |  |  |  |  |  |
| 2. | Regional Planning is currently reviewing proposed transmission improvements with a total cost of $275.9 M. |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1.	New Generation Beginning Commercial Operations	1

1.2.	New Signed Interconnection Agreements (also found in 1.4 Table) 	1

1.3.	Summary of Active Generation Interconnection Requests	1

1.4.	Potential Future Generation Interconnections	2

2.	Regional Planning Group Project Reviews	3

3.	Other Notable Activities	4

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://oldercot.ercot.com/tmaps.

## New Generation Beginning Commercial Operations

Gas

- Laredo Peaking Power Plant for 193 MW in Webb County

- Colorado Bend 2 Combined Cycle for 275 MW in Wharton County

- Quail Run 2 Combined Cycle for 275 in Ector County

Wind

- None, however total installed capacity has increased due to reconciliation with registration forms.  The new installed wind capacity is 5,519 MW.

## New Signed Interconnection Agreements

- Jackson Mountain Wind (06INR0029) in Nolan County for 90 MW

## Summary of Active Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY BEING PROCESSED |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Currently tracking 242 active generation interconnection or change requests As of May 31, 2008 |  |  |  |  |  |
|  |  | North | South | West | Total |
| Security Screening Study |  | 5 | 10 | 15 | 30 |
| SSS Completed |  | 6 | 10 | 24 | 40 |
| Full Interconnect Study |  | 30 | 28 | 72 | 130 |
| FIS Completed |  | 0 | 3 | 0 | 3 |
| Interconnect Agreement Completed |  | 7 | 7 | 23 | 37 |
| Capacity for Grid, MW |  | 29,133 | 33,187 | 43,921 | 106,241 |
| Wind Capacity, MW |  | 2,555 | 7,763 | 40,601 | 50,919 |

| Fuel | Public(MW) | Non-Public (MW) | Total (MW) |
| --- | --- | --- | --- |
| Combined Cycle - Gas | 3,740 | 26,341 | 30,081 |
| Combustion Turbine - Gas | 505 | 400 | 905 |
| Nuclear | 9,186 | 6,400 | 15,586 |
| Coal | 4,131 | 4,144 | 8,275 |
| Wind | 10,090 | 40,829 | 50,919 |
| Other |  | 475 | 475 |
| Totals | 27,652 | 78,589 | 106,241 |

## Potential Future Generation Interconnections

The table below summarizes the publicly known potential future generation projects for the ERCOT region.  (IA=Interconnect Agreement, PL=Public Letter)

| # Future Generation Interconnections (Public Projects) as of May 31, 2008 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INR | SiteName | Status | County | Region | Fuel | In-Service Date | MW Into Grid | Change from Last Report |  |
| 07INR0027 | South Houston Green Pwr Exp Prj1 | IA | Galveston | South | Gas-CC | Jun-08 | 244 |  |  |
| 07INR0022 | Airtricity Panther Creek Wind Farm | IA | Howard | West | Wind | Jun-08 | 150 |  |  |
| 08INR0028 | McAdoo Energy Center | IA | Dickens | North | Wind | Jul-08 | 300 |  |  |
| 08INR0050 | Victoria Power Station | IA | Victoria | South | Gas-CC | Jul-08 | 332 | Date Chg |  |
| 03INR0030b | Wild Horse Wind Farm 2 | IA | Cottle | West | Wind | Aug-08 | 39 |  |  |
| 04INR0017 | Ocotillo Wind Farm 1 | IA | Howard | West | Wind | Aug-08 | 59 |  |  |
| 04INR0011b | Mesquite Wind Phase 4 | IA | Shackelford | West | Wind | Aug-08 | 136 |  |  |
| 04INR0011c | Cottonwood Wind | IA | Shackelford | West | Wind | Aug-08 | 100 |  |  |
| 08INR0055 | Capricorn Ridge III | IA | Coke | West | Wind | Aug-08 | 249 |  |  |
| 06INR0012a | Sherbino Mesa Wind Farm 1 | IA | Pecos | West | Wind | Sep-08 | 150 |  |  |
| 08INR0038 | M Bar Wind | PL | Andrews | West | Wind | Sep-08 | 194 |  |  |
| 07INR0034 | Wolf Ridge Windfarm | IA | Cooke | North | Wind | Oct-08 | 113 |  |  |
| 07INR0025 | Airtricity Lamesa Wind Plant | IA | Dawson | West | Wind | Oct-08 | 183 |  |  |
| 07INR0037 | Bull Creek Wind Plant | IA | Borden | West | Wind | Oct-08 | 180 |  |  |
| 07INR0045b | Airtricity Inadale | IA | Scurry | West | Wind | Nov-08 | 212 |  |  |
| 07INR0045a | Airtricity Pyron Wind Farm | IA | Scurry | West | Wind | Nov-08 | 303 |  |  |
| 05INR0015a | Gulf Wind 1 | IA | Kenedy | South | Wind | Dec-08 | 283 |  |  |
| 06INR0022a | Penascal Wind Farm 1 | IA | Kenedy | South | Wind | Dec-08 | 202 |  |  |
| 07INR0005 | Notrees-1 | IA | Ector | West | Wind | Dec-08 | 151 |  |  |
| 04INR0011e | Hackberry Wind Farm | IA | Shackelford | West | Wind | Dec-08 | 165 |  |  |
| 07INR0011 | Turkey Track Energy Center | IA | Nolan | West | Wind | Dec-08 | 170 |  |  |
| 07INR0029 | South Trent Wind Farm | IA | Taylor | West | Wind | Dec-08 | 101 |  |  |
| 08INR0018 | Gunsight Mountain | IA | Howard | West | Wind | Dec-08 | 120 |  |  |
| 08INR0025 | Pistol Hill Energy Center | PL | Ector | West | Wind | Dec-08 | 300 |  |  |
| 08INR0037 | Airtricity Panther Creek 2 | IA | Howard | West | Wind | Dec-08 | 220 |  |  |
| 08INR0053 | Elbow Creek Wind Project | IA | Howard | West | Wind | Dec-08 | 117 |  |  |
| 08INR0059 | Gray Wind Project | PL | Borden | West | Wind | Dec-08 | 141 |  |  |
| 09INR0026a | Sterling Energy Center | PL | Sterling | West | Wind | Dec-08 | 200 |  |  |
| 08INR0046 | Bosque Expansion | IA | Bosque | North | Gas-CC | Mar-09 | 255 |  |  |
| 07INR0036 | Coyote Run Windfarm | IA | Borden | West | Wind | Mar-09 | 225 |  |  |
| 08INR0065 | Buffalo Gap 4 and 5 | PL | Nolan | West | Wind | Mar-09 | 465 |  |  |
| 09INR0072 | Dansby3 | PL | Brazos | North | Gas-CT | Apr-09 | 48 | New PL |  |
| 09INR0028 | V H Braunig 6 | PL | Bexar | South | Gas-CT | May-09 | 185 |  |  |
| 08INR0040 | Lenorah Project | PL | Martin | West | Wind | May-09 | 350 |  |  |
| 09INR0060 | Wind TexStephens WindFrm | PL | Borden | West | Wind | May-09 | 141 |  |  |
| 08INR0035 | Cedar Bayou 4 | IA | Chambers | South | Gas-CC | Jun-09 | 539 | MW adj |  |
| 09INR0026 | Sterling Energy Center | PL | Sterling | West | Wind | Jun-09 | 300 |  |  |
| 09INR0036 | McAdoo Energy Center II | PL | Dickens | West | Wind | Jun-09 | 500 |  |  |
| 09INR0006a | Oak Grove SES 1 | IA | Robertson | North | Coal | Jul-09 | 855 | Date adj |  |
| 08INR0003 | Sandow 5 | IA | Milam | North | Coal | Jul-09 | 581 |  |  |
| 09INR0027 | Winchester Power Park | IA | Fayette | South | Gas-CT | Jul-09 | 178 | Date adj |  |
| 05INR0015b | Gulf Wind 2 | PL | Kenedy | South | Wind | Sep-09 | 400 |  |  |
| 09INR0015 | Comanche Peak 1&2 Upgrade | PL | Somervell | North | Nuclear | Oct-09 | 86 |  |  |
| 09INR0045 | Sand Hill Peakers | PL | Travis | South | Gas-CT | Nov-09 | 94 | Date/MW adj |  |
| 03INR0030a | Wild Horse Wind Farm 1 | IA | Cottle | West | Wind | Nov-09 | 60 |  |  |
| 09INR0034 | Gatesville Wind Farm | PL | Coryell | North | Wind | Dec-09 | 200 |  |  |
| 09INR0006b | Oak Grove SES 2 | IA | Robertson | North | Coal | Jan-10 | 855 | Date adj |  |
| 06INR0029 | Jackson Mountain | IA | Nolan | West | Wind | Jan-10 | 90 | New IA |  |
| 09INR0037 | Scurry County Wind III | PL | Scurry | West | Wind | Mar-10 | 350 |  |  |
| 06INR0006 | Cobisa-Greenville | PL | Hunt | North | Gas-CC | May-10 | 1,750 |  |  |
| 09INR0002 | J K Spruce 2 | IA | Bexar | South | Coal | Jun-10 | 750 |  |  |
| 05INR0015c | Gulf Wind 3 | PL | Kenedy | South | Wind | Sep-10 | 400 |  |  |
| 06INR0012b | Sherbino Mesa Wind Farm 2 | IA | Pecos | West | Wind | Oct-10 | 150 |  |  |
| 06INR0026 | Wild Horse Mountain | IA | Howard | West | Wind | Dec-10 | 120 |  |  |
| 12INR0003 | Throckmorton Wind Farm | PL | Throckmorton | West | Wind | Dec-10 | 400 |  |  |
| 10INR0010 | Jack County 2 | PL | Jack | North | Gas-CC | Jun-11 | 620 |  |  |
| 07INR0004 | Pampa Energy Center | PL | Gray | West | Coal | May-12 | 165 |  |  |
| 09INR0001 | Sandy Creek 1 | IA | McLennan | North | Coal | Jun-12 | 925 | Date adj |  |
| 09INR0024 | B&B Panhandle Wind | PL | Carson | West | Wind | Jun-12 | 1,001 |  |  |
| 12INR0004 | Fort Concho Wind Farm | PL | Tom Green | West | Wind | Jul-12 | 400 |  |  |
| 15INR0002 | Comanche Peak 3 and 4 | PL | Somervel | North | Nuclear | Jan-15 | 3,200 |  |  |
| 15INR0008 | STP 3 and 4 | PL | Matagorda | South | Nuclear | Jan-15 | 2,700 |  |  |
| 11INR0011 | Victoria City Nuclear | PL | Victoria | South | Nuclear | Jan-15 | 3,200 |  |  |

# Regional Planning Group Project Reviews

# Oncor submitted a project to construct the Krum Tap Switching Station and rebuild the Krum – Decatur 69 kV line and the Krum Tap 138 kV line as a 138 kV double-circuit line with one circuit in place using a conductor with a minimum rating of 214 MVA. The estimated cost of this project is $17.8 M. The review of this project has been completed and the RPG Acceptance letter was distributed on May 19th, 2008.

# LCRA submitted a project to add a 3rd 345/138 kV autotransformer at the Zorn substation.  This project should be complete by summer peak 2013 and cost is estimated at $15 M.  This project is currently in ERCOT Independent Review.

# AEPSC submitted a project to increase the reliability of service in the Presidio area.  This project will install a second 138/69 kV autotransformer at Marfa in 2008, install 2-2.4 MW NaS battery units at Presidio in 2009, and replace the existing 69 kV line with a 138kV-capable but 69kV-operated line from Alamito Creek to Chinati to Presidio in 2012.  Total cost of the project is estimated to be $67 M.  This project is currently in ERCOT Independent Review.

# CNP Energy submitted a 2007 Five-Year Plan project to install a new 345/138 kV substation called Rothwood to eliminate potential unserved energy under contingency scenario(s).  The projected completion date is summer 2010 with an estimated cost of $23 M.  The review of this project is complete with ERCOT Board of Directors recommendation on May 20th, 2008.

# Oncor submitted a project to upgrade the Hillsboro to Alvarado 69 kV line.  This project will reconstruct the 27.2 mile line using conductor rated a minimum of 897 amperes on double circuit structures.  The estimated cost is $12.15 M.  This project is currently in ERCOT Independent Review.

# Oncor submitted a project to add a 300 Mvar dynamic reactive device at Renner station (tentative) by summer 2010.  This cost of this project will be $35 M.  This project is in ERCOT Independent Review.

# American Electric Power Service Corporation submitted a project to construct 2 new 138 kV substations, rebuild a 138 kV circuit, build  2 new 138 kV circuits, and install a new 138/69 kV autotransformer in the Abilene/San Angelo area.  The estimated cost of this project is $105.9 M.  This project is currently in the comment period.

# Other Notable Activities

- All postings referred to below can be found at http://oldercot.ercot.com/tmaps unless otherwise indicated.

- TPIT Report was filed on June 1, 2008