## Sheet1
# | Raised By | Pg | Section | Question | Response | Comments
1 | Luminant | 4 | 1 | The 168 Hour Test is a full rehearsal of the Nodal Day-Ahead Market, Adjustment Period and Real Time Operations Market and Nodal Operations Security Sequence during a continuous week long period and will include a systems stability test. During this test the ERCOT Market will continue to conduct actual operations and settlement in accordance with the Zonal Protocols. ERCOT and Market Participants who are engaged in the 168 Hour Test are required to continue zonal market operations and participate in the 168 Hour Test. | Accepted
2 | REP Nodal Group | 5 | 2 | ERCOT certifies that the readiness metrics listed in Appendix B have successfully been completed—REP Nodal Group: but for many of the Appendix 2 Metrics to be completed, the results of the 168 hour test have to be completed and analyzed- e.g. CO1, CO2, CO3--?? Comments: but for many of the Appendix 2 Metrics to be completed, the results of the 168 hour test have to be completed and analyzed- e.g. CO1, CO2, CO3--?? | Clarification | Metrics Co1, Co2 etc will have to be completed by the end of EDS 4
3 | REP Nodal Group | 5 | 3 | ERCOT provides a test summary report to TPTF outlining the successful testing processes Comment: Will this be daily, as the Test is progressing? MP personnel dedicated to the 168 hour test should get quick feedback so that they can plan their activities - such as when the Test will be re-started, etc. | Clarification | As listed in section 7.0 of the document, ERCOT will conduct daily conference calls to discuss new issues, resolutions and general progress In addition, the test summary report will be updated throughout the test and will be published to the TPTF upon completion of the test
4 | REP Nodal Group | 6 | 3 | ERCOT certifies that readiness metric R3 has been successfully completed Comment: recommend more precise wording, such as “successfully satisfied the requirements and test criteria under Metric R3.” Also, the appropriate Metrics (from Appendix B) should also be mentioned-- Some of the Metrics in Appendix B (such as CO 1, CO2, CO3) are to be completed with successful completion of 7 day test, not before start of the Test.. | Accepted
5 | REP Nodal Group | 6 | 3 | ERCOT provides a plan to TPTF to resolve any Market Participant comments on the settlement and invoice statements for the period covered by the successful 168-Hour Test Comment: Need more definition here. If these issues occur, they would be as a result of systems problems. Perhaps TPTF should further define success here, as accuracy/discrepancies are critical here and should be covered by some form of Metric or testing requirements. Further, if extracts/files are not available, then no amount of testing can verify. Extracts/Files: there should be mention in this document about which extracts and reports will be made available other than Test settlement statements and invoices. Which additional reports and extracts will be included in the 168 hour test? | Clarification | ERCOT will publish DAM and RTM settlement statements, invoices and extracts. All reports, statements and extracts will follow the normal market timeline as listed in the Nodal Protocols.
6 | Reliant | 6 | 5 | All ERCOT systems shall be under strict change control procedures administered by the Director of Operations and Infrastructure and Nodal Executive Director. No software changes to ERCOT systems will be implemented during the 168 -Hour Test without stopping testing and starting a new 168 hours of testing. Comment: It seems that no hardware changes should be allowed as well as any software changes. | Clarification | If application servers fail in the active environment during the 168-hour test,we expect standby site to become operational instantaneously without disrupting testing. This is a part of normal operations
7 | REP Nodal Group | 6 | 4 | Comment: How will the data for testing be defined for this Test? This is critical so that all MPs and ERCOT are on the same page and for Test results evaluation. Also, when re-starting the 168 hour test, any change in the Nodal systems will potentially impact MPs and ERCOT and any testing results. | Accepted | Section 4.0 has been added to address data needs for the 168-Hour test
8 | REP Nodal Group | 7 | 5.1 | Failures of physical hardware that effect operations functionality will be cause to re-start the 168-Hour Test. Comment: suggest that “hardware” be more closely defined, e.g. communication components, servers, etc. | Accepted
9 | REP Nodal Group | 7 | 5.2 | Comment: This effort can only be as good as the controlled updates applied by ERCOT during the Test. If ERCOT makes changes, then that must be known by all MPs otherwise MPs cannot tell if it is a code issue, bad data issue, or a processing issue. That is, no matter how small the fix employed by ERCOT, it should be considered that it would have an impact on MPs and the various operational models interacting with ERCOT. | Accepted | Please see last sentence under Section 4.0. All MPs will be notified in conjunction to implementing a change in ERCOT systems during the 168-hour test
10 | Direct Energy | 7 | 6 | Comment: We believe this section is not descriptive enough to help MPs fully understand the procedures and requirements of 169-Hour Test. This section needs to be expanded to disclose more details, such as MP’s activities (before, during and post test) in each system (DAM, DRUC, Adjustment Period, HRUC, SASM, RT, Outage Scheduler, etc.) | Clarification | QSEs are required to follow the requirements outlined in Nodal Protocols Section 3,4,5 and 6 for DAM, Adj Period and RT Ops. In addition, Section 6.0 of the document details the 7x24 operations expectations from each category of Market Participants during the 168-Hour test. Once the 168-Hour test is complete, the TAC approved Nodal Go-Live procedure will have to be followed.
11 | Direct Energy | 7 | 6 | Comment: The settlement piece in this document is confusing. Will MPs be settled using nodal data after the 168-Hour Test, but receive regular zonal invoices? Will the mock nodal invoices just for MPs review? What settlement system ERCOT will use for the period if ERCOT discontinues the 168-Hour Test due to Severity Level 1 or 2 defects? | Clarification | All financially binding settlements will be from zonal operations. All statements and invoices being published out of Nodal during the 168-Hour test are for test purposes only and are non-binding. Nodal does not control the grid during the 168-Hour test and all DAM, Adj Period and RT operations conducted during the 168-hour test are test only MPs should review the 168-hour test settlement statements for accuracy and communicate to ERCOT Helpdesk or their client services representative if there are any issues.
12 | Direct Energy | 7 | 6 | Comment: Will you please add the explanation of Severity Level 1, 2, 3 and 4 defects somewhere on the document, maybe in the footnote? | Clarification | Please see Appendix A of the document
13 | Luminant | 7 | 6 | Added: The 168 Hour Test shall always commence at hour beginning 0000 hrs of an Operating Day and end on an Operating Day at hour ending 2400 hrs. The 168 Hour Tests may not end on a Saturday or Sunday Operating Day. | Rejected | If issues are encountered in RT operations, then ERCOT will restart the clock at 0000 hours of the next day.
14 | Luminant | 7 | 7 | Rename Section 6 to 7X24 operations | Accepted with changes | Changed section to Operations Requirements as all categories of Market Participants do not need to support 168-Hour test 7x24
15 | Luminant | 8 | 7.1 | ERCOT shall produce test DAM Settlement Statements, Settlement Invoices and Shadow Settlement Extracts for all Market Participants registered to participate in the nodal market design according to the settlement timelines in the Protocols. ERCOT shall produce test Real Time Initial Settlement Statements, Settlement Invoices and Shadow Settlement Extracts for all Market Participants registered to participate in the nodal market design according to the settlement timelines in the Protocols. | Accepted
16 | Luminant | 8 | 7.1 | Data upload process for generation data will follow the currently-established timeline and will be uploaded into nodal settlements systems synchronously (or near synchronously) with updating the zonal settlements systems | Accepted
17 | Luminant | 8 | 7.2 | Deleted: During the 168-Hour Test, QSEs representing Generation Resources must participate in the DAM AS testing seven (7) days per week Changed to: During the 168-Hour Test, QSEs representing Generation Resources offering AS capacity into the zonal market must also offer that AS capacity in the 168 Hour Test DAM (pricing may be unique to each of the zonal or nodal markets). QSEs with load who are buying AS capacity from ERCOT in the zonal market shall buy the same AS capacity from ERCOT in the 168 Hour Test DAM | Accepted
18 | Luminant | 8 | 7.2 | QSEs may also submit energy-only offers and bids into the test operation of DAM; if made, such offers and bids must reasonably represent true current market conditions. | Accepted
19 | Luminant | 8 | 7.2 | Forced Outages of Resources or changes to a Resource’s capability occuring should occur during the test , the QSE should be report should be reported in accordance with zonal protocols such in the COP and through Real Time Telemetry. | Accepted with changes | Forced Outages of Resources or changes to a Resource’s capability occuring during the test should be reported in accordance with Nodal protocols such in the COP and through Real Time Telemetry.
20 | Luminant | 9 | 7.3 | If the QSE qualifies its Load Resources to offer Ancillary Service, the QSE should make AS offers during the 168-Hour Test DAM that are reasonably representative of those expected after the TNMID. During the 168-Hour Test, QSEs are requested to maintain valid offers for Ancillary Service in the DAM which should be reasonably representative of the amounts expected after Go-Live. QSEs representing Load Resources offering AS capacity into the zonal market must also offer that AS capacity in the 168 Hour Test DAM (pricing may be unique to each of the zonal or nodal markets). | Accepted
21 | REP Nodal Group | 10 | 7.6 | During the 168-Hour Test, ERCOT requires QSEs without Resources or Loads, who expect to participate in the DAM after the TNMID to participate in the DAM testing. QSEs should provide ERCOT with DAM bids for energy, test offers or bids for Point-to-Point (PTP) Obligations, Energy Trades, Capacity Trades, etc. representing true market conditions. Comment: Also, should these QSEs (and perhaps all QSEs) submit Test Disputes --- to test Metric CO3, and per section 6.1 herein?? | Clarification | QSEs are encouraged to submit Disputes to test the Disputes process .
22 | CNP | 10 | 7.6 | At ERCOT’s request, all TSPs shall review ERCOT’s model of the TSP’s system and provide ERCOT with assistance in verifying the modeling of any Private Networks that connect to the TSPs system Comment: CenterPoint Energy does not have access to Private Use Network information. Centerpoint will assist ERCOT in verifying inter-connectivity information associated with specific PUNs. Here is a suggested change: Suggested change: At ERCOT’s request, all TSPs shall review ERCOT’s model of the TSP’s system and provide ERCOT with assistance in verifying the inter-connectivity modeling of any Private Networks that connect to the TSPs system. | Accepted
23 | Luminant | 10 | 8 | Rename Section 7 to 168-Hour Test Communication Plan | Accepted
24 | Luminant | 10 | 8 | ERCOT shall post to the MISQuality Center on nodal.ercot.com, within a reasonable time after receiving notice of an issue | Accepted
25 | Luminant | 10 | 8 | Deleted: A summary listing of all Severity 1, 2, 3, 4 and 5 defects shall be provided to Market Participants upon their request. ERCOT will summarize all trend indicators Changed to: The quality Center shall also maintain a summary listing of all Severity 1, 2, 3, 4 and 5 along with appropriate trend indicators | Accepted
26 | Luminant | 11 | 11 | Deleted: A test CRR Auction will be provided prior to the 168-Hour Test which will offer CRRs that will be effective for the duration of the tests required to successfully complete the testing requirements. Added: A test CRR Monthly Auction will be conducted prior to the 168-Hour Test. The auction results are financially non-binding and CRRs procured through this auction will be effective only for the duration of the 168 Hour Test | Accepted
27 | Luminant | 11 | 11 | The test CRR auction will may be conducted as part of CRR EDS activities during EDS 3 Release 7.5 | Accepted
28 | REP Nodal Group | 13 | 13 | 12.0 Appendix B: Readiness Metrics to be completed before start of 168-Hour test Comment: some of these are to be completed with successful completion of 168 hour test, not before start of the Test- like CO1. | Clarification | Metrics Co1, Co2 etc will have to be completed by the end of EDS 4