## Slide 1: Texas Nodal Market Implementation: Program Update
Jerry Sullivan

## Slide 2: Agenda
Program Status
  Overall Status
  ERCOT Staff / Market Participant Readiness
Schedule Revision
  Planning Considerations
  Plan Forward Update
Key Concerns
  Areva (CIM) Status / Impact
  TSP Data Validation: Single Entry Model Go-Live Procedure
  Other Risks
Cost

## Slide 3: Program Status: Overall Status
`
Nodal Delivery status is:
ERCOT Staff Readiness status is:
Market Participant Readiness status is:
Cost
Schedule
Scope / Quality
Nodal Delivery
Amber status driven by Cycle 4 Survey results (engagement and training), EDS 3 trials participation, and new entrants to the market
Changed due to schedule impact
Primary Indicators
Secondary Indicators
Red
Amber
Green
Amber
Red
Amber
Green
EDS1
Red
EDS2
Amber
EDS3
Red
EDS4
Amber status driven by staffing and training metrics
* Slippage beyond Dec. 1 has cost implications
Amber*
 | Red | Amber | Green
Scope | Program is not aligned to protocols | Program is aligned to previous protocol versions | Program is aligned with current protocols
Quality | Current product quality is not sufficient for Nodal launch | Most Nodal products currently achieve quality standards | All Nodal products currently achieve quality standards
Schedule | Go-Live => 30 days+ | Go-Live =< 30 days+ | Go-Live = 12/1/2008
Cost | Estimate at Complete => 319M +10% | Estimate at Complete =< 319M +10% | Estimate at Complete =< 319M
Notes: <number>

## Slide 4: Program Status: ERCOT Staff
Engagement (green)
  new survey results came out at the end of May - ERCOT remains fully engaged
Training (amber)
  two departments in the IT division and one department in System Planning are behind scheduled training levels
  actively recruiting SMEs
Process (green)
  updated weekly
Staffing (amber)
  ERCOT is currently ~92% staffed
  (95% required for green status)
  recruitment is ongoing
Testing (green)
  no recent developments
ERCOT Staff Readiness status is AMBER
Notes: ASK KAREN – 1) staffing = 95% of total or of where we’re supposed to be now? Need change for DECEMBER 1? 2) training based on DEC 1? 3) still 92%?

## Slide 5: Program Status: Market Participants
Cycle 4 Survey
100% survey completion from TDSPs and QSEs with Resources
72% response from QSEs w/o Resources
67% response from LSEs
Market Participant Readiness status is AMBER
Engagement (amber)
  limited survey response drives amber status
Connectivity (amber)
  updated MP2 and MP3 data reflective of new additions to the market
Registration and Qualification (amber)
  MP10 (resource mapping) has improved steadily since the last meeting
  MP11 (RARF data) – only 6 RARFs have not been received (less than 0.5% of MWs), 83% of MWs have passed the second tier review
Telemetry (green)
  no change
Training (amber)
  limited survey response drives amber status
Trials Participation (amber)
  updated MP15 data (EDS 3 trials participation based on TPO and COP) drives amber status

## Slide 6: Schedule Revision: Planning Considerations
A clear, achievable delivery date
ERCOT wait until the EMS CIM Importer is thoroughly tested before committing to a new "go-live" date
Implementation will include both the Real-Time Market and the Day-Ahead Market, as originally planned
ERCOT review incorporating deferred items for the Dec. 1 date
Sufficient testing time for TSPs and QSEs is needed in the new "go-live" date
Sufficient time to validate the network operating model for TSPs
ERCOT provide a draft of the new integrated schedule to TPTF for review and comments
TPTF has made several recommendations about how to proceed with planning efforts. ERCOT will consider:
Notes: <number>

## Slide 7: Schedule Revision: Plan Forward
Process
  Dedicate a team to drive development of the new schedule (Complete)
  Standardize templates for individual project schedules, including all transition activities (Complete)
  Re-estimate the durations of all project activities based on historical data (In Progress)
  Identify comprehensive list of dependencies and link across project schedules, allowing schedules across projects to be dynamically generated as changes occur (In Progress)
  Develop the integrated master Nodal program schedule (In Progress)
  Review the schedule and options with TPTF and ERCOT (Pending)
Timeline
  The date for setting a new schedule date has not been finalized, but the team understands the sense of urgency as well as the importance of a realistic plan
ERCOT is aggressively working to develop a revised integrated Nodal program schedule that is realistic and achievable
Notes: <number>

## Slide 8: In the meantime…
Support for ongoing activities
  NPRR analysis
  Design and development
  Integration testing
  Data validation
  Documentation
  Training
  Other high-value activities
Improving processes and infrastructure
  Establishing Nodal Integrated Release 1.0, the baseline integrated testing environment inclusive of all Nodal applications and supporting infrastructure
  Improving release management process, build promotion strategy and requirements
  Improving data quality
ERCOT also continues delivery of high-value activities and improvements to processes and infrastructure
Notes: <number>

## Slide 9: AREVA (CIM): Status and Impact
The CIM Importer has not completed Pre-FAT due to missing data and CIM Importer development issues. Resolving the open issues is an iterative process
  exporting the data
  Identifying the errors (code or data (AREVA or ERCOT)
  fixing the issue
  re-exporting……
A new completion date will be provided once the iteration cycles decline
ERCOT technical team at AREVA the week of June 16th providing testing support and helping to resolve missing data in the NMMS CIM XML file
Not to scale
Today
May 2, Previous commitment of EMS CIM Delivery Date
June 27
delivery date
stated at
June BoD
meeting
Go-Live Period
Original Planned Integration Activities
Critical Schedule Events/Activities
168-Hour
Test
Go Live Date
Post Go Live Activities
June 13
delivery date stated at
May BoD
Meeting
Notes: <number>

## Slide 10: TSP Data Validation: Single Entry Model Go-Live Procedure
Single Entry Model (SEM) Process
  Model creation and data validation – ERCOT
  NMMS Tool (SEM) Go-Live – ERCOT
  Data/model validation - TSPs
  Transition to Nodal Protocol Section 3.10 for Network model maintenance
Current Status
  Published Single Entry Model Go-Live Procedure V0.03 for comments
  Compiling comments received from Network Data Support Working Group (NDSWG)
  Discussed key issues on the Procedure with ROS on June 12th
  Attended NDSWG meeting on June 17th and agreed on next steps for the procedure
Next Steps
  Meeting scheduled on June 27th with the Network Data Support Working Group to discuss TSP data/model validation activities prior to transition to Nodal Protocol Section 3
  Revise Procedure based on NDSWG feedback and seek TPTF approval
Notes: <number>

## Slide 11: Other Risks
Majority of vendor software releases have been received; outstanding releases include:
  NMMS (2 releases)
  MMS 5 (+ 2 known major patches to MMS4)
    MMS 5 scheduled due to CIM importer delays
    Will require additional FAT and Regression test cycles
Integration components have been designed and coded, but not completely delivered
  Risk of refactoring due to changes in upstream software remains high
  Total number of components fully tested remains low
Further NPRRs need to be closely evaluated for scope changes and impact to schedule
Other risks continue to be addressed by the program
Notes: <number>

## Slide 12: Cost: Element Summary
*Does not include impacts of schedule change